## Summary & Notes
裁料排程 Cutting Schedule (鱼与熊掌版)
生成日期 Generated: 2026-06-01 批次窗口 Window: 每 7 天（一周）
【这次的排法 —— 又快又不让别款 overdue】
你讲得对:不能把一个款『全部』单一次过剪完,不然 1007 剪完 36 张,别的款全 overdue 了。
所以这版是这样平衡的:
1. 先按『交期那一周』分段 —— 这周该交的先剪,下周的下周剪,不会把下个月的拉上来抢产能。
2. 在『同一周』里面,才把同款的单併在一起剪(省一次开料设定),剪得快。
3. 所以一个款(例如 1007)的单会按它各自的交期,分散到各周;不会全部塞在最前面。
4. 最前面是「OVERDUE / 这周」那一段 —— 已经到期 / 这周到期的,全部先剪(橙色)。
5. 数量一律 1。
【日期 —— 用回你系统的两个真实日期】
· Customer DD = 顾客交货日（跟系统一样）。Our Expected DD = 我们内部预计做好日（跟系统一样）。
· 分周、排先后,都是看 Our Expected DD（我们自己的目标日）。
· 已经把上一版我自己算的『Planned Ready』拿掉了,只剩你系统里的真实日期。
【数字一览】
在排总行数 Active rows: 262
裁料窗口段数 Windows: 6 裁料批次数 Cut groups: 70
会分到多周剪的款(没有全塞在前面)Split across weeks: 1003(A), 1005, 1007, 1013, 1030, 2006(A), 2008(A), 2009(A), 2038(A), 2041(A), 5530, 5531, 5535, 5536, 5540, DIVAN
【可调 —— 一句话就能改】
· 现在窗口是『一周』。想剪得更集中(同款拉更多张一起)→ 改成两周;想更贴紧交期 → 改成几天。你说一声我就调。
· 如果你要一张『每天剪哪几个款』的逐日表(用 床架 6 款/天、沙发 2 款/天 的产能算),我也能出 —— 那张会有我算的日期,你之前不太信那种,所以先做这版只用真实交期的。
【分页】
· Cut Order：逐张单,按裁料先后;同款同色一条带。Window 栏 = 该周交期段。
· Batch Summary：每个裁料批次一行 —— 第几个剪、哪一周、哪个款、几张单。先看这页定先后。
注:只读了线上资料来做,没有改动系统任何东西。

## Cut Order
Window (deadline) | Cut # | Model | SO / CO No | Customer | Item (one set per row) | Fabric | Qty | Customer DD | Our Expected DD | Status
0) OVERDUE / this week — cut first | 1 | LONG PILLOW | SO-2604-083-04 | Carress | LONG PILLOW | KN390-2 | 1 | 2026-04-15 | 2026-04-14 | PENDING
0) OVERDUE / this week — cut first | 1 | LONG PILLOW | SO-2604-083-05 | Carress | LONG PILLOW | KN390-2 | 1 | 2026-04-15 | 2026-04-14 | PENDING
0) OVERDUE / this week — cut first | 1 | LONG PILLOW | SO-2605-063-03 | Houzs Century | LONG PILLOW | BO315-31 | 1 | 2026-05-25 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 1 | LONG PILLOW | SO-2605-063-04 | Houzs Century | LONG PILLOW | BO315-31 | 1 | 2026-05-25 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2604-092-03 | Houzs Century | SQUARE PILLOW | CH141-5 | 1 | 2026-04-29 | 2026-04-28 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2604-210-03 | Houzs Century | SQUARE PILLOW | AM275-2 | 1 | 2026-05-04 | 2026-05-02 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2604-088-03 | Houzs Century | SQUARE PILLOW | BO315-31 | 1 | 2026-05-04 | 2026-05-03 | ON_HOLD
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2604-324-03 | Houzs Century | SQUARE PILLOW | BO315-22 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2604-324-04 | Houzs Century | SQUARE PILLOW | BO315-22 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2605-104-04 | Houzs Century | SQUARE PILLOW | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2605-104-05 | Houzs Century | SQUARE PILLOW | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2605-104-06 | Houzs Century | SQUARE PILLOW | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2605-222-03 | Houzs Century | SQUARE PILLOW | CH141-7 | 1 | 2026-05-30 | 2026-05-29 | PENDING
0) OVERDUE / this week — cut first | 2 | SQUARE PILLOW | SO-2605-222-04 | Houzs Century | SQUARE PILLOW | CH141-5 | 1 | 2026-05-30 | 2026-05-29 | PENDING
0) OVERDUE / this week — cut first | 3 | 5530 | SO-2604-088-01 | Houzs Century | 5530-1A(LHF)+1A(RHF)+1A(LHF)+1A(RHF) | BO315-21 | 1 | 2026-05-04 | 2026-05-03 | ON_HOLD
0) OVERDUE / this week — cut first | 3 | 5530 | SO-2604-086-01 | Houzs Century | 5530-2A(RHF)+L(LHF) | BO315-12 | 1 | 2026-05-11 | 2026-05-10 | PENDING
0) OVERDUE / this week — cut first | 3 | 5530 | SO-2604-265-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | CH141-13 | 1 | 2026-05-16 | 2026-05-14 | PENDING
0) OVERDUE / this week — cut first | 3 | 5530 | CO-2605-008-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | PC151-01 | 1 |  | 2026-05-15 | PENDING
0) OVERDUE / this week — cut first | 3 | 5530 | SO-2605-063-01 | Houzs Century | 5530-2A(LHF)+L(RHF)+1NA | BO315-31 | 1 | 2026-05-25 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 3 | 5530 | SO-2605-050-01 | Houzs Century | 5530-1A(LHF)+1A(RHF) | BO315-1 | 1 | 2026-05-30 | 2026-05-28 | PENDING
0) OVERDUE / this week — cut first | 3 | 5530 | SO-2605-109-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | BO315-21 | 1 | 2026-06-01 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 4 | 5537 | SO-2603-207-01 | Houzs Century | 5537-1A(LHF)+1A(RHF) | CH141-1 | 1 | 2026-05-04 | 2026-05-03 | PENDING
0) OVERDUE / this week — cut first | 5 | 2041(A) | SO-2604-276-03 | Houzs Century | 2041(A)-(SS) | PC151-02 | 1 | 2026-05-13 | 2026-05-11 | PENDING
0) OVERDUE / this week — cut first | 5 | 2041(A) | SO-2605-010-02 | Houzs Century | 2041(A)-(Q) | PC151-11 | 1 | 2026-05-30 | 2026-05-28 | PENDING
0) OVERDUE / this week — cut first | 5 | 2041(A) | SO-2605-131-05 | Houzs Century | 2041(A)-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-023-01 | Houzs Century | 1007-(K) | PC151-01 | 1 | 2026-05-18 | 2026-05-16 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-009-01 | Houzs Century | 1007-(K) | PC151-01 | 1 | 2026-05-22 | 2026-05-20 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-160-02 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-161-01 | Houzs Century | 1007-(Q) | PC151-11 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-167-01 | The Conts | 1007-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-205-01 | Houzs Century | 1007-(S) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-205-02 | Houzs Century | 1007-(S) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 6 | 1007 | SO-2605-234-03 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-02 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 7 | DIVAN | SO-2605-011-01 | Houzs Century | DIVAN-(K) | KS-02 | 1 | 2026-05-18 | 2026-05-16 | PENDING
0) OVERDUE / this week — cut first | 7 | DIVAN | SO-2604-300-01 | Houzs Century | DIVAN-(Q) | PC151-01 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 7 | DIVAN | SO-2605-131-04 | Houzs Century | DIVAN-(K) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 8 | 1023(HF)(W) | SO-2604-321-03 | Houzs Century | 1023(HF)(W)-(SS) | PC151-02 | 1 | 2026-05-21 | 2026-05-19 | PENDING
0) OVERDUE / this week — cut first | 9 | 2008(A) | SO-2605-162-01 | Houzs Century | 2008(A)-(K) | PC151-10 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 9 | 2008(A) | SO-2605-098-03 | Houzs Century | 2008(A)-(Q) | PC151-02 | 1 | 2026-05-29 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 9 | 2008(A) | SO-2605-098-04 | Houzs Century | 2008(A)-(Q) | PC151-02 | 1 | 2026-05-29 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 9 | 2008(A) | SO-2605-208-01 | Houzs Century | 2008(A)-(K) | PC151-04 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 9 | 2008(A) | SO-2605-234-01 | Houzs Century | 2008(A)-(K) | PC151-03 | 1 | 2026-06-02 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 10 | 2011(A) | SO-2605-171-01 | Houzs Century | 2011(A)-(K) | KS-18 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 11 | 5540 | SO-2604-324-01 | Houzs Century | 5540-2A(LHF)+1A(RHF) | BO315-22 | 1 | 2026-05-25 | 2026-05-23 | PENDING
0) OVERDUE / this week — cut first | 11 | 5540 | SO-2605-078-01 | Houzs Century | 5540-L(LHF)+CSL+2A(RHF) | BO315-23 | 1 | 2026-05-25 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 11 | 5540 | SO-2605-108-01 | Houzs Century | 5540-2S | BO315-21 | 1 | 2026-05-25 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 11 | 5540 | SO-2605-064-01 | Houzs Century | 5540-1A(LHF)+2A(RHF) | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 11 | 5540 | SO-2605-221-01 | Houzs Century | 5540-1A(LHF)+1NA+1A(RHF) | AM275-1 | 1 | 2026-05-28 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 11 | 5540 | SO-2605-105-01 | Houzs Century | 5540-1A(LHF)+1A(RHF) | BO315-31 | 1 | 2026-06-01 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-186-01 | Houzs Century | 1013-(SS) | PC151-03 | 1 | 2026-05-26 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-141-01 | Carress | 1013-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-166-01 | The Conts | 1013-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-166-02 | The Conts | 1013-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-188-01 | Houzs Century | 1013-(SS) | PC151-13 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-213-01 | Houzs Century | 1013-(K) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 12 | 1013 | SO-2605-227-01 | Houzs Century | 1013-(K) | PC151-03 | 1 | 2026-06-02 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 13 | 5531 | SO-2605-072-01 | Carress | 5531-L(LHF)+2A(RHF) | KN390-14 | 1 | 2026-05-25 | 2026-05-24 | PENDING
0) OVERDUE / this week — cut first | 13 | 5531 | SO-2604-327-01 | Carress | 5531-L(LHF)+2A(RHF) | NINJA 08 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 13 | 5531 | SO-2605-067-01 | Carress | 5531-L(LHF)+2A(RHF) | KN390-2 | 1 | 2026-06-01 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 13 | 5531 | SO-2605-079-01 | Carress | 5531-2A(LHF)+L(RHF) | M2402-13 | 1 | 2026-06-01 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 14 | 5536 | SO-2605-220-01 | Houzs Century | 5536-2S | BO315-23 | 1 | 2026-05-27 | 2026-05-26 | PENDING
0) OVERDUE / this week — cut first | 15 | 1005 | SO-2605-124-01 | Houzs Century | 1005-(Q) | PC151-02 | 1 | 2026-05-29 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 15 | 1005 | SO-2605-131-07 | Houzs Century | 1005-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 15 | 1005 | SO-2605-157-01 | Houzs Century | 1005-(Q) | PC151-04 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 15 | 1005 | SO-2605-234-02 | Houzs Century | 1005-(Q) | PC151-01 | 1 | 2026-06-02 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 16 | 5535 | SO-2605-104-01 | Houzs Century | 5535-1A(LHF)+1NA+L(RHF) | BO315-1 | 1 | 2026-05-28 | 2026-05-27 | PENDING
0) OVERDUE / this week — cut first | 16 | 5535 | SO-2605-222-01 | Houzs Century | 5535-2A(LHF)+L(RHF) | CH141-14 | 1 | 2026-05-30 | 2026-05-29 | PENDING
0) OVERDUE / this week — cut first | 17 | 1003(A) | SO-2605-187-01 | Houzs Century | 1003(A)-(Q) | PC151-14 | 1 | 2026-05-30 | 2026-05-28 | PENDING
0) OVERDUE / this week — cut first | 17 | 1003(A) | SO-2605-131-08 | Houzs Century | 1003(A)-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 17 | 1003(A) | SO-2605-212-01 | Houzs Century | 1003(A)-(K) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 18 | 2006(A) | SO-2605-102-01 | Houzs Century | 2006(A)-(K) | PC151-17 | 1 | 2026-05-30 | 2026-05-28 | PENDING
0) OVERDUE / this week — cut first | 19 | 1041 | SO-2605-131-11 | Houzs Century | 1041-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 20 | 2003 | SO-2605-131-06 | Houzs Century | 2003-(K) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 21 | 2009(A) | SO-2605-131-10 | Houzs Century | 2009(A)-(K) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 22 | 2038(A) | SO-2605-204-02 | Houzs Century | 2038(A)-(Q) | PC151-10 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 22 | 2038(A) | SO-2605-204-03 | Houzs Century | 2038(A)-(SS) | PC151-11 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 23 | 2038(A)(HF)(W) | SO-2605-251-01 | Houzs Century | 2038(A)(HF)(W)-(Q) | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 23 | 2038(A)(HF)(W) | SO-2605-233-01 | Houzs Century | 2038(A)(HF)(W)-(K) | PC151-12 | 1 | 2026-06-02 | 2026-05-31 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2604-307-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-173-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-174-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-175-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-176-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-177-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-178-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-179-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-180-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
0) OVERDUE / this week — cut first | 24 | 6112 | SO-2605-181-01 | The Conts | 6112-2S | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-154-01 | Houzs Century | 1007-(Q) | PC151-02 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-195-01 | Carress | 1007-(Q) | PC151-17 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-207-01 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-248-01 | Houzs Century | 1007-(K) | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-249-01 | Houzs Century | 1007-(Q) | PC151-17 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-185-01 | Houzs Century | 1007-(S) | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-185-03 | Houzs Century | 1007-(Q) | PC151-08 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-185-04 | Houzs Century | 1007-(Q) | PC151-09 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-192-04 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-255-01 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-256-01 | Houzs Century | 1007-(K) | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-257-01 | Houzs Century | 1007-(Q) | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-257-02 | Houzs Century | 1007-(Q) | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-215-02 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 25 | 1007 | SO-2605-203-01 | Houzs Century | 1007-(K) | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-153-02 | Houzs Century | 1013-(Q) | PC151-03 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-193-01 | Carress | 1013-(Q) | PC151-03 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-214-01 | Houzs Century | 1013-(Q) | KS-14 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-096-01 | Houzs Century | 1013-(SK) | PC151-10 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-096-02 | Houzs Century | 1013-(Q) | PC151-10 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-096-03 | Houzs Century | 1013-(Q) | PC151-10 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-254-01 | Houzs Century | 1013-(Q) | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-254-02 | Houzs Century | 1013-(S) | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-278-01 | Houzs Century | 1013-(Q) | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-185-02 | Houzs Century | 1013-(Q) | PC151-14 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-262-01 | Houzs Century | 1013-(Q) | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-262-02 | Houzs Century | 1013-(SS) | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-215-03 | Houzs Century | 1013-(S) | PC151-09 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-215-04 | Houzs Century | 1013-(S) | PC151-08 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-070-01 | Carress | 1013-(K) | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-070-02 | Carress | 1013-(SS) | PC151-18 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-264-01 | Houzs Century | 1013-(Q) | PC151-04 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-276-01 | Houzs Century | 1013-(K) | PC151-12 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-277-01 | Houzs Century | 1013-(SS) | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-285-01 | Houzs Century | 1013-(SS) | PC151-09 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 26 | 1013 | SO-2605-285-02 | Houzs Century | 1013-(SS) | PC151-11 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-099-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-099-02 | Houzs Century | 2008(A)-(Q) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-209-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-209-02 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-192-01 | Houzs Century | 2008(A)-(K) | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-192-02 | Houzs Century | 2008(A)-(K) | PC151-12 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-192-03 | Houzs Century | 2008(A)-(K) | PC151-10 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-238-01 | Houzs Century | 2008(A)-(K) | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-238-02 | Houzs Century | 2008(A)-(K) | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-238-03 | Houzs Century | 2008(A)-(K) | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-263-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-215-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-258-01 | Houzs Century | 2008(A)-(K) | PC151-04 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 27 | 2008(A) | SO-2605-295-01 | Houzs Century | 2008(A)-(K) | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 28 | 2009(A) | SO-2605-247-01 | Houzs Century | 2009(A)-(K) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 28 | 2009(A) | SO-2605-239-01 | Carress | 2009(A)-(Q) | PC151-01 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 28 | 2009(A) | SO-2605-241-01 | Houzs Century | 2009(A)-(K) | PC151-06 | 1 | 2026-06-09 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 28 | 2009(A) | SO-2605-241-02 | Houzs Century | 2009(A)-(Q) | PC151-15 | 1 | 2026-06-09 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 29 | 2038(A) | SO-2605-153-01 | Houzs Century | 2038(A)-(K) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 29 | 2038(A) | SO-2605-209-03 | Houzs Century | 2038(A)-(Q) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 29 | 2038(A) | SO-2605-209-04 | Houzs Century | 2038(A)-(Q) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 29 | 2038(A) | SO-2605-279-01 | Houzs Century | 2038(A)-(Q) | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 29 | 2038(A) | SO-2605-140-01 | Houzs Century | 2038(A)-(Q) | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 29 | 2038(A) | SO-2605-298-01 | Houzs Century | 2038(A)-(Q) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 30 | 5530 | SO-2605-051-01 | Houzs Century | 5530-1A(LHF)+1NA+1A(RHF) | CH141-11 | 1 | 2026-06-02 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 30 | 5530 | SO-2604-293-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | CH141-12 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 30 | 5530 | SO-2605-080-01 | Houzs Century | 5530-1A(LHF)+2NA+L(RHF)+STOOL | BO315-25 | 1 | 2026-06-03 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 30 | 5530 | SO-2605-130-01 | Houzs Century | 5530-1A(LHF)+1NA+1A(RHF) | BO315-1 | 1 | 2026-06-08 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 30 | 5530 | SO-2605-240-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | BO315-22 | 1 | 2026-06-08 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 31 | 5540 | SO-2605-077-01 | Houzs Century | 5540-1A(LHF)+1NA+CSL+L(RHF) | FABRIC HR805-10 | 1 | 2026-06-02 | 2026-06-01 | PENDING
1) 01 Jun – 07 Jun | 32 | 2006(A) | SO-2605-132-01 | Houzs Century | 2006(A)-(K) | PC151-01 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 32 | 2006(A) | SO-2605-210-01 | Houzs Century | 2006(A)-(K) | PC151-14 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 32 | 2006(A) | SO-2605-286-01 | Houzs Century | 2006(A)-(K) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 33 | 5531 | SO-2605-194-01 | Carress | 5531-L(LHF)+2A(RHF) | GARFIELD - 3 TUNDORA | 1 | 2026-06-03 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 33 | 5531 | SO-2605-197-01 | Carress | 5531-1A(LHF)+2A(RHF) | M2402-4 | 1 | 2026-06-03 | 2026-06-02 | PENDING
1) 01 Jun – 07 Jun | 33 | 5531 | SO-2605-071-01 | Carress | 5531-2A(LHF)+L(RHF) | NINJA 02 | 1 | 2026-06-08 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 33 | 5531 | SO-2605-183-01 | Carress | 5531-1A(LHF)+2A(RHF) | M2402-18 | 1 | 2026-06-08 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 33 | 5531 | SO-2605-196-01 | Carress | 5531-L(LHF)+2A(RHF) | KN390-2 | 1 | 2026-06-08 | 2026-06-07 | PENDING
1) 01 Jun – 07 Jun | 34 | DIVAN | SO-2605-283-01 | Houzs Century | DIVAN-(SS) | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1) 01 Jun – 07 Jun | 34 | DIVAN | SO-2605-296-01 | Houzs Century | DIVAN-(Q) | PC151-03 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 34 | DIVAN | SO-2605-296-02 | Houzs Century | DIVAN-(Q) | PC151-03 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 34 | DIVAN | SO-2605-296-03 | Houzs Century | DIVAN-(S) | PC151-03 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 34 | DIVAN | SO-2605-300-01 | Houzs Century | DIVAN-(K) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 35 | 1030 | SO-2605-299-01 | Houzs Century | 1030-(Q) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 35 | 1030 | SO-2605-299-02 | Houzs Century | 1030-(Q) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 35 | 1030 | SO-2605-299-03 | Houzs Century | 1030-(Q) | PC151-18 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 35 | 1030 | SO-2605-300-02 | Houzs Century | 1030-(Q) | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1) 01 Jun – 07 Jun | 36 | 1003(A) | SO-2605-226-01 | Houzs Century | 1003(A)-(Q) | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 36 | 1003(A) | SO-2605-226-02 | Houzs Century | 1003(A)-(Q) | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 36 | 1003(A) | SO-2605-291-01 | Houzs Century | 1003(A)-(K) | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 37 | 1005 | SO-2605-291-02 | Houzs Century | 1005-(Q) | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 38 | 2041(A) | SO-2605-280-01 | Houzs Century | 2041(A)-(Q) | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1) 01 Jun – 07 Jun | 38 | 2041(A) | SO-2605-280-02 | Houzs Century | 2041(A)-(Q) | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
2) 08 Jun – 14 Jun | 39 | 1003(A) | SO-2605-123-01 | Houzs Century | 1003(A)-(SK) | PC151-02 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-259-02 | Carress | 1007-(Q) | PC151-14 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-297-02 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-243-02 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-243-03 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-243-04 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-246-01 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-275-01 | Houzs Century | 1007-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-275-02 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-282-02 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-292-02 | Houzs Century | 1007-(SS) | PC151-03 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 40 | 1007 | SO-2605-292-03 | Houzs Century | 1007-(SS) | PC151-03 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-229-02 | Houzs Century | 1013-(K) | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-244-01 | Houzs Century | 1013-(Q) | PC151-02 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-245-01 | Houzs Century | 1013-(S) | PC151-02 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-269-01 | The Conts | 1013-(Q) | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-269-02 | The Conts | 1013-(Q) | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-111-01 | Carress | 1013-(Q) | PC151-17 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-111-02 | Carress | 1013-(K) | PC151-17 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-261-01 | Houzs Century | 1013-(Q) | PC151-01 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-261-02 | Houzs Century | 1013-(Q) | PC151-15 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-216-01 | Carress | 1013-(K) | PC151-14 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-216-02 | Carress | 1013-(Q) | PC151-06 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-216-03 | Carress | 1013-(Q) | PC151-15 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-216-04 | Carress | 1013-(K) | PC151-13 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-271-01 | Carress | 1013-(Q) | PC151-17 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-271-02 | Carress | 1013-(K) | PC151-17 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-293-01 | Houzs Century | 1013-(Q) | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 41 | 1013 | SO-2605-293-02 | Houzs Century | 1013-(K) | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 42 | 1052 | SO-2605-288-02 | Houzs Century | 1052-(Q) | PC151-17 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-229-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2604-281-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-200-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-282-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-242-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-242-02 | Houzs Century | 2008(A)-(K) | PC151-12 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-252-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 43 | 2008(A) | SO-2605-292-01 | Houzs Century | 2008(A)-(K) | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 44 | 2038(A) | SO-2605-123-02 | Houzs Century | 2038(A)-(SS) | PC151-03 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 44 | 2038(A) | SO-2605-288-01 | Houzs Century | 2038(A)-(Q) | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 44 | 2038(A) | SO-2605-235-01 | Houzs Century | 2038(A)-(Q) | PC151-02 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 45 | 5530 | SV-2605-003-01 | Houzs Century | 5530-L(RHF) | BO315-2 | 1 | 2026-06-09 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 46 | DIVAN | SO-2605-259-01 | Carress | DIVAN-(K) | PC151-13 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2) 08 Jun – 14 Jun | 46 | DIVAN | SO-2605-200-02 | Houzs Century | DIVAN-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 46 | DIVAN | SO-2605-200-03 | Houzs Century | DIVAN-(Q) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 46 | DIVAN | SO-2605-206-01 | Houzs Century | DIVAN-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 46 | DIVAN | SO-2605-265-01 | Houzs Century | DIVAN-(Q) | PC151-14 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 46 | DIVAN | SO-2605-265-02 | Houzs Century | DIVAN-(S) | PC151-14 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 47 | 2006(A) | SO-2605-261-03 | Houzs Century | 2006(A)-(K) | PC151-02 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 47 | 2006(A) | SO-2605-297-01 | Houzs Century | 2006(A)-(K) | PC151-01 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 47 | 2006(A) | SO-2605-294-01 | Houzs Century | 2006(A)-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 48 | 5535 | SO-2605-270-01 | The Conts | 5535-2A(LHF)+L(RHF) | PC151-01 | 1 | 2026-06-10 | 2026-06-09 | PENDING
2) 08 Jun – 14 Jun | 49 | 2009(A) | SO-2605-243-01 | Houzs Century | 2009(A)-(K) | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2) 08 Jun – 14 Jun | 49 | 2009(A) | SO-2605-211-01 | Houzs Century | 2009(A)-(SK) | PC151-01 | 1 | 2026-06-16 | 2026-06-14 | PENDING
2) 08 Jun – 14 Jun | 50 | 2033(HF)(W) | SO-2605-202-01 | Houzs Century | 2033(HF)(W)-(K) | PC151-02 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2) 08 Jun – 14 Jun | 50 | 2033(HF)(W) | SO-2605-202-02 | Houzs Century | 2033(HF)(W)-(SS) | PC151-02 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2) 08 Jun – 14 Jun | 51 | 5531 | SO-2605-076-01 | Carress | 5531-L(LHF)+2A(RHF) | GARFIELD-2 CHERVRON | 1 | 2026-06-12 | 2026-06-11 | PENDING
2) 08 Jun – 14 Jun | 51 | 5531 | SO-2605-237-01 | Carress | 5531-L(LHF)+2A(RHF) | KN390-1 | 1 | 2026-06-13 | 2026-06-12 | PENDING
2) 08 Jun – 14 Jun | 52 | 1005 | SO-2605-281-01 | Houzs Century | 1005-(Q) | PC151-03 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2) 08 Jun – 14 Jun | 53 | 1023 | SO-2605-274-01 | Houzs Century | 1023-(K) | PC151-01 | 1 | 2026-06-16 | 2026-06-14 | PENDING
2) 08 Jun – 14 Jun | 54 | 5536 | SO-2605-223-01 | Houzs Century | 5536-1A(LHF)+CNR+2A(RHF)+2S | FABRIC HR805-90 | 1 | 2026-06-15 | 2026-06-14 | PENDING
3) 15 Jun – 21 Jun | 55 | 1030 | SO-2605-228-01 | Houzs Century | 1030-(K) | PC151-01 | 1 | 2026-06-17 | 2026-06-15 | PENDING
3) 15 Jun – 21 Jun | 56 | 2038(A) | SO-2605-260-01 | Houzs Century | 2038(A)-(Q) | PC151-10 | 1 | 2026-06-17 | 2026-06-15 | PENDING
3) 15 Jun – 21 Jun | 57 | 5535 | SO-2605-273-01 | Houzs Century | 5535-L(LHF)+2A(RHF) | BO315-24 | 1 | 2026-06-16 | 2026-06-15 | PENDING
3) 15 Jun – 21 Jun | 57 | 5535 | SO-2605-106-01 | Houzs Century | 5535-1A(LHF)+1NA+1A(RHF)+1A(LHF)+1A(RHF)+1S | M2402-4 | 1 | 2026-06-22 | 2026-06-21 | PENDING
3) 15 Jun – 21 Jun | 57 | 5535 | SO-2605-303-01 | Carress | 5535-2A(LHF)+1A(RHF) | KN390-3 | 1 | 2026-06-22 | 2026-06-21 | PENDING
3) 15 Jun – 21 Jun | 58 | 5536 | SO-2605-225-01 | Houzs Century | 5536-1A(LHF)+1A(RHF) | NINJA 02 | 1 | 2026-06-16 | 2026-06-15 | PENDING
3) 15 Jun – 21 Jun | 59 | 1013 | SO-2605-069-01 | Carress | 1013-(Q) | PC151-13 | 1 | 2026-06-18 | 2026-06-16 | PENDING
3) 15 Jun – 21 Jun | 59 | 1013 | SO-2605-289-01 | Carress | 1013-(Q) | PC151-01 | 1 | 2026-06-22 | 2026-06-20 | PENDING
3) 15 Jun – 21 Jun | 60 | 5531 | SO-2605-236-01 | Carress | 5531-2A(LHF)+L(RHF) | M2402-1 | 1 | 2026-06-17 | 2026-06-16 | PENDING
3) 15 Jun – 21 Jun | 61 | 1007 | SO-2605-284-01 | Houzs Century | 1007-(Q) | PC151-01 | 1 | 2026-06-19 | 2026-06-17 | PENDING
3) 15 Jun – 21 Jun | 62 | 2006(A) | SO-2605-190-01 | Houzs Century | 2006(A)-(K) | PC151-01 | 1 | 2026-06-19 | 2026-06-17 | PENDING
3) 15 Jun – 21 Jun | 62 | 2006(A) | SO-2605-191-01 | Houzs Century | 2006(A)-(Q) | PC151-02 | 1 | 2026-06-19 | 2026-06-17 | PENDING
3) 15 Jun – 21 Jun | 63 | 5530 | SO-2605-290-01 | Houzs Century | 5530-1A(LHF)+2A(RHF)+STOOL | BO315-21 | 1 | 2026-06-19 | 2026-06-18 | PENDING
4) 22 Jun – 28 Jun | 64 | 1003(A) | SO-2605-189-01 | Houzs Century | 1003(A)-(K) | PC151-01 | 1 | 2026-06-24 | 2026-06-22 | PENDING
4) 22 Jun – 28 Jun | 64 | 1003(A) | SO-2605-231-01 | Houzs Century | 1003(A)-(Q) | PC151-02 | 1 | 2026-06-25 | 2026-06-23 | PENDING
4) 22 Jun – 28 Jun | 65 | 2041(A) | SO-2605-231-02 | Houzs Century | 2041(A)-(Q) | PC151-02 | 1 | 2026-06-25 | 2026-06-23 | PENDING
4) 22 Jun – 28 Jun | 66 | 5530 | SO-2605-198-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | BO315-3 | 1 | 2026-06-24 | 2026-06-23 | PENDING
4) 22 Jun – 28 Jun | 66 | 5530 | SO-2605-199-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | BO315-3 | 1 | 2026-06-24 | 2026-06-23 | PENDING
4) 22 Jun – 28 Jun | 66 | 5530 | SO-2605-224-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | M2402-4 | 1 | 2026-06-26 | 2026-06-25 | PENDING
4) 22 Jun – 28 Jun | 67 | 5536 | SO-2605-184-01 | Houzs Century | 5536-2A(LHF)+CNR+1A(RHF) | BO315-5 | 1 | 2026-06-24 | 2026-06-23 | PENDING
4) 22 Jun – 28 Jun | 68 | 5531 | SO-2605-182-01 | Carress | 5531-L(LHF)+2A(RHF) | NINJA 02 | 1 | 2026-06-25 | 2026-06-24 | PENDING
4) 22 Jun – 28 Jun | 68 | 5531 | SO-2605-301-01 | Carress | 5531-2S | M2402-13 | 1 | 2026-06-29 | 2026-06-28 | PENDING
4) 22 Jun – 28 Jun | 69 | 1007 | SO-2605-302-01 | Carress | 1007-(K) | PC151-15 | 1 | 2026-06-29 | 2026-06-27 | PENDING
6) 06 Jul – 12 Jul | 70 | 2006(A) | SV-2605-002-01 | Houzs Century | 2006(A)-(K) | PC151-14 | 1 | 2026-07-08 | 2026-07-06 | PENDING

## Batch Summary
Cut # | Window (deadline) | Model | Category | # Orders | Earliest Customer DD | Earliest Our Expected DD | Latest Our Expected DD
1 | 0) OVERDUE / this week — cut first | LONG PILLOW | Accessory | 4 | 2026-04-15 | 2026-04-14 | 2026-05-24
2 | 0) OVERDUE / this week — cut first | SQUARE PILLOW | Accessory | 10 | 2026-04-29 | 2026-04-28 | 2026-05-29
3 | 0) OVERDUE / this week — cut first | 5530 | Sofa | 7 | 2026-05-04 | 2026-05-03 | 2026-05-31
4 | 0) OVERDUE / this week — cut first | 5537 | Sofa | 1 | 2026-05-04 | 2026-05-03 | 2026-05-03
5 | 0) OVERDUE / this week — cut first | 2041(A) | Bedframe | 3 | 2026-05-13 | 2026-05-11 | 2026-05-30
6 | 0) OVERDUE / this week — cut first | 1007 | Bedframe | 8 | 2026-05-18 | 2026-05-16 | 2026-05-31
7 | 0) OVERDUE / this week — cut first | DIVAN | Bedframe | 3 | 2026-05-18 | 2026-05-16 | 2026-05-30
8 | 0) OVERDUE / this week — cut first | 1023(HF)(W) | Bedframe | 1 | 2026-05-21 | 2026-05-19 | 2026-05-19
9 | 0) OVERDUE / this week — cut first | 2008(A) | Bedframe | 5 | 2026-05-25 | 2026-05-23 | 2026-05-31
10 | 0) OVERDUE / this week — cut first | 2011(A) | Bedframe | 1 | 2026-05-25 | 2026-05-23 | 2026-05-23
11 | 0) OVERDUE / this week — cut first | 5540 | Sofa | 6 | 2026-05-25 | 2026-05-23 | 2026-05-31
12 | 0) OVERDUE / this week — cut first | 1013 | Bedframe | 7 | 2026-05-26 | 2026-05-24 | 2026-05-31
13 | 0) OVERDUE / this week — cut first | 5531 | Sofa | 4 | 2026-05-25 | 2026-05-24 | 2026-05-31
14 | 0) OVERDUE / this week — cut first | 5536 | Sofa | 1 | 2026-05-27 | 2026-05-26 | 2026-05-26
15 | 0) OVERDUE / this week — cut first | 1005 | Bedframe | 4 | 2026-05-29 | 2026-05-27 | 2026-05-31
16 | 0) OVERDUE / this week — cut first | 5535 | Sofa | 2 | 2026-05-28 | 2026-05-27 | 2026-05-29
17 | 0) OVERDUE / this week — cut first | 1003(A) | Bedframe | 3 | 2026-05-30 | 2026-05-28 | 2026-05-30
18 | 0) OVERDUE / this week — cut first | 2006(A) | Bedframe | 1 | 2026-05-30 | 2026-05-28 | 2026-05-28
19 | 0) OVERDUE / this week — cut first | 1041 | Bedframe | 1 | 2026-06-01 | 2026-05-30 | 2026-05-30
20 | 0) OVERDUE / this week — cut first | 2003 | Bedframe | 1 | 2026-06-01 | 2026-05-30 | 2026-05-30
21 | 0) OVERDUE / this week — cut first | 2009(A) | Bedframe | 1 | 2026-06-01 | 2026-05-30 | 2026-05-30
22 | 0) OVERDUE / this week — cut first | 2038(A) | Bedframe | 2 | 2026-06-01 | 2026-05-30 | 2026-05-30
23 | 0) OVERDUE / this week — cut first | 2038(A)(HF)(W) | Bedframe | 2 | 2026-06-01 | 2026-05-30 | 2026-05-31
24 | 0) OVERDUE / this week — cut first | 6112 | Sofa | 10 | 2026-06-01 | 2026-05-30 | 2026-05-30
25 | 1) 01 Jun – 07 Jun | 1007 | Bedframe | 15 | 2026-06-03 | 2026-06-01 | 2026-06-06
26 | 1) 01 Jun – 07 Jun | 1013 | Bedframe | 21 | 2026-06-03 | 2026-06-01 | 2026-06-06
27 | 1) 01 Jun – 07 Jun | 2008(A) | Bedframe | 14 | 2026-06-03 | 2026-06-01 | 2026-06-06
28 | 1) 01 Jun – 07 Jun | 2009(A) | Bedframe | 4 | 2026-06-03 | 2026-06-01 | 2026-06-07
29 | 1) 01 Jun – 07 Jun | 2038(A) | Bedframe | 6 | 2026-06-03 | 2026-06-01 | 2026-06-04
30 | 1) 01 Jun – 07 Jun | 5530 | Sofa | 5 | 2026-06-02 | 2026-06-01 | 2026-06-07
31 | 1) 01 Jun – 07 Jun | 5540 | Sofa | 1 | 2026-06-02 | 2026-06-01 | 2026-06-01
32 | 1) 01 Jun – 07 Jun | 2006(A) | Bedframe | 3 | 2026-06-04 | 2026-06-02 | 2026-06-04
33 | 1) 01 Jun – 07 Jun | 5531 | Sofa | 5 | 2026-06-03 | 2026-06-02 | 2026-06-07
34 | 1) 01 Jun – 07 Jun | DIVAN | Bedframe | 5 | 2026-06-05 | 2026-06-03 | 2026-06-04
35 | 1) 01 Jun – 07 Jun | 1030 | Bedframe | 4 | 2026-06-06 | 2026-06-04 | 2026-06-04
36 | 1) 01 Jun – 07 Jun | 1003(A) | Bedframe | 3 | 2026-06-08 | 2026-06-06 | 2026-06-06
37 | 1) 01 Jun – 07 Jun | 1005 | Bedframe | 1 | 2026-06-08 | 2026-06-06 | 2026-06-06
38 | 1) 01 Jun – 07 Jun | 2041(A) | Bedframe | 2 | 2026-06-08 | 2026-06-06 | 2026-06-06
39 | 2) 08 Jun – 14 Jun | 1003(A) | Bedframe | 1 | 2026-06-10 | 2026-06-08 | 2026-06-08
40 | 2) 08 Jun – 14 Jun | 1007 | Bedframe | 11 | 2026-06-10 | 2026-06-08 | 2026-06-13
41 | 2) 08 Jun – 14 Jun | 1013 | Bedframe | 17 | 2026-06-10 | 2026-06-08 | 2026-06-13
42 | 2) 08 Jun – 14 Jun | 1052 | Bedframe | 1 | 2026-06-10 | 2026-06-08 | 2026-06-08
43 | 2) 08 Jun – 14 Jun | 2008(A) | Bedframe | 8 | 2026-06-10 | 2026-06-08 | 2026-06-13
44 | 2) 08 Jun – 14 Jun | 2038(A) | Bedframe | 3 | 2026-06-10 | 2026-06-08 | 2026-06-10
45 | 2) 08 Jun – 14 Jun | 5530 | Sofa | 1 | 2026-06-09 | 2026-06-08 | 2026-06-08
46 | 2) 08 Jun – 14 Jun | DIVAN | Bedframe | 6 | 2026-06-10 | 2026-06-08 | 2026-06-10
47 | 2) 08 Jun – 14 Jun | 2006(A) | Bedframe | 3 | 2026-06-11 | 2026-06-09 | 2026-06-10
48 | 2) 08 Jun – 14 Jun | 5535 | Sofa | 1 | 2026-06-10 | 2026-06-09 | 2026-06-09
49 | 2) 08 Jun – 14 Jun | 2009(A) | Bedframe | 2 | 2026-06-12 | 2026-06-10 | 2026-06-14
50 | 2) 08 Jun – 14 Jun | 2033(HF)(W) | Bedframe | 2 | 2026-06-13 | 2026-06-11 | 2026-06-11
51 | 2) 08 Jun – 14 Jun | 5531 | Sofa | 2 | 2026-06-12 | 2026-06-11 | 2026-06-12
52 | 2) 08 Jun – 14 Jun | 1005 | Bedframe | 1 | 2026-06-15 | 2026-06-13 | 2026-06-13
53 | 2) 08 Jun – 14 Jun | 1023 | Bedframe | 1 | 2026-06-16 | 2026-06-14 | 2026-06-14
54 | 2) 08 Jun – 14 Jun | 5536 | Sofa | 1 | 2026-06-15 | 2026-06-14 | 2026-06-14
55 | 3) 15 Jun – 21 Jun | 1030 | Bedframe | 1 | 2026-06-17 | 2026-06-15 | 2026-06-15
56 | 3) 15 Jun – 21 Jun | 2038(A) | Bedframe | 1 | 2026-06-17 | 2026-06-15 | 2026-06-15
57 | 3) 15 Jun – 21 Jun | 5535 | Sofa | 3 | 2026-06-16 | 2026-06-15 | 2026-06-21
58 | 3) 15 Jun – 21 Jun | 5536 | Sofa | 1 | 2026-06-16 | 2026-06-15 | 2026-06-15
59 | 3) 15 Jun – 21 Jun | 1013 | Bedframe | 2 | 2026-06-18 | 2026-06-16 | 2026-06-20
60 | 3) 15 Jun – 21 Jun | 5531 | Sofa | 1 | 2026-06-17 | 2026-06-16 | 2026-06-16
61 | 3) 15 Jun – 21 Jun | 1007 | Bedframe | 1 | 2026-06-19 | 2026-06-17 | 2026-06-17
62 | 3) 15 Jun – 21 Jun | 2006(A) | Bedframe | 2 | 2026-06-19 | 2026-06-17 | 2026-06-17
63 | 3) 15 Jun – 21 Jun | 5530 | Sofa | 1 | 2026-06-19 | 2026-06-18 | 2026-06-18
64 | 4) 22 Jun – 28 Jun | 1003(A) | Bedframe | 2 | 2026-06-24 | 2026-06-22 | 2026-06-23
65 | 4) 22 Jun – 28 Jun | 2041(A) | Bedframe | 1 | 2026-06-25 | 2026-06-23 | 2026-06-23
66 | 4) 22 Jun – 28 Jun | 5530 | Sofa | 3 | 2026-06-24 | 2026-06-23 | 2026-06-25
67 | 4) 22 Jun – 28 Jun | 5536 | Sofa | 1 | 2026-06-24 | 2026-06-23 | 2026-06-23
68 | 4) 22 Jun – 28 Jun | 5531 | Sofa | 2 | 2026-06-25 | 2026-06-24 | 2026-06-28
69 | 4) 22 Jun – 28 Jun | 1007 | Bedframe | 1 | 2026-06-29 | 2026-06-27 | 2026-06-27
70 | 6) 06 Jul – 12 Jul | 2006(A) | Bedframe | 1 | 2026-07-08 | 2026-07-06 | 2026-07-06