## Summary & Notes
各部门工序 Plan Due 排程 (Process Plan-Due, 栏位 = ERP 原样)
生成 2026-06-01 6/1 放假不排工,计划从 6/2 开始。只读,没有改动系统任何东西。
【这本表怎么看】
· Process Due Dates:一张单一行,横看 8 个部门各自要哪天做好(done=已做完,-=不需要)。
· 后面 8 页 = 8 个部门各一页(1-Cut … 8-Pack)。每页的栏位跟你 ERP 的部门生产页一模一样,
只在最左边多加一栏『Plan Due 计划到期』= 我们排出来这件活该哪天做好。
· 每页只列该部门『还没做完(WAITING)』的活,按 Plan Due 先后排,最上面的先做。
同一个计划到期日的用底色分组。最左 Plan Due 那格的颜色 = 整张单的状态(见下)。
【Plan Due 怎么算出来的】
按近 30 天每天真实做得出来的量,一个部门接一个部门算:上一道工序哪天做完,下一道
才那天开工;每天只能做到产能上限;周日 + 6/1 放假不排。算出来那天 = 该工序最迟做好日。
【状态 Status(最左 Plan Due 格的底色)】
OVERDUE 已逾期 / LATE 赶不上 Customer DD / AT-RISK 破内部缓冲 Hookka DD / ON-TIME 准时 / ON-HOLD 暂停。
【结果一览】
共 327 张活跃单。 OVERDUE=61 LATE=202 AT-RISK=24 ON-TIME=37 ON-HOLD=3
【各部门:还要做的活 / 产能(近30天实际平均)】
裁布 Fabric Cut 待做 114 件 (WAITING) 产能 2321 分钟/天 ≈ 23.5 件/天
车缝 Fabric Sew 待做 421 件 (WAITING) 产能 3114 分钟/天 ≈ 63.0 件/天
锯木 Wood Cut 待做 483 件 (WAITING) 产能 1226 分钟/天 ≈ 61.2 件/天
粘棉 Foam 待做 470 件 (WAITING) 产能 818 分钟/天 ≈ 32.8 件/天
组框 Framing 待做 580 件 (WAITING) 产能 1706 分钟/天 ≈ 60.8 件/天
打底 Webbing 待做 630 件 (WAITING) 产能 960 分钟/天 ≈ 57.5 件/天
包面 Upholstery 待做 703 件 (WAITING) 产能 1622 分钟/天 ≈ 58.3 件/天
包装 Packing 待做 475 件 (WAITING) 产能 1893 分钟/天 ≈ 79.5 件/天
瓶颈:FOAM 粘棉 818 分钟/天最低,整条线卡在这里。要把 Plan Due 提前,先在这里加人。
注:这只是 planning 表,还没写进 ERP。你看过、确认排法 OK,我再帮你把 due date 写进系统。

## Process Due Dates
SO / PO | Customer | Model | Type | Cut | Sew | Wood | Foam | Frame | Web | Uphol | Pack | Ready | Customer DD | Hookka DD | Status
SO-2605-186-01 | Houzs Century | 1013-(SS) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-26 | 2026-05-24 | OVERDUE
SO-2605-187-01 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2605-162-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-02 | done | done | 06-02 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-161-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-160-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-124-01 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-05-29 | 2026-05-27 | OVERDUE
SO-2605-098-04 | Houzs Century | 2008(A)-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-29 | 2026-05-27 | OVERDUE
SO-2605-098-03 | Houzs Century | 2008(A)-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-29 | 2026-05-27 | OVERDUE
SO-2605-102-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2605-023-01 | Houzs Century | 1007-(K) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-18 | 2026-05-16 | OVERDUE
SO-2605-009-01 | Houzs Century | 1007-(K) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-22 | 2026-05-20 | OVERDUE
SO-2604-321-03 | Houzs Century | 1023(HF)(W)-(SS) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-21 | 2026-05-19 | OVERDUE
SO-2604-210-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | done | done | - | - | - | - | - | 06-02 | 06-02 | 2026-05-04 | 2026-05-02 | OVERDUE
SO-2604-092-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | done | done | - | - | - | - | - | 06-02 | 06-02 | 2026-04-29 | 2026-04-28 | OVERDUE
SO-2605-171-01 | Houzs Century | 2011(A)-(K) | BEDFRAME | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-010-02 | Houzs Century | 2041(A)-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2604-265-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | done | done | 06-02 | done | done | 06-03 | 06-03 | 06-03 | 2026-05-16 | 2026-05-14 | OVERDUE
SO-2604-086-02 | Houzs Century | 5530-L(LHF) | SOFA | - | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-11 | 2026-05-10 | OVERDUE
SO-2604-086-01 | Houzs Century | 5530-2A(RHF) | SOFA | done | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-11 | 2026-05-10 | OVERDUE
SO-2604-276-03 | Houzs Century | 2041(A)-(SS) | BEDFRAME | done | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-13 | 2026-05-11 | OVERDUE
SO-2605-104-06 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-072-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-02 | 06-02 | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-072-01 | Carress | 5531-L(LHF) | SOFA | done | 06-02 | 06-02 | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-05 | Houzs Century | 5530-1NA | SOFA | - | done | done | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-04 | Houzs Century | LONG PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | - | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-03 | Houzs Century | LONG PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | done | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | done | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-050-02 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | done | 06-02 | done | done | 06-04 | 06-04 | 06-04 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2605-050-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | done | 06-02 | done | 06-03 | 06-04 | 06-04 | 06-04 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2604-324-04 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | - | 06-04 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2604-324-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2604-345-03 | Carress | 5531-2S | SOFA | - | 06-02 | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-05-27 | 2026-05-25 | OVERDUE
SO-2604-265-01 | Houzs Century | 5530-L(LHF) | SOFA | done | done | done | 06-02 | done | done | 06-04 | 06-04 | 06-04 | 2026-05-16 | 2026-05-14 | OVERDUE
SO-2604-083-05 | Carress | LONG PILLOW | ACCESSORY | done | 06-04 | - | - | - | - | - | - | 06-04 | 2026-04-15 | 2026-04-14 | OVERDUE
SO-2604-083-04 | Carress | LONG PILLOW | ACCESSORY | done | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-04-15 | 2026-04-14 | OVERDUE
SO-2605-222-04 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-222-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-222-02 | Houzs Century | 5535-L(RHF) | SOFA | - | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-222-01 | Houzs Century | 5535-2A(LHF) | SOFA | done | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-221-03 | Houzs Century | 5540-1A(RHF) | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-221-02 | Houzs Century | 5540-1NA | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-05 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-220-01 | Houzs Century | 5536-2S | SOFA | done | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-27 | 2026-05-26 | OVERDUE
SO-2605-104-05 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-04 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-03 | Houzs Century | 5535-L(RHF) | SOFA | - | 06-02 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-02 | Houzs Century | 5535-1NA | SOFA | - | 06-02 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-01 | Houzs Century | 5535-1A(LHF) | SOFA | 06-02 | 06-02 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-108-01 | Houzs Century | 5540-2S | SOFA | done | done | done | 06-05 | done | done | done | done | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-078-03 | Houzs Century | 5540-2A(RHF) | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-078-02 | Houzs Century | 5540-CSL | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-078-01 | Houzs Century | 5540-L(LHF) | SOFA | done | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2604-324-02 | Houzs Century | 5540-1A(RHF) | SOFA | - | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2604-324-01 | Houzs Century | 5540-2A(LHF) | SOFA | 06-02 | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2603-207-02 | Houzs Century | 5537-1A(RHF) | SOFA | - | done | done | done | done | done | 06-05 | 06-05 | 06-05 | 2026-05-04 | 2026-05-03 | OVERDUE
SO-2603-207-01 | Houzs Century | 5537-1A(LHF) | SOFA | done | done | done | done | done | done | 06-05 | 06-05 | 06-05 | 2026-05-04 | 2026-05-03 | OVERDUE
SO-2605-221-01 | Houzs Century | 5540-1A(LHF) | SOFA | 06-02 | 06-03 | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-064-02 | Houzs Century | 5540-2A(RHF) | SOFA | - | done | done | done | done | done | 06-06 | 06-06 | 06-06 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-064-01 | Houzs Century | 5540-1A(LHF) | SOFA | done | done | done | done | done | done | 06-06 | 06-06 | 06-06 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-011-01 | Houzs Century | DIVAN-(K) | BEDFRAME | done | done | done | - | done | done | 06-06 | 06-06 | 06-06 | 2026-05-18 | 2026-05-16 | OVERDUE
SO-2604-300-01 | Houzs Century | DIVAN-(Q) | BEDFRAME | done | done | done | - | done | done | 06-06 | done | 06-06 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-205-02 | Houzs Century | 1007-(S) | BEDFRAME | done | done | done | 06-02 | done | done | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-205-01 | Houzs Century | 1007-(S) | BEDFRAME | done | done | done | 06-02 | done | done | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-208-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-212-01 | Houzs Century | 1003(A)-(K) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-213-01 | Houzs Century | 1013-(K) | BEDFRAME | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-188-01 | Houzs Century | 1013-(SS) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-167-01 | The Conts | 1007-(Q) | BEDFRAME | done | done | done | 06-02 | done | done | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-166-02 | The Conts | 1013-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-166-01 | The Conts | 1013-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-157-01 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-11 | Houzs Century | 1041-(Q) | BEDFRAME | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-08 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-07 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-06 | Houzs Century | 2003-(K) | BEDFRAME | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-141-01 | Carress | 1013-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-251-01 | Houzs Century | 2038(A)(HF)(W)-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-233-01 | Houzs Century | 2038(A)(HF)(W)-(K) | BEDFRAME | done | done | done | 06-02 | done | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-02 | 2026-05-31 | LATE
SO-2605-234-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-02 | 06-03 | 06-03 | 06-03 | 2026-06-02 | 2026-05-31 | LATE
SO-2605-204-03 | Houzs Century | 2038(A)-(SS) | BEDFRAME | done | done | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-204-02 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-10 | Houzs Century | 2009(A)-(K) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-05 | Houzs Century | 2041(A)-(Q) | BEDFRAME | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-109-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | done | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-109-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | done | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-079-02 | Carress | 5531-L(RHF) | SOFA | - | 06-02 | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-079-01 | Carress | 5531-2A(LHF) | SOFA | 06-02 | 06-02 | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2604-327-02 | Carress | 5531-2A(RHF) | SOFA | - | done | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-30 | LATE
SO-2604-327-01 | Carress | 5531-L(LHF) | SOFA | done | done | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-067-02 | Carress | 5531-2A(RHF) | SOFA | - | done | done | 06-03 | done | 06-03 | 06-05 | 06-05 | 06-05 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-067-01 | Carress | 5531-L(LHF) | SOFA | done | done | done | 06-04 | done | 06-03 | 06-05 | 06-05 | 06-05 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-176-01 | The Conts | 6112-2S | SOFA | done | done | 06-03 | 06-06 | 06-04 | 06-06 | 06-06 | 06-06 | 06-06 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-04 | Houzs Century | DIVAN-(K) | BEDFRAME | done | done | done | - | 06-04 | 06-06 | done | done | 06-06 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-132-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | done | done | done | done | done | 06-06 | 06-06 | 06-06 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-105-02 | Houzs Century | 5540-1A(RHF) | SOFA | - | done | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-105-01 | Houzs Century | 5540-1A(LHF) | SOFA | 06-02 | done | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-248-01 | Houzs Century | 1007-(K) | BEDFRAME | done | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-249-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-255-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-256-01 | Houzs Century | 1007-(K) | BEDFRAME | done | done | 06-04 | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-257-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-257-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-207-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | done | done | 06-08 | 06-08 | 06-08 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-195-01 | Carress | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-185-04 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-185-03 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-175-01 | The Conts | 6112-2S | SOFA | done | done | 06-03 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-174-01 | The Conts | 6112-2S | SOFA | done | done | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-173-01 | The Conts | 6112-2S | SOFA | done | done | done | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-154-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | done | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-03 | 2026-06-01 | LATE
SO-2604-307-01 | The Conts | 6112-2S | SOFA | done | done | done | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-299-03 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-02 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-299-02 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-02 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-299-01 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-02 | 06-06 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-276-01 | Houzs Century | 1013-(K) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-277-01 | Houzs Century | 1013-(SS) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-278-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-285-02 | Houzs Century | 1013-(SS) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-285-01 | Houzs Century | 1013-(SS) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-262-02 | Houzs Century | 1013-(SS) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-262-01 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-264-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-254-02 | Houzs Century | 1013-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-254-01 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-203-01 | Houzs Century | 1007-(K) | BEDFRAME | done | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-214-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-215-04 | Houzs Century | 1013-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-215-03 | Houzs Century | 1013-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-215-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-193-01 | Carress | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | done | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-185-02 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-185-01 | Houzs Century | 1007-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-192-04 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-153-02 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | done | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-096-03 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-096-02 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-096-01 | Houzs Century | 1013-(SK) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-070-02 | Carress | 1013-(SS) | BEDFRAME | 06-03 | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-070-01 | Carress | 1013-(K) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-300-02 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-05 | 06-02 | 06-06 | 06-08 | 06-10 | 06-10 | 06-10 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-286-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | 06-05 | 06-05 | 06-02 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-263-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-258-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-238-03 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-238-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-238-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-209-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-209-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-210-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | done | done | 06-02 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-192-03 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-03 | 06-05 | 06-05 | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-192-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-192-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-099-02 | Houzs Century | 2008(A)-(Q) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-099-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | done | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-051-03 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | done | 06-10 | done | 06-10 | done | done | 06-10 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-051-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | done | 06-10 | done | 06-10 | done | done | 06-10 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-295-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-09 | 06-11 | 06-11 | 06-11 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-298-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-279-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-280-02 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-280-01 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-239-01 | Carress | 2009(A)-(Q) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-241-02 | Houzs Century | 2009(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-09 | 2026-06-07 | LATE
SO-2605-241-01 | Houzs Century | 2009(A)-(K) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-09 | 2026-06-07 | LATE
SO-2605-247-01 | Houzs Century | 2009(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-209-04 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | done | done | done | done | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-209-03 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | done | done | 06-10 | done | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-215-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-09 | 06-11 | 06-11 | 06-11 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-153-01 | Houzs Century | 2038(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-140-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | done | done | 06-10 | done | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-05 | 2026-06-03 | LATE
SO-2604-293-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-183-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-183-01 | Carress | 5531-1A(LHF) | SOFA | done | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-197-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-06 | 06-06 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-197-01 | Carress | 5531-1A(LHF) | SOFA | done | 06-08 | 06-06 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-240-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-06 | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-240-01 | Houzs Century | 5530-L(LHF) | SOFA | 06-04 | 06-06 | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-194-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-194-01 | Carress | 5531-L(LHF) | SOFA | 06-04 | 06-08 | 06-06 | 06-12 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-196-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-130-03 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-130-02 | Houzs Century | 5530-1NA | SOFA | - | done | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-130-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-080-04 | Houzs Century | 5530-STOOL | SOFA | - | 06-06 | done | 06-10 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-080-03 | Houzs Century | 5530-L(RHF) | SOFA | - | 06-06 | done | 06-10 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-080-02 | Houzs Century | 5530-2NA | SOFA | - | 06-06 | done | 06-11 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-080-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | 06-06 | done | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2604-293-01 | Houzs Century | 5530-L(LHF) | SOFA | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-296-03 | Houzs Century | DIVAN-(S) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-296-02 | Houzs Century | DIVAN-(Q) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-296-01 | Houzs Century | DIVAN-(Q) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-297-02 | Houzs Century | 1007-(Q) | BEDFRAME | 06-05 | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-300-01 | Houzs Century | DIVAN-(K) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-275-02 | Houzs Century | 1007-(Q) | BEDFRAME | 06-05 | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-275-01 | Houzs Century | 1007-(K) | BEDFRAME | 06-05 | 06-09 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-282-02 | Houzs Century | 1007-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-283-01 | Houzs Century | DIVAN-(SS) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-269-02 | The Conts | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-259-02 | Carress | 1007-(Q) | BEDFRAME | done | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-243-04 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-243-03 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-243-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-246-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-196-01 | Carress | 5531-L(LHF) | SOFA | 06-05 | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-123-01 | Houzs Century | 1003(A)-(SK) | BEDFRAME | done | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-077-04 | Houzs Century | 5540-L(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-077-03 | Houzs Century | 5540-CSL | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-077-02 | Houzs Century | 5540-1NA | SOFA | - | 06-08 | 06-06 | 06-13 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-077-01 | Houzs Century | 5540-1A(LHF) | SOFA | 06-05 | 06-08 | 06-06 | 06-13 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-071-02 | Carress | 5531-L(RHF) | SOFA | - | done | done | 06-12 | 06-09 | 06-12 | 06-13 | done | 06-13 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-071-01 | Carress | 5531-2A(LHF) | SOFA | done | done | done | 06-12 | 06-09 | 06-12 | 06-13 | done | 06-13 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-294-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | 06-05 | 06-09 | 06-09 | 06-02 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-297-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | 06-05 | 06-09 | 06-09 | 06-02 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-288-02 | Houzs Century | 1052-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-15 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-282-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-15 | 06-15 | 06-15 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-269-01 | The Conts | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-261-03 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | 06-09 | 06-09 | 06-02 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-261-02 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-261-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-244-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-245-01 | Houzs Century | 1013-(S) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-229-02 | Houzs Century | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-229-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-111-02 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-111-01 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-292-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-15 | 2026-06-13 | LATE
SO-2605-288-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-10 | 2026-06-08 | LATE
SV-2605-003-01 | Houzs Century | 5530-L(RHF) | SOFA | 06-06 | 06-10 | 06-10 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-09 | 2026-06-08 | LATE
SO-2605-242-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-242-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-243-01 | Houzs Century | 2009(A)-(K) | BEDFRAME | done | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-252-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-15 | 2026-06-13 | LATE
SO-2605-235-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-06 | 06-10 | 06-10 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-200-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-202-02 | Houzs Century | 2033(HF)(W)-(SS) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-202-01 | Houzs Century | 2033(HF)(W)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-123-02 | Houzs Century | 2038(A)-(SS) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-103-03 | Houzs Century | 5536-1A(RHF) | SOFA | - | done | 06-10 | 06-16 | 06-12 | 06-16 | done | done | 06-16 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-103-02 | Houzs Century | 5536-CNR | SOFA | - | done | done | 06-16 | done | 06-16 | done | done | 06-16 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-076-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-10 | 06-10 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-11 | LATE
SO-2604-281-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-270-02 | The Conts | 5535-L(RHF) | SOFA | - | 06-10 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-270-01 | The Conts | 5535-2A(LHF) | SOFA | 06-06 | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-265-02 | Houzs Century | DIVAN-(S) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-265-01 | Houzs Century | DIVAN-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-259-01 | Carress | DIVAN-(K) | BEDFRAME | done | 06-11 | 06-10 | - | 06-13 | done | 06-17 | 06-17 | 06-17 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-237-02 | Carress | 5531-2A(RHF) | SOFA | - | done | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-13 | 2026-06-12 | LATE
SO-2605-237-01 | Carress | 5531-L(LHF) | SOFA | done | done | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-13 | 2026-06-12 | LATE
SO-2605-223-04 | Houzs Century | 5536-2S | SOFA | - | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-223-03 | Houzs Century | 5536-2A(RHF) | SOFA | - | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-223-02 | Houzs Century | 5536-CNR | SOFA | - | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-223-01 | Houzs Century | 5536-1A(LHF) | SOFA | 06-08 | 06-11 | 06-10 | 06-16 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-200-03 | Houzs Century | DIVAN-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-200-02 | Houzs Century | DIVAN-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-206-01 | Houzs Century | DIVAN-(K) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-076-01 | Carress | 5531-L(LHF) | SOFA | 06-06 | 06-10 | 06-10 | 06-15 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-11 | LATE
SO-2605-273-02 | Houzs Century | 5535-2A(RHF) | SOFA | - | 06-12 | 06-11 | 06-17 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-273-01 | Houzs Century | 5535-L(LHF) | SOFA | 06-09 | 06-12 | 06-11 | 06-17 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-260-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-17 | 2026-06-15 | LATE
SO-2605-236-02 | Carress | 5531-L(RHF) | SOFA | - | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-17 | 2026-06-16 | LATE
SO-2605-236-01 | Carress | 5531-2A(LHF) | SOFA | 06-08 | 06-12 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-17 | 2026-06-16 | LATE
SO-2605-225-02 | Houzs Century | 5536-1A(RHF) | SOFA | - | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-225-01 | Houzs Century | 5536-1A(LHF) | SOFA | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-227-01 | Houzs Century | 1013-(K) | BEDFRAME | done | done | done | done | done | 06-02 | done | done | 06-02 | 2026-06-02 | 2026-05-31 | AT-RISK
SO-2605-234-03 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-02 | 2026-05-31 | AT-RISK
SO-2605-234-02 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-02 | 2026-05-31 | AT-RISK
SO-2605-181-01 | The Conts | 6112-2S | SOFA | done | 06-03 | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-180-01 | The Conts | 6112-2S | SOFA | done | 06-03 | 06-03 | 06-06 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-179-01 | The Conts | 6112-2S | SOFA | 06-02 | 06-04 | 06-03 | 06-06 | 06-04 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-178-01 | The Conts | 6112-2S | SOFA | 06-03 | 06-04 | 06-03 | 06-06 | 06-04 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-177-01 | The Conts | 6112-2S | SOFA | 06-03 | 06-04 | 06-03 | 06-06 | 06-04 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-291-01 | Houzs Century | 1003(A)-(K) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-08 | 2026-06-06 | AT-RISK
SO-2605-226-02 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-08 | 2026-06-06 | AT-RISK
SO-2605-226-01 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-08 | 2026-06-06 | AT-RISK
SO-2605-293-02 | Houzs Century | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-293-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-271-02 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-271-01 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-274-01 | Houzs Century | 1023-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-15 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-16 | 2026-06-14 | AT-RISK
SO-2605-216-04 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-216-03 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-216-02 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-216-01 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-211-01 | Houzs Century | 2009(A)-(SK) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-16 | 2026-06-14 | AT-RISK
SO-2605-228-01 | Houzs Century | 1030-(K) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-02 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-17 | 2026-06-15 | AT-RISK
SO-2605-069-01 | Carress | 1013-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | 06-16 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-18 | 2026-06-16 | AT-RISK
SO-2605-191-01 | Houzs Century | 2006(A)-(Q) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-02 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-17 | AT-RISK
SO-2604-088-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | done | done | - | - | - | - | - | 06-02 | 06-02 | 2026-05-04 | 2026-05-03 | ON-HOLD
SO-2604-088-02 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-04 | 2026-05-03 | ON-HOLD
SO-2604-088-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-04 | 2026-05-03 | ON-HOLD
SO-2605-291-02 | Houzs Century | 1005-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-02 | 06-04 | 06-06 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-06-06 | ON-TIME
SO-2605-292-03 | Houzs Century | 1007-(SS) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-15 | 2026-06-13 | ON-TIME
SO-2605-292-02 | Houzs Century | 1007-(SS) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-15 | 2026-06-13 | ON-TIME
SO-2605-281-01 | Houzs Century | 1005-(Q) | BEDFRAME | 06-05 | 06-08 | 06-06 | 06-02 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-15 | 2026-06-13 | ON-TIME
SO-2605-289-01 | Carress | 1013-(Q) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-22 | 2026-06-20 | ON-TIME
SO-2605-284-01 | Houzs Century | 1007-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | 06-16 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-19 | 2026-06-17 | ON-TIME
SO-2605-190-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-02 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-19 | 2026-06-17 | ON-TIME
SO-2605-303-02 | Carress | 5535-1A(RHF) | SOFA | - | 06-12 | 06-11 | 06-17 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-303-01 | Carress | 5535-2A(LHF) | SOFA | 06-09 | 06-12 | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-290-03 | Houzs Century | 5530-STOOL | SOFA | - | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-18 | ON-TIME
SO-2605-290-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-18 | ON-TIME
SO-2605-290-01 | Houzs Century | 5530-1A(LHF) | SOFA | 06-08 | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-18 | ON-TIME
SO-2605-106-06 | Houzs Century | 5535-1S | SOFA | - | done | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-05 | Houzs Century | 5535-1A(RHF) | SOFA | - | done | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-04 | Houzs Century | 5535-1A(LHF) | SOFA | - | done | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-03 | Houzs Century | 5535-1A(RHF) | SOFA | - | done | 06-11 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-02 | Houzs Century | 5535-1NA | SOFA | - | done | 06-11 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-01 | Houzs Century | 5535-1A(LHF) | SOFA | done | done | 06-11 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-301-01 | Carress | 5531-2S | SOFA | 06-09 | 06-13 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-29 | 2026-06-28 | ON-TIME
SO-2605-302-01 | Carress | 1007-(K) | BEDFRAME | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-29 | 2026-06-27 | ON-TIME
SO-2605-231-02 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-23 | ON-TIME
SO-2605-231-01 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-23 | ON-TIME
SO-2605-224-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-26 | 2026-06-25 | ON-TIME
SO-2605-224-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-26 | 2026-06-25 | ON-TIME
SO-2605-198-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-12 | 06-12 | 06-18 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-198-01 | Houzs Century | 5530-L(LHF) | SOFA | done | 06-12 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-199-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-199-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-182-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-12 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-24 | ON-TIME
SO-2605-182-01 | Carress | 5531-L(LHF) | SOFA | 06-09 | 06-13 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-24 | ON-TIME
SO-2605-189-01 | Houzs Century | 1003(A)-(K) | BEDFRAME | done | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-22 | ON-TIME
SV-2605-002-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | 06-13 | 06-12 | 06-02 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-07-08 | 2026-07-06 | ON-TIME
CO-2605-008-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | 06-13 | 06-20 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 |  |  | ON-TIME
CO-2605-008-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | 06-13 | 06-20 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 |  |  | ON-TIME
SO-2605-184-03 | Houzs Century | 5536-1A(RHF) | SOFA | - | 06-13 | 06-12 | 06-20 | 06-15 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-184-02 | Houzs Century | 5536-CNR | SOFA | - | 06-13 | 06-12 | 06-20 | 06-15 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-184-01 | Houzs Century | 5536-2A(LHF) | SOFA | 06-09 | 06-13 | 06-12 | 06-20 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-06-24 | 2026-06-23 | ON-TIME

## 1-Cut
裁布 Fabric Cut — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Fab Cutting DD | PIC 1 | PIC 2 | Completed Date | Overdue | Raw Material Ready | Status
2026-06-02 Tue |  | 1 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ KS-18 ¦ (FC) | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 | 2026-06-02 | [5 empty] | WAITING
2026-06-02 Tue |  | 2 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (19") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-02 Tue | 2026-05-25 | 3 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF)+L(RHF) ¦ (24) ¦ M2402-13 ¦ (FC) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue | 2026-05-19 | 4 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF)+1NA+L(RHF) ¦ (32) ¦ BO315-1 ¦ (FC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue | 2026-05-19 | 5 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF)+1A(RHF) ¦ BO315-31 ¦ (FC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-06-03 | [5 empty] | WAITING
2026-06-02 Tue | 2026-05-21 | 6 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF)+1NA+1A(RHF) ¦ (32) ¦ AM275-1 ¦ (FC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue | 2026-05-13 | 7 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF)+1A(RHF) ¦ (28) ¦ BO315-22 ¦ (FC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 | [5 empty] | WAITING
2026-06-02 Tue |  | 8 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S ¦ (30) ¦ PC151-01 ¦ (FC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-03 Wed |  | 9 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 10 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) ¦ (5FT) ¦ (22") ¦ (DV 4") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 11 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-12 ¦ (FC) | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-03 Wed |  | 12 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 13 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 14 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ KS-14 ¦ (FC) | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 | ZIN MIN NWE |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 15 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-04 ¦ (FC) | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 16 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (23") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 17 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) ¦ (200CMX200CM) ¦ (21") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-03 Wed |  | 18 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-18 ¦ (FC) | 3.5FT | PC151-18 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 | ZIN MIN NWE | THI THI AYE |  |  |  | WAITING
2026-06-03 Wed |  | 19 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-03 Wed |  | 20 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-09 ¦ (FC) | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-03 Wed |  | 21 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-11 ¦ (FC) | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-03 Wed |  | 22 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-03 Wed |  | 23 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S ¦ (30) ¦ PC151-01 ¦ (FC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-03 Wed |  | 24 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S ¦ (30) ¦ PC151-01 ¦ (FC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed | 2026-05-13 | 25 | SO-2605-063-03 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | LONG PILLOW | LONG PILLOW ¦ (12" X 28") ¦ BO315-31 ¦ (FC) | 12" X 28" | BO315-31 |  |  |  | 1 |  |  | 2026-05-13 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed | 2026-05-13 | 26 | SO-2605-063-04 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | LONG PILLOW | LONG PILLOW ¦ (12" X 28") ¦ BO315-31 ¦ (FC) | 12" X 28" | BO315-31 |  |  |  | 1 |  |  | 2026-05-13 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 27 | SO-2604-324-03 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ BO315-22 ¦ (FC) | 16" X 16" | BO315-22 |  |  |  | 1 |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 28 | SO-2604-324-04 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ BO315-22 ¦ (FC) | 16" X 16" | BO315-22 |  |  |  | 1 |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 29 | SO-2605-104-04 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-3 ¦ (FC) | 16" X 16" | CH141-3 | 0 | 0 |  | 1 |  |  | 2026-05-20 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 30 | SO-2605-104-05 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-3 ¦ (FC) | 16" X 16" | CH141-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 31 | SO-2605-104-06 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-3 ¦ (FC) | 16" X 16" | CH141-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 32 | SO-2605-222-03 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-7 ¦ (FC) | 16" X 16" | CH141-7 |  |  |  | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 33 | SO-2605-222-04 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-5 ¦ (FC) | 16" X 16" | CH141-5 |  |  |  | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 34 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (26") ¦ (DV 8") ¦ PC151-04 ¦ (FC) | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  | 2026-06-02 | [5 empty] | WAITING
2026-06-04 Thu |  | 35 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. | 2026-06-02 | [5 empty] | WAITING
2026-06-04 Thu |  | 36 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-06 ¦ (FC) | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-04 Thu |  | 37 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) ¦ (5FT) ¦ (20") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-04 Thu |  | 38 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-04 Thu |  | 39 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) ¦ (5FT) ¦ (26") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 40 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) ¦ (5FT) ¦ (26") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu | 2026-05-13 | 41 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF)+2A(RHF) ¦ (28) ¦ CH141-12 ¦ (FC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-04 Thu | 2026-05-25 | 42 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF)+2A(RHF) ¦ (28) ¦ BO315-22 ¦ (FC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu | 2026-05-25 | 43 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (28) ¦ GARFIELD - 3 TUNDORA ¦ (FC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-06-05 | [5 empty] | WAITING
2026-06-05 Fri |  | 44 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) ¦ (5FT) ¦ (23") ¦ (DV 10") ¦ PC151-03 ¦ (FC) | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 45 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) ¦ (6FT) ¦ (23") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 46 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (19") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 47 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (21") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 48 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 49 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) ¦ (3.5FT) ¦ (19") ¦ (DV 8") ¦ PC151-03 ¦ (FC) | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 50 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) ¦ (3.5FT) ¦ (19") ¦ (DV 8") ¦ PC151-03 ¦ (FC) | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 51 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 52 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-14 ¦ (FC) | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 53 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-13 ¦ (FC) | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 54 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (24") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 55 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (26") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 56 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (21") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 57 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 58 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-06 ¦ (FC) | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 59 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 60 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 61 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 62 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 63 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 64 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 65 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 66 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-05 Fri |  | 67 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) ¦ (3FT) ¦ (16") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 68 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) ¦ (6FT) ¦ (22") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm | 2026-06-07 | [5 empty] | WAITING
2026-06-05 Fri |  | 69 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-05 Fri |  | 70 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) ¦ (6FT) ¦ (23") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri |  | 71 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-03 | [5 empty] | WAITING
2026-06-05 Fri | 2026-05-25 | 72 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (28) ¦ KN390-2 ¦ (FC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 73 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF)+1NA+CSL+L(RHF) ¦ (30) ¦ FABRIC HR805-10 ¦ (FC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 74 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 75 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 76 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 77 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 78 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 10") ¦ PC151-12 ¦ (FC) | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 79 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 80 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (21") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 81 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (19") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-06 Sat |  | 82 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) ¦ (200CMX200CM) ¦ (26") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 83 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) ¦ (6FT) ¦ (24") ¦ (DV 10") ¦ PC151-02 ¦ (FC) | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 84 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) ¦ (3.5FT) ¦ (24") ¦ (DV 12") ¦ PC151-02 ¦ (FC) | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 85 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 86 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-06 Sat |  | 87 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-03 ¦ (FC) | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-06 Sat |  | 88 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) ¦ (28) ¦ BO315-2 ¦ (FC) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat | 2026-05-25 | 89 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (24) ¦ GARFIELD-2 CHERVRON ¦ (FC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 90 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF)+L(RHF) ¦ (28) ¦ PC151-01 ¦ (FC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-08 Mon |  | 91 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-10 | [5 empty] | WAITING
2026-06-08 Mon |  | 92 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ PC151-13 ¦ (FC) | 5FT | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-06-09 | [5 empty] | WAITING
2026-06-08 Mon |  | 93 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-13 | [5 empty] | WAITING
2026-06-08 Mon |  | 94 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) ¦ (6FT) ¦ (22") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-08 Mon |  | 95 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-10 | [5 empty] | WAITING
2026-06-08 Mon |  | 96 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  | 2026-06-10 | [5 empty] | WAITING
2026-06-08 Mon |  | 97 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-10 ¦ (FC) | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  | 2026-06-08 | [5 empty] | WAITING
2026-06-08 Mon |  | 98 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF)+2A(RHF)+STOOL ¦ (28) ¦ BO315-21 ¦ (FC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-08 | [5 empty] | WAITING
2026-06-08 Mon |  | 99 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF)+L(RHF) ¦ (28) ¦ M2402-1 ¦ (FC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-06 | [5 empty] | WAITING
2026-06-08 Mon |  | 100 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF)+CNR+2A(RHF)+2S ¦ (30) ¦ FABRIC HR805-90 ¦ (FC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-03 | [5 empty] | WAITING
2026-06-08 Mon |  | 101 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | DIVAN-(K) ¦ (6FT) ¦ (10") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | 6FT | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  | 2026-06-03 | [5 empty] | WAITING
2026-06-08 Mon |  | 102 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | DIVAN-(Q) ¦ (5FT) ¦ (8") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-08 Mon |  | 103 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | DIVAN-(Q) ¦ (5FT) ¦ (8") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-08 Mon |  | 104 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | DIVAN-(Q) ¦ (5FT) ¦ (15") ¦ (DV 8") ¦ PC151-14 ¦ (FC) | 5FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg | 2026-06-03 | [5 empty] | WAITING
2026-06-08 Mon |  | 105 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | DIVAN-(S) ¦ (3FT) ¦ (15") ¦ (DV 8") ¦ PC151-14 ¦ (FC) | 3FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 106 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-16 | [5 empty] | WAITING
2026-06-09 Tue |  | 107 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) ¦ (6FT) ¦ (28") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-20 | [5 empty] | WAITING
2026-06-09 Tue |  | 108 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-02 ¦ (FC) | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-16 | [5 empty] | WAITING
2026-06-09 Tue |  | 109 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S ¦ (28) ¦ M2402-13 ¦ (FC) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-18 | [5 empty] | WAITING
2026-06-09 Tue |  | 110 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (24) ¦ NINJA 02 ¦ (FC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-09 Tue |  | 111 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF)+1A(RHF) ¦ (32) ¦ KN390-3 ¦ (FC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-11 | [5 empty] | WAITING
2026-06-09 Tue |  | 112 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF)+2A(RHF) ¦ (32) ¦ BO315-24 ¦ (FC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-05 | [5 empty] | WAITING
2026-06-09 Tue |  | 113 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF)+1A(RHF) ¦ (30) ¦ NINJA 02 ¦ (FC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 114 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF)+CNR+1A(RHF) ¦ (30) ¦ BO315-5 ¦ (FC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-13 | [5 empty] | WAITING

## 2-Sew
车缝 Fabric Sew — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Fab Sewing DD | PIC 1 | PIC 2 | Completed Date | Overdue | Status
2026-06-02 Tue |  | 1 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 10" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 2 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" PC151-01 | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 3 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 16 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 4 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" PC151-01 | 6FT | PC151-01 | 16 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-18 | 5 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 8" Divan- 6FT KS-18 | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-18 | 6 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" KS-18 | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-25 | 7 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" PC151-10 | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-25 | 8 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 8" Divan- 5FT PC151-10 | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 9 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 10" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 10 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" PC151-01 | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-26 | 11 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Left Arm M2402-13 | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-14 | 12 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 M2402-13 | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-26 | 13 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Back Cushion 24 M2402-13 | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 14 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-14 | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 15 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 KN390-14 | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 16 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531 -Right Arm KN390-14 | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-18 | 17 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Left Arm M2402-4 | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-18 | 18 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Back Cushion 28 M2402-4 | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-18 | 19 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S -Base 28 M2402-4 | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-18 | 20 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Right Arm M2402-4 | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue | 2026-05-09 | 21 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531-L(LHF) -Base 28 KN390-14 | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 22 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531 -Left Arm KN390-14 | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 23 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-14 | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-26 | 24 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Right Arm M2402-13 | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-26 | 25 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Back Cushion 24 M2402-13 | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-26 | 26 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) -Base 24 M2402-13 | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 27 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 28 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Back Cushion 32 BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 29 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Left Arm BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 30 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA -Base 32 BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 31 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535 -Back Cushion 32 BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 32 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) -Base 32 BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 33 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Back Cushion 32 BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 34 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Right Arm BO315-1 | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 35 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Left Arm CH141-14 | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 36 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 CH141-14 | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 37 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Back Cushion 30 CH141-14 | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 38 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) -Base 30 CH141-14 | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 39 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Right Arm CH141-14 | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 40 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Back Cushion 30 CH141-14 | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-26 | 41 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Back Cushion 30 BO315-23 | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 42 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Left Arm AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 43 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 44 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Back Cushion 32 AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed | 2026-05-18 | 45 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 BO315-22 | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-18 | 46 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Back Cushion 28 BO315-22 | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-18 | 47 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Right Arm BO315-22 | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 48 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Back Cushion 32 AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 49 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Right Arm AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 50 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 51 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA -Base 32 AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 52 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540 -Back Cushion 32 AM275-1 | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed | 2026-05-18 | 53 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Back Cushion 28 BO315-22 | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-18 | 54 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Left Arm BO315-22 | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-18 | 55 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 BO315-22 | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 56 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Back Cushion 26 BO315-23 | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 57 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Right Arm BO315-23 | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 58 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 BO315-23 | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 59 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL BO315-23 |  | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 60 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL BO315-23 |  | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 61 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Back Cushion 32 BO315-23 | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 62 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Left Arm BO315-23 | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 63 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) -Base 32 BO315-23 | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 64 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Left Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 65 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Right Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 66 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S -Base 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 67 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 68 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Left Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 69 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Right Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 70 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 71 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S -Base 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-02 | OHN MAR SHEIN |  |  |  | WAITING
2026-06-04 Thu | 2026-05-18 | 72 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S -Base 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-18 | 73 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-18 | 74 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Right Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-18 | 75 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Left Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 76 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S -Base 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 77 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-18 | 78 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Left Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-18 | 79 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Right Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 80 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S -Base 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 81 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 82 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Left Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 83 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Right Arm PC151-01 | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-25 | 84 | SO-2604-083-04 | PO-2603-104 | TCF0409 | Carress | KL | SO-2604-083 | LONG PILLOW | LONG PILLOW KN390-2 |  | KN390-2 |  |  |  | 1 |  |  | 2026-04-09 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-25 | 85 | SO-2604-083-05 | PO-2603-104 | TCF0409 | Carress | KL | SO-2604-083 | LONG PILLOW | LONG PILLOW KN390-2 |  | KN390-2 |  |  |  | 1 |  |  | 2026-04-09 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 86 | SO-2605-063-03 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | LONG PILLOW | LONG PILLOW BO315-31 | 12" X 28" | BO315-31 |  |  |  | 1 |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 87 | SO-2605-063-04 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | LONG PILLOW | LONG PILLOW BO315-31 | 12" X 28" | BO315-31 |  |  |  | 1 |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 88 | SO-2604-324-03 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | SQUARE PILLOW | SQUARE PILLOW BO315-22 | 16" X 16" | BO315-22 |  |  |  | 1 |  |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 89 | SO-2604-324-04 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | SQUARE PILLOW | SQUARE PILLOW BO315-22 | 16" X 16" | BO315-22 |  |  |  | 1 |  |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-18 | 90 | SO-2605-104-06 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW CH141-3 | 16" X 16" | CH141-3 | 0 | 0 |  | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 91 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 92 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri | 2026-05-26 | 93 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri | 2026-05-26 | 94 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri | 2026-05-26 | 95 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri | 2026-05-26 | 96 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 97 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 4" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 98 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri | 2026-05-26 | 99 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri | 2026-05-26 | 100 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" PC151-01 | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 101 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 10" Divan- 6FT PC151-02 | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 102 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" PC151-02 | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 103 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 8" Divan- 6FT PC151-12 | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 104 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" PC151-12 | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 105 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT PC151-10 | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 106 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 107 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT PC151-10 | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 108 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri | 2026-05-23 | 109 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 8" Divan- 5FT KS-14 | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri | 2026-05-23 | 110 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" KS-14 | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 111 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 10" Divan- 5FT PC151-04 | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 112 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" PC151-04 | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 113 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 114 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" PC151-02 | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 115 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 8" Divan- 200CMX200CM PC151-10 | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 116 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" PC151-10 | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 117 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 8" Divan- 3.5FT PC151-02 | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 118 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" PC151-02 | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 119 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT PC151-09 | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 120 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" PC151-09 | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 121 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT PC151-11 | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 122 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" PC151-11 | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  | 2026-06-01 |  |  |  |  | WAITING
2026-06-05 Fri |  | 123 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 124 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 125 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 126 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 127 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" PC151-18 | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 128 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT PC151-18 | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 129 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 130 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 131 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 132 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-01 | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 133 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT PC151-10 | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 134 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-10 | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri | 2026-05-18 | 135 | SO-2605-104-04 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW CH141-3 | 16" X 16" | CH141-3 | 0 | 0 |  | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri | 2026-05-18 | 136 | SO-2605-104-05 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW CH141-3 | 16" X 16" | CH141-3 | 0 | 0 |  | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 137 | SO-2605-222-03 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | SQUARE PILLOW | SQUARE PILLOW CH141-7 | 16" X 16" | CH141-7 |  |  |  | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 138 | SO-2605-222-04 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | SQUARE PILLOW | SQUARE PILLOW CH141-5 | 16" X 16" | CH141-5 |  |  |  | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat | 2026-05-26 | 139 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" PC151-04 | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat | 2026-05-26 | 140 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 8" Divan- 6FT PC151-04 | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 141 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 8" Divan- 6FT PC151-02 | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 142 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-02 | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat | 2026-05-26 | 143 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" PC151-06 | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat | 2026-05-26 | 144 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 8" Divan- 6FT PC151-06 | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat | 2026-05-26 | 145 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 8" Divan- 5FT PC151-15 | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat | 2026-05-26 | 146 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" PC151-15 | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 147 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-06 Sat |  | 148 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" PC151-01 | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-06 Sat |  | 149 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 150 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 151 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 152 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 153 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 154 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 155 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-25 | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 156 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 CH141-12 | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 157 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Back Cushion 28 CH141-12 | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 158 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Right Arm CH141-12 | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 159 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 BO315-22 | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 160 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-22 | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 161 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Right Arm BO315-22 | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 162 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530 -Back Cushion 28 BO315-25 | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 163 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) -Base 28 CH141-12 | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 164 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Back Cushion 28 CH141-12 | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 165 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Left Arm CH141-12 | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 166 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Left Arm BO315-22 | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 167 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-22 | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 168 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) -Base 28 BO315-22 | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 169 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-25 | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 170 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL BO315-25 | 24 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 171 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Right Arm M2402-4 | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 172 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-4 | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 173 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 M2402-4 | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 174 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" PC151-02 | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 175 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 8" Divan- 200CMX200CM PC151-02 | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 176 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 10" Divan- 5FT PC151-03 | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-08 Mon |  | 177 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" PC151-03 | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-08 Mon | 2026-05-26 | 178 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 8" Divan- 5FT PC151-14 | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 179 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" PC151-14 | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 180 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 181 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" PC151-01 | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 182 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 183 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 184 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Left Arm M2402-18 | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 185 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 M2402-18 | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 186 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-18 | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 187 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 M2402-4 | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 188 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Left Arm M2402-4 | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 189 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-4 | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 190 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 M2402-18 | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 191 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-18 | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 192 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Right Arm M2402-18 | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 193 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 GARFIELD - 3 TUNDORA | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 194 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 195 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Right Arm GARFIELD - 3 TUNDORA | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 196 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-2 | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 197 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 KN390-2 | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 198 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Right Arm KN390-2 | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 199 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Left Arm GARFIELD - 3 TUNDORA | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 200 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) -Base 28 GARFIELD - 3 TUNDORA | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon | 2026-05-26 | 201 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 202 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) -Base 28 KN390-2 | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 203 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Left Arm KN390-2 | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 204 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-2 | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 205 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 206 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Back Cushion 30 FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 207 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Left Arm FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 208 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA -Base 30 FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 209 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540 -Back Cushion 30 FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 210 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 211 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 212 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) -Base 30 FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 213 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Back Cushion 30 FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 214 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Right Arm FABRIC HR805-10 | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 215 | SO-2605-300-01 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | DIVAN-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 216 | SO-2605-296-01 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT PC151-03 | 5FT | PC151-03 | 0 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 217 | SO-2605-296-02 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT PC151-03 | 5FT | PC151-03 | 0 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 218 | SO-2605-296-03 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(S) | 8" Divan- 3FT PC151-03 | 3FT | PC151-03 | 0 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 219 | SO-2605-283-01 | PO-008976 | HC10887 | Houzs Century | PG | SO-2605-283 | DIVAN-(SS) | 8" Divan- 3.5FT PC151-01 | 3.5FT | PC151-01 | 0 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 220 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 221 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" PC151-01 | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 222 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 223 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 224 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 225 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 226 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 227 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 228 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 229 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 230 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 10" Divan- 5FT PC151-01 | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 231 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" PC151-01 | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 232 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT PC151-03 | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 233 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 234 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT PC151-03 | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 235 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 236 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 8" Divan- 6FT PC151-17 | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 237 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" PC151-17 | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 238 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT PC151-14 | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 239 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" PC151-14 | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 240 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT PC151-13 | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 241 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" PC151-13 | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 242 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 243 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" PC151-01 | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 244 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 8" Divan- 6FT PC151-17 | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 245 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" PC151-17 | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 246 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 247 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" PC151-01 | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 248 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 8" Divan- 5FT PC151-17 | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 249 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" PC151-17 | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 250 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" PC151-06 | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 251 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT PC151-06 | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 252 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT PC151-15 | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 253 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 254 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" PC151-02 | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 255 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 256 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 257 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 258 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT PC151-15 | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 259 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 260 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 261 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 262 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 263 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 264 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 8" Divan- 5FT PC151-17 | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 265 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" PC151-17 | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 266 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 267 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" PC151-01 | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-09 Tue |  | 268 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" PC151-02 | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 269 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 8" Divan- 3FT PC151-02 | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 270 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm | 2026-06-09 |  |  |  |  | WAITING
2026-06-09 Tue |  | 271 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm | 2026-06-09 |  |  |  |  | WAITING
2026-06-09 Tue |  | 272 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 8" Divan- 5FT PC151-17 | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 273 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" PC151-17 | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 274 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-02 | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 275 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 8" Divan- 6FT PC151-02 | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 276 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 277 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" PC151-01 | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 278 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 279 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 280 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 281 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 282 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 283 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue | 2026-05-26 | 284 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue | 2026-05-26 | 285 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 286 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 287 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-01 | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-10 Wed |  | 288 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 289 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 290 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-12 | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 291 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT PC151-12 | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 292 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 293 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-01 | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 294 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-10 Wed |  | 295 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" PC151-01 | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-10 Wed |  | 296 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 297 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 298 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 8" Divan- 200CMX200CM PC151-01 | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 299 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" PC151-01 | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 300 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 10" Divan- 6FT PC151-02 | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-10 Wed |  | 301 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" PC151-02 | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-10 Wed |  | 302 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT PC151-02 | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-10 Wed |  | 303 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" PC151-02 | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-10 Wed |  | 304 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-02 | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 305 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 306 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 307 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed | 2026-05-26 | 308 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" PC151-03 | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-10 Wed | 2026-05-26 | 309 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 8" Divan- 3.5FT PC151-03 | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-10 Wed |  | 310 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) -Base 28 BO315-2 | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 311 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-2 | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 312 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Right Arm BO315-2 | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 313 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Right Arm GARFIELD-2 CHERVRON | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 314 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 315 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 GARFIELD-2 CHERVRON | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 316 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Left Arm GARFIELD-2 CHERVRON | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 317 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 318 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) -Base 24 GARFIELD-2 CHERVRON | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 319 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) -Base 28 PC151-01 | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 320 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Back Cushion 28 PC151-01 | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 321 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Right Arm PC151-01 | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 322 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-11 Thu |  | 323 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-11 Thu |  | 324 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 8" Divan- 5FT PC151-13 | 5FT | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 325 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 1013-(Q) -HB 24" PC151-13 | 5FT | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 326 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-11 Thu |  | 327 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" PC151-01 | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-11 Thu |  | 328 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 329 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 330 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 8" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-11 Thu |  | 331 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-11 Thu |  | 332 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 8" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-11 Thu |  | 333 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" PC151-02 | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-11 Thu |  | 334 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" PC151-10 | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 335 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 10" Divan- 5FT PC151-10 | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 336 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 337 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 338 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Left Arm BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 339 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 340 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 341 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Right Arm BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 342 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL BO315-21 | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 343 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) -Base 28 M2402-1 | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 344 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Right Arm M2402-1 | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 345 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Back Cushion 28 M2402-1 | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 346 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Back Cushion 28 PC151-01 | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 347 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Left Arm PC151-01 | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 348 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 PC151-01 | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 349 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 350 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Back Cushion 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 351 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Left Arm FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 352 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Back Cushion 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 353 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 354 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Right Arm FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 355 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Right Arm FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 356 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S -Base 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 357 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Back Cushion 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 358 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Left Arm FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 359 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR -Base 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 360 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536 -Back Cushion 30 FABRIC HR805-90 | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 361 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 362 | SO-2605-259-01 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | DIVAN-(K) | 8" Divan- 6FT PC151-13 | 6FT | PC151-13 | 14 | 8 | 4 | 1 | Divan Top(W) | Divan Only specified; product matched to DIVAN-(K) | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 363 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 364 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT PC151-01 | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 365 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | 8" Divan- 5FT PC151-14 | 5FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 366 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | 8" Divan- 3FT PC151-14 | 3FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri | 2026-05-26 | 367 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" PC151-01 | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri | 2026-05-26 | 368 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 10" Divan- 6FT PC151-01 | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 369 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 10" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 370 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" PC151-02 | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 371 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 8" Divan- 6FT PC151-15 | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-22 |  |  |  |  | WAITING
2026-06-12 Fri |  | 372 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" PC151-15 | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-22 |  |  |  |  | WAITING
2026-06-12 Fri |  | 373 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 10" Divan- 5FT PC151-02 | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 374 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" PC151-02 | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 375 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 BO315-3 | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 376 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Right Arm BO315-3 | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 377 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-3 | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 378 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-3 | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 379 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) -Base 28 BO315-3 | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 380 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Left Arm BO315-3 | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 381 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 M2402-1 | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 382 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Back Cushion 28 M2402-1 | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 383 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Left Arm M2402-1 | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 384 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 NINJA 02 | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 385 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Back Cushion 24 NINJA 02 | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 386 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Right Arm NINJA 02 | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 387 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 KN390-3 | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-13 |  |  |  |  | WAITING
2026-06-12 Fri |  | 388 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Back Cushion 32 KN390-3 | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-13 |  |  |  |  | WAITING
2026-06-12 Fri |  | 389 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Right Arm KN390-3 | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-13 |  |  |  |  | WAITING
2026-06-12 Fri |  | 390 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 KN390-3 | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-13 |  |  |  |  | WAITING
2026-06-12 Fri |  | 391 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Back Cushion 32 KN390-3 | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-13 |  |  |  |  | WAITING
2026-06-12 Fri |  | 392 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Left Arm KN390-3 | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-13 |  |  |  |  | WAITING
2026-06-12 Fri |  | 393 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 BO315-24 | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 394 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Back Cushion 32 BO315-24 | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 395 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Right Arm BO315-24 | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 396 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) -Base 32 BO315-24 | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 397 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Back Cushion 32 BO315-24 | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 398 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Left Arm BO315-24 | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 399 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 NINJA 02 | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 400 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Back Cushion 30 NINJA 02 | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 401 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Left Arm NINJA 02 | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 402 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 NINJA 02 | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 403 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Back Cushion 30 NINJA 02 | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 404 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Right Arm NINJA 02 | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 405 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 12" Divan- 6FT PC151-14 | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  | 2026-07-01 |  |  |  |  | WAITING
2026-06-13 Sat |  | 406 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" PC151-14 | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  | 2026-07-01 |  |  |  |  | WAITING
2026-06-13 Sat |  | 407 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S -Base 28 M2402-13 | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-13 Sat |  | 408 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Back Cushion 28 M2402-13 | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-13 Sat |  | 409 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Left Arm M2402-13 | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-13 Sat |  | 410 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Right Arm M2402-13 | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-13 Sat |  | 411 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) -Base 24 NINJA 02 | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-13 Sat |  | 412 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Back Cushion 24 NINJA 02 | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-13 Sat |  | 413 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Left Arm NINJA 02 | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-13 Sat |  | 414 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 415 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Back Cushion 30 BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 416 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Right Arm BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 417 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 418 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Back Cushion 30 BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 419 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Left Arm BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 420 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR -Base 30 BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 421 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536 -Back Cushion 30 BO315-5 | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-15 |  |  |  |  | WAITING

## 3-Wood
锯木 Wood Cut — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Wood Cutting DD | PIC 1 | PIC 2 | Completed Date | Overdue | Status
2026-06-02 Tue |  | 1 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-25 | YE LI SOE | KYAR TUN HLA |  | OVERDUE | WAITING
2026-06-02 Tue |  | 2 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" (WD) | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 3 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" (WD) | 6FT | PC151-01 | 16 | 8 | 1 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 4 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 8" Divan- 6FT (WD) | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 5 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" (WD) | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 6 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 7 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" (WD) | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 8 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-11 | 10 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 9 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" (WD) | 3.5FT | PC151-11 | 10 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 10 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-25 | YE LI SOE | KYAR TUN HLA |  | OVERDUE | WAITING
2026-06-02 Tue |  | 11 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Left Arm (WC) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 | YE LI SOE | KYAR TUN HLA |  | OVERDUE | WAITING
2026-06-02 Tue |  | 12 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 13 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 14 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 15 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 16 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 17 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S -Base 28 (WC) | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 18 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Right Arm (WC) | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 19 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Left Arm (WC) | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 20 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (WC) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 21 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Left Arm (WC) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 22 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Back Cushion 28 (WC) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-09 | 23 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531 -Left Arm (WC) | 28 | KN390-14 | 0 | 0 | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 24 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (WC) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 | YE LI SOE | KYAR TUN HLA |  | OVERDUE | WAITING
2026-06-02 Tue |  | 25 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Right Arm (WC) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 | YE LI SOE | KYAR TUN HLA |  | OVERDUE | WAITING
2026-06-02 Tue |  | 26 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 27 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Back Cushion 32 (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 28 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Left Arm (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 29 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA -Base 32 (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 30 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535 -Back Cushion 32 (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 31 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (WC) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 32 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Back Cushion 30 (WC) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 33 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Left Arm (WC) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 34 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 35 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Back Cushion 32 (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 36 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Right Arm (WC) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 37 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (WC) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 38 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Back Cushion 30 (WC) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 39 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Right Arm (WC) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 40 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Left Arm (WC) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-06-26 | KYAR TUN HLA | YE LI SOE |  |  | WAITING
2026-06-02 Tue |  | 41 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Right Arm (WC) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-06-26 | KYAR TUN HLA | YE LI SOE |  |  | WAITING
2026-06-02 Tue |  | 42 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Back Cushion 30 (WC) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 43 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536-2S -Base 30 (WC) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-06-26 | KYAR TUN HLA | YE LI SOE |  |  | WAITING
2026-06-02 Tue |  | 44 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (WC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 45 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Back Cushion 28 (WC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 46 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Right Arm (WC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 47 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (WC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 48 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Back Cushion 28 (WC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 49 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Left Arm (WC) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 50 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Back Cushion (WC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 51 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Left Arm (WC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 52 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF) -Base (WC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 53 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Back Cushion 32 (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 54 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Left Arm (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 55 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 56 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Right Arm (WC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 57 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Back Cushion (WC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 58 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540-1A(RHF) -Base (WC) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 59 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Back Cushion 32 (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 60 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 61 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Right Arm (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 62 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA -Base 32 (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 63 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540 -Back Cushion 32 (WC) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 64 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (WC) | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 65 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Back Cushion 26 (WC) | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 66 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Right Arm (WC) | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 67 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (WC) |  | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 68 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (WC) |  | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 69 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (WC) | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 70 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Back Cushion 32 (WC) | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 71 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Left Arm (WC) | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-11 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 72 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 73 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 74 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 75 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 76 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 77 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 78 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 79 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 80 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 81 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 82 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 83 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 84 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 85 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 86 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 87 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 88 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 89 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 90 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 91 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 92 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 93 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 94 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 95 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 96 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 97 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 98 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 99 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 100 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 101 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 102 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 103 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" (WD) | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 104 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 105 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" (WD) | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 106 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 4" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 107 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" (WD) | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 108 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 109 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" (WD) | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 110 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 111 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" (WD) | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 112 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-13 | 14 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 113 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 1007-(K) -HB 23" (WD) | 6FT | PC151-13 | 14 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 114 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 115 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 1007-(Q) -HB 21" (WD) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 116 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-17 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 117 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-17 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 118 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 119 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 120 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 121 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 122 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 123 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" (WD) | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 124 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu | 2026-05-26 | 125 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" (WD) | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 126 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 127 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" (WD) | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 128 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 129 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 130 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 131 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 132 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 133 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" (WD) | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 134 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 8" Divan- 200CMX200CM (WD) | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 135 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" (WD) | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 136 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 137 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" (WD) | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 138 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 139 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" (WD) | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 140 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 141 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" (WD) | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 142 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 143 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 144 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 145 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 146 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 147 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 148 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112-2S -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 149 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 150 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 151 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 152 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 153 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 154 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 155 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" (WD) | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 156 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 157 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 158 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 159 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" (WD) | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 160 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 161 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" (WD) | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 162 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 163 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" (WD) | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 164 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 165 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" (WD) | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 166 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-05 Fri |  | 167 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" (WD) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-05 Fri |  | 168 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 169 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 170 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 171 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" (WD) | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 172 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 173 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" (WD) | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 174 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 175 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Left Arm (WC) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 176 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 177 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Right Arm (WC) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 178 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530-1NA -Base 28 (WC) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 179 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530 -Back Cushion 28 (WC) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 180 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Right Arm (WC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 181 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 182 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 183 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 184 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 185 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Right Arm (WC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 186 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (WC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 187 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Left Arm (WC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 188 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Back Cushion 28 (WC) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 189 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (WC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 190 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 191 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Left Arm (WC) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 192 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 8" Divan- 200CMX200CM (WD) | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 193 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" (WD) | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 194 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-06 Sat |  | 195 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" (WD) | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-06 Sat |  | 196 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 197 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" (WD) | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 198 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 199 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" (WD) | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 200 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 201 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" (WD) | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 202 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 203 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" (WD) | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 204 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Left Arm (WC) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 205 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (WC) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 206 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Back Cushion 28 (WC) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 207 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Left Arm (WC) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 208 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (WC) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 209 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Back Cushion 28 (WC) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 210 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 211 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 212 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 213 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 214 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 215 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 216 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 217 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 218 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 219 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 220 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 221 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 222 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Back Cushion 28 (WC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 223 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Left Arm (WC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 224 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (WC) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 225 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Back Cushion 28 (WC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 226 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Left Arm (WC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 227 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (WC) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 228 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 229 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Back Cushion 30 (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 230 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Left Arm (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 231 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA -Base 30 (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 232 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540 -Back Cushion 30 (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 233 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 234 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 235 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 236 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Back Cushion 30 (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 237 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Right Arm (WC) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 238 | SO-2605-300-01 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | DIVAN-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 239 | SO-2605-296-01 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-03 | 0 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 240 | SO-2605-296-02 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-03 | 0 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 241 | SO-2605-296-03 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(S) | 8" Divan- 3FT (WD) | 3FT | PC151-03 | 0 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 242 | SO-2605-283-01 | PO-008976 | HC10887 | Houzs Century | PG | SO-2605-283 | DIVAN-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-01 | 0 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 243 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 244 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 245 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 246 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 247 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 248 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 249 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 250 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 251 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-08 Mon |  | 252 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" (WD) | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-08 Mon |  | 253 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 254 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" (WD) | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 255 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 256 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" (WD) | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 257 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 258 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" (WD) | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 259 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 260 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" (WD) | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 261 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 262 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" (WD) | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 263 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 264 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" (WD) | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 265 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 266 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" (WD) | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 267 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 268 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" (WD) | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 269 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 270 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 271 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 272 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 273 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 274 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 275 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 276 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" (WD) | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 277 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 278 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 279 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 280 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 281 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 282 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 283 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 284 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 285 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 286 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 287 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 288 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" (WD) | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-08 Mon |  | 289 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 8" Divan- 3FT (WD) | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 290 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" (WD) | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 291 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm | 2026-06-10 |  |  |  |  | WAITING
2026-06-08 Mon |  | 292 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" (WD) | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm | 2026-06-10 |  |  |  |  | WAITING
2026-06-08 Mon |  | 293 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 294 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" (WD) | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 295 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 296 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" (WD) | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 297 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-09 Tue |  | 298 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" (WD) | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-09 Tue |  | 299 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 300 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" (WD) | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 301 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 302 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 303 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 304 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 305 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 306 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 307 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 308 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 309 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 310 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 311 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-09 Tue |  | 312 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" (WD) | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-09 Tue |  | 313 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-09 Tue |  | 314 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" (WD) | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-09 Tue |  | 315 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-09 Tue |  | 316 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" (WD) | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-09 Tue |  | 317 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 318 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 319 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 8" Divan- 200CMX200CM (WD) | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 320 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" (WD) | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 321 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 322 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" (WD) | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 323 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT (WD) | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 324 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" (WD) | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 325 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 326 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" (WD) | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 327 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 8" Divan- 3.5FT (WD) | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 328 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" (WD) | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 329 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-10 Wed |  | 330 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" (WD) | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-10 Wed |  | 331 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-10 Wed |  | 332 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 333 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" (WD) | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 334 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (WC) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-06-01 |  |  |  |  | WAITING
2026-06-10 Wed |  | 335 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-06-01 |  |  |  |  | WAITING
2026-06-10 Wed |  | 336 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Right Arm (WC) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-06-01 |  |  |  |  | WAITING
2026-06-10 Wed |  | 337 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (WC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 338 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Back Cushion 24 (WC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 339 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 340 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 341 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 342 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 343 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Left Arm (WC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 344 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (WC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 345 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Back Cushion 24 (WC) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 346 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (WC) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 347 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Back Cushion 24 (WC) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 348 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Left Arm (WC) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 349 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (WC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 350 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Back Cushion 28 (WC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 351 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Left Arm (WC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 352 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (WC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 353 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Back Cushion 28 (WC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 354 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Right Arm (WC) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 355 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 356 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Back Cushion 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 357 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Left Arm (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed | 2026-05-15 | 358 | SO-2605-103-03 | PO-008770 | ZNT5112 | Houzs Century | KL | SO-2605-103 | 5536-1A(RHF) | 5536 -Right Arm (WC) |  | BO315-32 | 0 | 0 | 1 | 1 |  |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 359 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 360 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Back Cushion 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 361 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Right Arm (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 362 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S -Base 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 363 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Back Cushion 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 364 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Left Arm (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 365 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Right Arm (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 366 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR -Base 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 367 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536 -Back Cushion 30 (WC) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 368 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 369 | SO-2605-259-01 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | DIVAN-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-13 | 14 | 8 | 4 | 1 | Divan Top(W) | Divan Only specified; product matched to DIVAN-(K) | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 370 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 371 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 372 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 373 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | 8" Divan- 3FT (WD) | 3FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 374 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-11 Thu |  | 375 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-11 Thu |  | 376 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 377 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" (WD) | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 378 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-11 Thu |  | 379 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" (WD) | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-11 Thu |  | 380 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 8" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-11 Thu |  | 381 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" (WD) | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-11 Thu |  | 382 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 383 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" (WD) | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 384 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 385 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 386 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Left Arm (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 387 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 388 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 389 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Right Arm (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 390 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL (WC) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 391 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (WC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 392 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Back Cushion 28 (WC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 393 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Left Arm (WC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 394 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (WC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 395 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Back Cushion 28 (WC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 396 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Right Arm (WC) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-09 |  |  |  |  | WAITING
2026-06-11 Thu |  | 397 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (WC) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 398 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 (WC) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 399 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (WC) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 400 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 401 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 402 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 403 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 404 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 405 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 406 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 407 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 408 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (WC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 409 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Back Cushion 32 (WC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 410 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Right Arm (WC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 411 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535-1NA -Base 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 412 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535 -Back Cushion 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 413 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535-1S -Base 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 414 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Back Cushion 30 (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 415 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Left Arm (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 416 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Right Arm (WC) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 417 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (WC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 418 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Back Cushion 32 (WC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 419 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Left Arm (WC) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-14 |  |  |  |  | WAITING
2026-06-11 Thu |  | 420 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (WC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-11 Thu |  | 421 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Back Cushion 32 (WC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-11 Thu |  | 422 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Right Arm (WC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-11 Thu |  | 423 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (WC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-11 Thu |  | 424 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Back Cushion 32 (WC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-11 Thu |  | 425 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Left Arm (WC) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 426 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 10" Divan- 6FT (WD) | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 427 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" (WD) | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 428 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-12 Fri |  | 429 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" (WD) | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-12 Fri |  | 430 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 8" Divan- 6FT (WD) | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-23 |  |  |  |  | WAITING
2026-06-12 Fri |  | 431 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" (WD) | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-23 |  |  |  |  | WAITING
2026-06-12 Fri |  | 432 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 12" Divan- 6FT (WD) | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  | 2026-07-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 433 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" (WD) | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  | 2026-07-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 434 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 10" Divan- 5FT (WD) | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-12 Fri |  | 435 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" (WD) | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-12 Fri |  | 436 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (WC) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 437 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 438 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Left Arm (WC) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 439 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (WC) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 440 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Back Cushion 28 (WC) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 441 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Left Arm (WC) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 442 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 443 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 444 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Right Arm (WC) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 445 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 446 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Left Arm (WC) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 447 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (WC) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 448 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (WC) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 449 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Back Cushion 28 (WC) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 450 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Right Arm (WC) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 451 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (WC) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 452 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Back Cushion 28 (WC) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 453 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Right Arm (WC) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-12 Fri |  | 454 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (WC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-12 Fri |  | 455 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Back Cushion 24 (WC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-12 Fri |  | 456 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Right Arm (WC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-12 Fri |  | 457 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S -Base 28 (WC) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-12 Fri |  | 458 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Back Cushion 28 (WC) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-12 Fri |  | 459 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Left Arm (WC) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-12 Fri |  | 460 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Right Arm (WC) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-12 Fri |  | 461 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (WC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-12 Fri |  | 462 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Back Cushion 24 (WC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-12 Fri |  | 463 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Left Arm (WC) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-12 Fri |  | 464 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Back Cushion 30 (WC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 465 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (WC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 466 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Left Arm (WC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 467 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 468 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Back Cushion 30 (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 469 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Right Arm (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 470 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (WC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 471 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Back Cushion 30 (WC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 472 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Right Arm (WC) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 473 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 474 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Back Cushion 30 (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 475 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Left Arm (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 476 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR -Base 30 (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-12 Fri |  | 477 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536 -Back Cushion 30 (WC) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-13 Sat |  | 478 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Left Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 479 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 480 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 481 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Right Arm (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 482 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530-L(RHF) -Base 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 483 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Back Cushion 30 (WC) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING

## 4-Foam
粘棉 Foam — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Foaming DD | PIC 1 | PIC 2 | Completed Date | Overdue | Status
2026-06-02 Tue |  | 1 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 1003(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 2 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" PC151-01 Foam | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 3 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 1005-(Q) -HB 21" PC151-01 Foam | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 4 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 1005-(Q) -HB 25" PC151-04 Foam | 5FT | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 5 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" PC151-03 Foam | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-02 Tue |  | 6 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 7 | SO-2605-167-01 | KENSHO 21-01 |  | The Conts | KL | SO-2605-167 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 8 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 9 | SO-2605-205-01 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 1007-(S) -HB 22" PC151-01 Foam | 3FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 10 | SO-2605-205-02 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 1007-(S) -HB 22" PC151-01 Foam | 3FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 11 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 12 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 13 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 14 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 1013-(SS) -HB 20" PC151-13 Foam | 3.5FT | PC151-13 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 15 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-02 Tue |  | 16 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 17 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 18 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" PC151-18 Foam | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 19 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 20 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" PC151-01 Foam | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 21 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" PC151-01 Foam | 6FT | PC151-01 | 16 | 8 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 22 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-02 Tue |  | 23 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-14 Foam | 6FT | PC151-14 | 14 | 10 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 24 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-02 Foam | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 25 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-01 Foam | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 26 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-02 Tue |  | 27 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-02 Tue |  | 28 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" PC151-14 Foam | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  | 2026-07-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 29 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-02 Tue |  | 30 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 2008(A)-(K) -HB 23" PC151-04 Foam | 6FT | PC151-04 | 12 | 10 | 1 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 31 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 2009(A)-(K) -HB 23" PC151-01 Foam | 6FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 32 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" KS-18 Foam | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 33 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" PC151-12 Foam | 6FT | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  | 2026-05-28 | KYAW ZIN OO |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 34 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 35 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" PC151-10 Foam | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 36 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" PC151-11 Foam | 3.5FT | PC151-11 | 10 | 8 | 1 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 37 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" PC151-11 Foam | 5FT | PC151-11 | 14 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 38 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" PC151-01 Foam | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 39 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530-1A(LHF) -Base 30 (Foam) | 30 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 40 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | 30 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 41 | SO-2605-050-02 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(RHF) | 5530 -Right Arm (Foam) | 30 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 42 | SO-2604-265-02 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | 28 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-15 | 43 | SO-2604-265-02 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | 28 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-15 | 44 | SO-2604-265-01 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-L(LHF) | 5530 -Left Arm (Foam) | 28 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 45 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530-2A(LHF) -Base (Foam) |  | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 46 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Back Cushion BO315-21 Foam |  | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 47 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Left Arm (Foam) |  | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 48 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530-L(RHF) -Base (Foam) |  | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 49 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Back Cushion BO315-21 Foam |  | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 50 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Right Arm (Foam) |  | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 51 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Back Cushion 24 M2402-13 Foam | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 52 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Left Arm (Foam) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 53 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 (Foam) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 54 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 55 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Back Cushion 28 NINJA 08 Foam | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 56 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-29 | 57 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-29 | 58 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-29 | 59 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-2 Foam | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 60 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Right Arm (Foam) | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 61 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S -Base 28 (Foam) | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 62 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Left Arm (Foam) | 28 | M2402-4 |  |  | 6 | 1 |  |  | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 63 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 64 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Back Cushion 28 NINJA 08 Foam | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 65 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 28 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 66 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (Foam) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 67 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Back Cushion 24 M2402-13 Foam | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 68 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Right Arm (Foam) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-29 | 69 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-29 | 70 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu | 2026-05-29 | 71 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-2 Foam | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 72 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (Foam) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 73 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Back Cushion 32 BO315-1 Foam | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 74 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Left Arm (Foam) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 75 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA -Base 32 (Foam) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 76 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535 -Back Cushion 32 BO315-1 Foam | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 77 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (Foam) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 78 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Back Cushion 30 CH141-14 Foam | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 79 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Left Arm (Foam) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 80 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (Foam) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 81 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Back Cushion 32 BO315-1 Foam | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 82 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Right Arm (Foam) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-05-22 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 83 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (Foam) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 84 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Back Cushion 30 CH141-14 Foam | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 85 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Right Arm (Foam) | 30 | CH141-14 |  |  | 1 | 1 |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 86 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Right Arm (Foam) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 87 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Left Arm (Foam) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 88 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Back Cushion 30 BO315-23 Foam | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 89 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536-2S -Base 30 (Foam) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 90 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (Foam) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 91 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Back Cushion 28 BO315-22 Foam | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 92 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Right Arm (Foam) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 93 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (Foam) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 94 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Back Cushion 28 BO315-22 Foam | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 95 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Left Arm (Foam) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  | 2026-05-20 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 96 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF) -Base (Foam) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 97 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Back Cushion BO315-31 Foam |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 98 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Left Arm (Foam) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 99 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Left Arm (Foam) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 100 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Back Cushion 32 AM275-1 Foam | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 101 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (Foam) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 102 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540-1A(RHF) -Base (Foam) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 103 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Back Cushion BO315-31 Foam |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 104 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Right Arm (Foam) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 105 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (Foam) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 106 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Back Cushion 32 AM275-1 Foam | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 107 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Right Arm (Foam) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 108 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540 -Back Cushion 32 AM275-1 Foam | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 109 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA -Base 32 (Foam) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 110 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (Foam) | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 111 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Back Cushion 26 BO315-23 Foam | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 112 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Right Arm (Foam) | 26 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 113 | SO-2605-108-01 | PO-008779 | ZNT6067 | Houzs Century | KL | SO-2605-108 | 5540-2S | 5540-2S -Base (Foam) |  | BO315-21 | 0 | 0 | 6 | 1 | Nylon Fabric | Two seater make it 1 piece | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 114 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (Foam) |  | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 115 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (Foam) |  | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 116 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (Foam) | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 117 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Back Cushion 32 BO315-23 Foam | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 118 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Left Arm (Foam) | 32 | BO315-23 |  |  | 6 | 1 |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 119 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 120 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 121 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 122 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 123 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 124 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 125 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 126 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 127 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 128 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 129 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 130 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 131 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 132 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 133 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 134 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 135 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 136 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 137 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 138 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 139 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 140 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 141 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 142 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 143 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 144 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 145 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 146 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" PC151-02 Foam | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 147 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 1007-(K) -HB 23" PC151-13 Foam | 6FT | PC151-13 | 14 | 8 | 1 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 148 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 1007-(Q) -HB 20" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 149 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" PC151-08 Foam | 5FT | PC151-08 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 150 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" PC151-09 Foam | 5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 151 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 1007-(Q) -HB 22" PC151-17 Foam | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 152 | SO-2605-207-01 | PO-008884 | HC10876 | Houzs Century | PG | SO-2605-207 | 1007-(Q) | 1007-(Q) -HB 24" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 153 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 1007-(Q) -HB 20" PC151-17 Foam | 5FT | PC151-17 | 10 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 154 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 155 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" PC151-17 Foam | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 156 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" PC151-17 Foam | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 157 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 158 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 159 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 160 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 161 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 162 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 163 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 164 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 165 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 166 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 167 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 168 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 169 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112-2S -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 170 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 171 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 172 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 173 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" PC151-01 Foam | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 174 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 175 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 1007-(Q) -HB 21" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 176 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 1007-(S) -HB 22" PC151-01 Foam | 3FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 177 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 1013-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 178 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" PC151-12 Foam | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 179 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 Foam | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 180 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 Foam | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 181 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 1013-(Q) -HB 20" PC151-03 Foam | 5FT | PC151-03 | 12 | 8 |  | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 182 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 1013-(Q) -HB 22" PC151-14 Foam | 5FT | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 183 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 1013-(Q) -HB 22" PC151-03 Foam | 5FT | PC151-03 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 184 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" KS-14 Foam | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 185 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 1013-(Q) -HB 20" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 186 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 1013-(Q) -HB 20" PC151-17 Foam | 5FT | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 187 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" PC151-04 Foam | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 188 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" PC151-02 Foam | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 189 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" PC151-09 Foam | 3FT | PC151-09 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 190 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" PC151-08 Foam | 3FT | PC151-08 | 12 | 8 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 191 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 1013-(S) -HB 20" PC151-02 Foam | 3FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 192 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" PC151-10 Foam | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 193 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 1013-(SS) -HB 22" PC151-18 Foam | 3.5FT | PC151-18 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 194 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 1013-(SS) -HB 20" PC151-17 Foam | 3.5FT | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 195 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" PC151-02 Foam | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 196 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" PC151-09 Foam | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 197 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" PC151-11 Foam | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 198 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 199 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-12 Foam | 6FT | PC151-12 | 12 | 8 | 1 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 200 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-10 Foam | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 201 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-13 Foam | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 202 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-13 Foam | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 203 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-13 Foam | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 204 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 2008(A)-(K) -HB 26" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 205 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 206 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-13 Foam | 6FT | PC151-13 | 12 | 8 | 4 | 1 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 207 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-01 Foam | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 208 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" PC151-04 Foam | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 209 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-02 Foam | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 210 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" PC151-06 Foam | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 211 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 2009(A)-(K) -HB 21" PC151-01 Foam | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 212 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 213 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" PC151-15 Foam | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 214 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 2038(A)-(K) -HB 20" PC151-01 Foam | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 215 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" PC151-13 Foam | 5FT | PC151-13 | 14 | 8 | 4 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 216 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" PC151-01 Foam | 5FT | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-28 | KYAW ZIN OO |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 217 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 218 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 219 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 Foam | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 220 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 Foam | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 221 | SO-2605-051-01 | PO-008654 | ZNT6705 | Houzs Century | PG | SO-2605-051 | 5530-1A(LHF) | 5530-1A(LHF) -Base 24 (Foam) | 24 | CH141-11 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 222 | SO-2605-051-03 | PO-008654 | ZNT6705 | Houzs Century | PG | SO-2605-051 | 5530-1A(RHF) | 5530-1A(RHF) -Base 24 (Foam) | 24 | CH141-11 |  |  | 6 | 1 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 223 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 224 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Back Cushion 28 CH141-12 Foam | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 225 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 226 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Foam) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 227 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Back Cushion 28 CH141-12 Foam | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 228 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Left Arm (Foam) | 28 | CH141-12 |  |  | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 229 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 230 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 231 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-25 Foam | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 232 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL (Foam) | 24 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 233 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL (Foam) | 24 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 234 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Foam) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 235 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-25 Foam | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 236 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 237 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Foam) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 238 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-1 Foam | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 239 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 240 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 (Foam) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 241 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Back Cushion 28 BO315-1 Foam | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 242 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 243 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530-1NA -Base 28 (Foam) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 244 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530 -Back Cushion 28 BO315-1 Foam | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 245 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 246 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-22 Foam | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 247 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 248 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530-2NA -Base 28 (Foam) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 249 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530 -Back Cushion 28 BO315-25 Foam | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 250 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Foam) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 251 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-22 Foam | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 252 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Left Arm (Foam) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 253 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Left Arm (Foam) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 254 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-4 Foam | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 255 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Foam) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 256 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 257 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-4 Foam | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 258 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 259 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-18 Foam | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 260 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Left Arm (Foam) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 261 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Foam) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri | 2026-05-29 | 262 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Left Arm (Foam) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri | 2026-05-29 | 263 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Foam) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri | 2026-05-29 | 264 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Back Cushion 28 NINJA 02 Foam | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 265 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 266 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-18 Foam | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 267 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 268 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 269 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA Foam | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 270 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 271 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 272 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-2 Foam | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 273 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 274 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 275 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA Foam | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 276 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 277 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 278 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-2 Foam | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 279 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri | 2026-05-29 | 280 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Back Cushion 28 NINJA 02 Foam | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri | 2026-05-29 | 281 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Right Arm (Foam) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri | 2026-05-29 | 282 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Foam) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 283 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 284 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 285 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 286 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Back Cushion 30 FABRIC HR805-10 Foam | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 287 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Right Arm (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 288 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" PC151-02 Foam | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 289 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 290 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 291 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 292 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 293 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 294 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" PC151-14 Foam | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 295 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 296 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" PC151-01 Foam | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 297 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-13 Sat |  | 298 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 Foam | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 299 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 Foam | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 300 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" PC151-17 Foam | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 301 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" PC151-14 Foam | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 302 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" PC151-13 Foam | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 303 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 304 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" PC151-17 Foam | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 305 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" PC151-01 Foam | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 306 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" PC151-17 Foam | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 307 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" PC151-06 Foam | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 308 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 Foam | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 309 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 310 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 311 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 Foam | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 312 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 313 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 314 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" PC151-17 Foam | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 315 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 316 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" PC151-02 Foam | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 317 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 318 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Back Cushion 30 FABRIC HR805-10 Foam | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 319 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Left Arm (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 320 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA -Base 30 (Foam) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 321 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540 -Back Cushion 30 FABRIC HR805-10 Foam | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 322 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 323 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" PC151-17 Foam | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-15 Mon |  | 324 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 325 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 326 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 327 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 Foam | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 328 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-12 Foam | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 329 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-01 Foam | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-15 Mon |  | 330 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-01 Foam | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 331 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" PC151-01 Foam | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-15 Mon |  | 332 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" PC151-01 Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 333 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" PC151-01 Foam | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 334 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" PC151-02 Foam | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 335 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" PC151-02 Foam | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 336 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-02 Foam | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 337 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-15 Mon |  | 338 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" PC151-03 Foam | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 339 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 340 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-2 Foam | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 341 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 342 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Foam) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 343 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON Foam | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 344 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 345 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON Foam | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 346 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Foam) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 347 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 348 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-16 Tue |  | 349 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 1013-(Q) -HB 24" PC151-13 Foam | 5FT | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 350 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 351 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-1 Foam | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 352 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 353 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Foam) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 354 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Back Cushion 24 KN390-1 Foam | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 355 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 356 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (Foam) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 357 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Back Cushion 28 PC151-01 Foam | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 358 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Left Arm (Foam) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 359 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (Foam) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 360 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Back Cushion 28 PC151-01 Foam | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 361 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Right Arm (Foam) | 28 | PC151-01 |  |  |  | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 362 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 363 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 364 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Left Arm (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 365 | SO-2605-103-03 | PO-008770 | ZNT5112 | Houzs Century | KL | SO-2605-103 | 5536-1A(RHF) | 5536 -Right Arm (Foam) |  | BO315-32 | 0 | 0 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 366 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 367 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 368 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Right Arm (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 369 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S -Base 30 (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 370 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 371 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Left Arm (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 372 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Right Arm (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 373 | SO-2605-103-02 | PO-008770 | ZNT5112 | Houzs Century | KL | SO-2605-103 | 5536-CNR | 5536-CNR -Base (Foam) |  | BO315-32 | 0 | 0 | 1 | 1 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 374 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR -Base 30 (Foam) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-16 Tue |  | 375 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-17 Wed |  | 376 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" PC151-01 Foam | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-17 Wed |  | 377 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" PC151-10 Foam | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 378 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Foam) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 379 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-21 Foam | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 380 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 381 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 382 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-21 Foam | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 383 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 384 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL (Foam) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 385 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Foam) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-11 |  |  |  |  | WAITING
2026-06-17 Wed |  | 386 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Back Cushion 28 M2402-1 Foam | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-11 |  |  |  |  | WAITING
2026-06-17 Wed |  | 387 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Left Arm (Foam) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. | 2026-06-11 |  |  |  |  | WAITING
2026-06-17 Wed |  | 388 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Foam) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-11 |  |  |  |  | WAITING
2026-06-17 Wed |  | 389 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Back Cushion 28 M2402-1 Foam | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-11 |  |  |  |  | WAITING
2026-06-17 Wed |  | 390 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Right Arm (Foam) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. | 2026-06-11 |  |  |  |  | WAITING
2026-06-17 Wed |  | 391 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (Foam) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-16 |  |  |  |  | WAITING
2026-06-17 Wed |  | 392 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Back Cushion 32 KN390-3 Foam | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-16 |  |  |  |  | WAITING
2026-06-17 Wed |  | 393 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Right Arm (Foam) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-16 |  |  |  |  | WAITING
2026-06-17 Wed |  | 394 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (Foam) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 395 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Back Cushion 32 BO315-24 Foam | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 396 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Right Arm (Foam) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 397 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (Foam) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 398 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Back Cushion 32 BO315-24 Foam | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 399 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Left Arm (Foam) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-18 Thu |  | 400 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" PC151-01 Foam | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-18 Thu |  | 401 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" PC151-02 Foam | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-18 Thu |  | 402 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" PC151-15 Foam | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm | 2026-06-24 |  |  |  |  | WAITING
2026-06-18 Thu |  | 403 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" PC151-02 Foam | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-18 Thu |  | 404 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-18 Thu |  | 405 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-3 Foam | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-18 Thu |  | 406 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-18 Thu |  | 407 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (Foam) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 408 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 M2402-4 Foam | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 409 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (Foam) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 410 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 M2402-4 Foam | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 411 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 412 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 413 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 M2402-4 Foam | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 414 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 415 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 M2402-4 Foam | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 416 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 417 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535-1NA -Base 30 (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 418 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535 -Back Cushion 30 M2402-4 Foam | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 419 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535-1S -Base 30 (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 420 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Back Cushion 30 M2402-4 Foam | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 421 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Left Arm (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 422 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Right Arm (Foam) | 30 | M2402-4 |  |  | 1 | 1 |  |  | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 423 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (Foam) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 424 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Back Cushion 32 KN390-3 Foam | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 425 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Left Arm (Foam) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" | 2026-06-16 |  |  |  |  | WAITING
2026-06-18 Thu |  | 426 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Foam) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-10 |  |  |  |  | WAITING
2026-06-18 Thu |  | 427 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Back Cushion 30 NINJA 02 Foam | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-10 |  |  |  |  | WAITING
2026-06-18 Thu |  | 428 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Left Arm (Foam) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. | 2026-06-10 |  |  |  |  | WAITING
2026-06-18 Thu |  | 429 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Foam) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-10 |  |  |  |  | WAITING
2026-06-18 Thu |  | 430 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Back Cushion 30 NINJA 02 Foam | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-10 |  |  |  |  | WAITING
2026-06-18 Thu |  | 431 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Right Arm (Foam) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. | 2026-06-10 |  |  |  |  | WAITING
2026-06-19 Fri |  | 432 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Foam) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 433 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Back Cushion 28 BO315-3 Foam | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 434 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Left Arm (Foam) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 435 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Foam) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 436 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Back Cushion 28 M2402-4 Foam | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 437 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Left Arm (Foam) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 438 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Foam) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 439 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-3 Foam | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 440 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Left Arm (Foam) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 441 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 442 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-3 Foam | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 443 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Right Arm (Foam) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 444 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 445 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Back Cushion 28 M2402-4 Foam | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 446 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Right Arm (Foam) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 447 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Foam) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 448 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Back Cushion 24 NINJA 02 Foam | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 449 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 450 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S -Base 28 (Foam) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-23 |  |  |  |  | WAITING
2026-06-19 Fri |  | 451 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Back Cushion 28 M2402-13 Foam | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-23 |  |  |  |  | WAITING
2026-06-19 Fri |  | 452 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Left Arm (Foam) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-23 |  |  |  |  | WAITING
2026-06-19 Fri |  | 453 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Right Arm (Foam) | 28 | M2402-13 |  |  |  | 1 |  |  | 2026-06-23 |  |  |  |  | WAITING
2026-06-19 Fri |  | 454 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Foam) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 455 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Back Cushion 24 NINJA 02 Foam | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 456 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Left Arm (Foam) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 457 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Left Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 458 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 459 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 460 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Back Cushion 30 PC151-01 Foam | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 461 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Right Arm (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 462 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530-L(RHF) -Base 30 (Foam) | 30 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 463 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Foam) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 464 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Back Cushion 30 BO315-5 Foam | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 465 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Right Arm (Foam) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 466 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (Foam) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 467 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Back Cushion 30 BO315-5 Foam | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 468 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Left Arm (Foam) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 469 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR -Base 30 (Foam) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 470 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536 -Back Cushion 30 BO315-5 Foam | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  | 2026-06-18 |  |  |  |  | WAITING

## 5-Frame
组框 Framing — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Quantity | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Wood Cutting CD | Framing DD | PIC 1 | PIC 2 | Completed Date | Overdue | Status
2026-06-02 Tue |  | 1 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 2 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" Frame | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 3 | SO-2605-124-01 | PO-008799 | HC9650 | Houzs Century | SRW | SO-2605-124 | 1005-(Q) | 1005-(Q) -HB 24" Frame | 5FT | 1 | PC151-02 | 12 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 4 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 5 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 1005-(Q) -HB 21" Frame | 5FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 6 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 7 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 8 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 9 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 10 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 11 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 12 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 13 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" Frame | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 14 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" Frame | 6FT | 1 | PC151-01 | 16 | 8 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 15 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 16 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 2009(A)-(K) -HB 23" Frame | 6FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 17 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 18 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" Frame | 6FT | 1 | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 19 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 20 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 21 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-10 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 22 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" Frame | 5FT | 1 | PC151-10 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 23 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-11 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 24 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" Frame | 3.5FT | 1 | PC151-11 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 25 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-11 | 14 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 26 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" Frame | 5FT | 1 | PC151-11 | 14 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 27 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-13 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 28 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530-2A(LHF) -Base (Frame) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-23 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 29 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Left Arm (Frame) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-23 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 30 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Back Cushion (Frame) |  | 2 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-23 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 31 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530-L(RHF) -Base (Frame) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-23 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 32 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Right Arm (Frame) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-23 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 33 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Back Cushion (Frame) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-23 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 34 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 (Frame) | 24 | 1 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 35 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Back Cushion 24 (Frame) | 24 | 2 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 36 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Left Arm (Frame) | 24 | 1 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 37 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 38 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 39 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 40 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S -Base 28 (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 |  |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 41 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Left Arm (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 |  |  |  | 2026-05-14 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 42 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Frame) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 43 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 44 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 45 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Right Arm (Frame) | 24 | 1 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 46 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (Frame) | 24 | 1 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 47 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 48 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Back Cushion 32 (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 49 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Left Arm (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 50 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA -Base 32 (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 51 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535 -Back Cushion 32 (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 52 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (Frame) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 53 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Back Cushion 30 (Frame) | 30 | 2 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 54 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Left Arm (Frame) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 55 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 56 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Back Cushion 32 (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 57 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Right Arm (Frame) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 58 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (Frame) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 59 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Back Cushion 30 (Frame) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 60 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Right Arm (Frame) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 61 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Left Arm (Frame) | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 62 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Right Arm (Frame) | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 63 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Back Cushion 30 (Frame) | 30 | 2 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 64 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536-2S -Base 30 (Frame) | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 65 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF) -Base (Frame) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 66 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Back Cushion (Frame) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 67 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Left Arm (Frame) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 68 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Left Arm (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 69 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 70 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Back Cushion 32 (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 71 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (Frame) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 72 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Back Cushion 28 (Frame) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 73 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Right Arm (Frame) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 74 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540-1A(RHF) -Base (Frame) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 75 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Back Cushion (Frame) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 76 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Right Arm (Frame) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 77 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 78 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Back Cushion 32 (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 79 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Right Arm (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 80 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA -Base 32 (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 81 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540 -Back Cushion 32 (Frame) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 82 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (Frame) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 83 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Back Cushion 28 (Frame) | 28 | 2 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 84 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Left Arm (Frame) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 85 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (Frame) | 26 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 86 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Back Cushion 26 (Frame) | 26 | 2 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 87 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Right Arm (Frame) | 26 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 88 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (Frame) |  | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 89 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (Frame) |  | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 90 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (Frame) | 32 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 91 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Back Cushion 32 (Frame) | 32 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed | 2026-05-09 | 92 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Left Arm (Frame) | 32 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 93 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 94 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 95 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 96 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 97 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 98 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 99 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 100 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-04 Thu |  | 101 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 102 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 103 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 104 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Frame | 5FT | 1 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 105 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 106 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Frame | 5FT | 1 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 107 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 4" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 4 | 6 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 108 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 12 | 4 | 6 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 109 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 110 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" Frame | 6FT | 1 | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 111 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 112 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 113 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-17 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 114 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 115 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 116 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 117 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 118 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 119 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 120 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 121 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 122 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 123 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 124 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 125 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 126 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 127 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 128 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 129 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 130 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 131 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 132 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 133 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 134 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 135 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 136 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 137 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 138 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 139 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 140 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 141 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 142 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 143 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 144 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 145 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 146 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 147 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 148 | SO-2605-131-04 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | DIVAN-(K) | 4" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 0 | 4 | 7 | 1 |  | STEEL LEG | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 149 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 150 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" Frame | 6FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 151 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 152 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 1007-(K) -HB 23" Frame | 6FT | 1 | PC151-13 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 153 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-08 | 10 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 154 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" Frame | 5FT | 1 | PC151-08 | 10 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 155 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 156 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 157 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 158 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 159 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 1007-(Q) -HB 21" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 160 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 161 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 162 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 163 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 164 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 165 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 1007-(S) -HB 22" Frame | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri | 2026-05-15 | 166 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-10 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 167 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-12 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 168 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" Frame | 6FT | 1 | PC151-12 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 169 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 170 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" Frame | 5FT | 1 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 171 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 172 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" Frame | 5FT | 1 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 173 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 174 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 175 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | KS-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 176 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" Frame | 5FT | 1 | KS-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 177 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 178 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 1013-(Q) -HB 20" Frame | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 179 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 180 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 1013-(Q) -HB 20" Frame | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 181 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 182 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" Frame | 5FT | 1 | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 183 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 184 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" Frame | 5FT | 1 | PC151-02 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 185 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-09 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 186 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" Frame | 3FT | 1 | PC151-09 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 187 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-08 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 188 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" Frame | 3FT | 1 | PC151-08 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 189 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 190 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 1013-(S) -HB 20" Frame | 3FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 191 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 8" Divan- 200CMX200CM Frame | 200CMX200CM | 2 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 192 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" Frame | 200CMX200CM | 1 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 193 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 1013-(SS) -HB 22" Frame | 3.5FT | 1 | PC151-18 | 12 | 8 | 2 | 1 |  |  | 2026-05-11 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 194 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 195 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 1013-(SS) -HB 20" Frame | 3.5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 196 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-02 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 197 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" Frame | 3.5FT | 1 | PC151-02 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 198 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 199 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" Frame | 3.5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 200 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-11 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 201 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" Frame | 3.5FT | 1 | PC151-11 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 202 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 203 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 204 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-18 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 205 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" Frame | 5FT | 1 | PC151-18 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 206 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 207 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 208 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 209 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 210 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-14 | 14 | 10 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 211 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-14 | 14 | 10 |  | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 212 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 213 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 214 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 12 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 215 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-13 | 12 | 8 | 4 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 216 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-12 | 12 | 8 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 217 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Frame | 6FT | 1 | PC151-12 | 12 | 8 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 218 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-10 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 219 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-10 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 220 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 221 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 222 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 223 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 224 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 225 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 226 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 227 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Frame | 6FT | 1 | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 228 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 229 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Frame | 6FT | 1 | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 230 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 231 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 232 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 233 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Frame | 6FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 234 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 235 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 236 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-06 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 237 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-06 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 238 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 239 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 2009(A)-(K) -HB 21" Frame | 6FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 240 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 241 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-29 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 242 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-15 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 243 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" Frame | 5FT | 1 | PC151-15 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 244 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 2038(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-26 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 245 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 246 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 247 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 248 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 249 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 250 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Frame | 5FT | 1 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 251 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 252 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Frame | 5FT | 1 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 253 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 254 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 2 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 255 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 256 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530 -Back Cushion 28 (Frame) | 28 | 2 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 257 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530-2NA -Base 28 (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 258 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Frame) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 259 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 260 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 261 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 262 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 263 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 264 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL (Frame) | 24 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  | 2026-05-28 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 265 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL (Frame) | 24 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  | 2026-05-28 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 266 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 267 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 268 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Frame) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 269 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-13 | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 270 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-13 | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 271 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-13 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 272 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-13 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 273 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-13 | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 274 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-13 | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 275 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530-1NA -Base 28 (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 276 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 277 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 278 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 2 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 279 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 280 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 281 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 282 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Frame) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 283 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 284 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Frame) | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 285 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 286 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 287 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 288 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 289 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Frame) | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 290 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 291 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 292 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | 28 | 1 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 293 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 294 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 295 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 296 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 297 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 298 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 299 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 300 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 301 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 302 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 303 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 304 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Frame) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 305 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 306 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 307 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Frame) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 308 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 309 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 310 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 311 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 312 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Frame) | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 313 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 314 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Back Cushion 30 (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 315 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Left Arm (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 316 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540 -Back Cushion 30 (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 317 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA -Base 30 (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 318 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 319 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 320 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 321 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Right Arm (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 322 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Back Cushion 30 (Frame) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 323 | SO-2605-300-01 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | DIVAN-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 324 | SO-2605-296-01 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 325 | SO-2605-296-02 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 326 | SO-2605-296-03 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 327 | SO-2605-283-01 | PO-008976 | HC10887 | Houzs Century | PG | SO-2605-283 | DIVAN-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-01 | 0 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 328 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 8" Divan- 200CMX200CM Frame | 200CMX200CM | 2 | PC151-02 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 329 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" Frame | 200CMX200CM | 1 | PC151-02 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 330 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-03 | 12 | 10 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 331 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" Frame | 5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 332 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-10 Wed |  | 333 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" Frame | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-10 Wed |  | 334 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 335 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 336 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 337 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 338 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 339 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 340 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 341 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" Frame | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 342 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 343 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" Frame | 5FT | 1 | PC151-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 344 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-10 Wed |  | 345 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-10 Wed |  | 346 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-10 Wed |  | 347 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" Frame | 5FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-10 Wed |  | 348 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-10 Wed |  | 349 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-10 Wed |  | 350 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 351 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" Frame | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 352 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 353 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" Frame | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 354 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 355 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" Frame | 6FT | 1 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 356 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 357 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" Frame | 6FT | 1 | PC151-13 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 358 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 359 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" Frame | 6FT | 1 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 360 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-17 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 361 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" Frame | 6FT | 1 | PC151-17 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 362 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 363 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" Frame | 6FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 364 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 365 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 366 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 367 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" Frame | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 368 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 369 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 370 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-15 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 371 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-15 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 372 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 373 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 374 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 375 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 376 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 377 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" Frame | 5FT | 1 | PC151-17 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 378 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 379 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-10 Wed |  | 380 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-02 | 8 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 381 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" Frame | 3FT | 1 | PC151-02 | 8 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 382 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 383 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" Frame | 6FT | 1 | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 384 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-06 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 385 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-06 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 386 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-15 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 387 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" Frame | 5FT | 1 | PC151-15 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 388 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 389 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-11 Thu |  | 390 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-17 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-11 Thu |  | 391 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" Frame | 5FT | 1 | PC151-17 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-11 Thu |  | 392 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-02 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 393 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-02 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 394 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-11 Thu |  | 395 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" Frame | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-11 Thu |  | 396 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-11 Thu |  | 397 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-11 Thu |  | 398 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 399 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 400 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-11 Thu |  | 401 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-11 Thu |  | 402 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 403 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 404 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 405 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 406 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 407 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | 6FT | 1 | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 408 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-11 Thu |  | 409 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Frame | 6FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-11 Thu |  | 410 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-11 Thu |  | 411 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" Frame | 6FT | 1 | PC151-01 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-12 Fri |  | 412 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-12 Fri |  | 413 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-12 Fri |  | 414 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 415 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 416 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 8" Divan- 200CMX200CM Frame | 200CMX200CM | 2 | PC151-01 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-12 Fri |  | 417 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" Frame | 200CMX200CM | 1 | PC151-01 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-12 Fri |  | 418 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-02 | 14 | 10 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 419 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" Frame | 6FT | 1 | PC151-02 | 14 | 10 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 420 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-02 | 12 | 12 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 421 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" Frame | 3.5FT | 1 | PC151-02 | 12 | 12 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 422 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 423 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Frame | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 424 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 425 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 426 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 8" Divan- 3.5FT Frame | 3.5FT | 1 | PC151-03 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 427 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" Frame | 3.5FT | 1 | PC151-03 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 428 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 429 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 430 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 431 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Frame) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 432 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 433 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Frame) | 24 | 2 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 434 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | 28 | 1 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 435 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 436 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 437 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Frame) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 438 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Back Cushion 24 (Frame) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 439 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Left Arm (Frame) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-12 Fri |  | 440 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Frame) | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 441 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Back Cushion 24 (Frame) | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 442 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Left Arm (Frame) | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 443 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (Frame) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 444 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Back Cushion 28 (Frame) | 28 | 2 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 445 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Left Arm (Frame) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 446 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (Frame) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 447 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Back Cushion 28 (Frame) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 448 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Right Arm (Frame) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 449 | SO-2605-103-03 | PO-008770 | ZNT5112 | Houzs Century | KL | SO-2605-103 | 5536-1A(RHF) | 5536 -Right Arm (Frame) |  | 1 | BO315-32 | 0 | 0 | 1 | 1 |  |  | 2026-05-21 | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 450 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 451 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Back Cushion 30 (Frame) | 30 | 2 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 452 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Right Arm (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 453 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S -Base 30 (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 454 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Back Cushion 30 (Frame) | 30 | 2 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 455 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Left Arm (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 456 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Right Arm (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 457 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR -Base 30 (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-12 Fri |  | 458 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536 -Back Cushion 30 (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 459 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-13 Sat |  | 460 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-13 Sat |  | 461 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-05-10 | 2026-06-13 |  |  |  |  | WAITING
2026-06-13 Sat |  | 462 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-13 Sat |  | 463 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" Frame | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-13 Sat |  | 464 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 12 | 10 |  | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 465 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 12 | 10 |  | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 466 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-13 Sat |  | 467 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Frame | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-13 Sat |  | 468 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-13 Sat |  | 469 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" Frame | 5FT | 1 | PC151-02 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-13 Sat |  | 470 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 471 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" Frame | 5FT | 1 | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 472 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Frame) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 473 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 474 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 475 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 476 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 2 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 477 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 478 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL (Frame) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-13 Sat |  | 479 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Frame) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 480 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Frame) | 28 | 2 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 481 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Left Arm (Frame) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 482 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Frame) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 483 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Back Cushion 28 (Frame) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 484 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Right Arm (Frame) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 485 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 486 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 487 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 488 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 489 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 490 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (Frame) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 491 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Back Cushion 32 (Frame) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 492 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Right Arm (Frame) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 493 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535-1S -Base 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 494 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Back Cushion 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 495 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Left Arm (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 496 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Right Arm (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 497 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (Frame) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 498 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Back Cushion 32 (Frame) | 32 | 2 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 499 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Left Arm (Frame) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-13 Sat |  | 500 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (Frame) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-13 Sat |  | 501 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Back Cushion 32 (Frame) | 32 | 2 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-13 Sat |  | 502 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Right Arm (Frame) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-13 Sat |  | 503 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (Frame) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-13 Sat |  | 504 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Back Cushion 32 (Frame) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-13 Sat |  | 505 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Left Arm (Frame) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-13 Sat |  | 506 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 507 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 508 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Left Arm (Frame) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 509 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 510 | SO-2605-259-01 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | DIVAN-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-13 | 14 | 8 | 4 | 1 | Divan Top(W) | Divan Only specified; product matched to DIVAN-(K) |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 511 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 512 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 513 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | 8" Divan- 5FT Frame | 5FT | 2 | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 514 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | 8" Divan- 3FT Frame | 3FT | 1 | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 515 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 10" Divan- 6FT Frame | 6FT | 2 | PC151-01 | 14 | 10 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-15 Mon |  | 516 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" Frame | 6FT | 1 | PC151-01 | 14 | 10 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-15 Mon |  | 517 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-15 Mon |  | 518 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" Frame | 5FT | 1 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-15 Mon |  | 519 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 8" Divan- 6FT Frame | 6FT | 2 | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-24 |  |  |  |  | WAITING
2026-06-15 Mon |  | 520 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" Frame | 6FT | 1 | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-24 |  |  |  |  | WAITING
2026-06-15 Mon |  | 521 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 10" Divan- 5FT Frame | 5FT | 2 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-15 Mon |  | 522 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" Frame | 5FT | 1 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-15 Mon |  | 523 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Frame) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 524 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 2 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 525 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 526 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Frame) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-15 Mon |  | 527 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 2 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-15 Mon |  | 528 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-15 Mon |  | 529 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 530 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 2 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 531 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 532 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Frame) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 533 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 534 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Left Arm (Frame) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 535 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 536 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 537 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 538 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-15 Mon |  | 539 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-15 Mon |  | 540 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Right Arm (Frame) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-15 Mon |  | 541 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Frame) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-15 Mon |  | 542 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Frame) | 24 | 2 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-15 Mon |  | 543 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-15 Mon |  | 544 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S -Base 28 (Frame) | 28 | 1 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-15 Mon |  | 545 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Back Cushion 28 (Frame) | 28 | 2 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-15 Mon |  | 546 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Left Arm (Frame) | 28 | 1 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-15 Mon |  | 547 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Right Arm (Frame) | 28 | 1 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-15 Mon |  | 548 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Frame) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-15 Mon |  | 549 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Back Cushion 24 (Frame) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-15 Mon |  | 550 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Left Arm (Frame) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-15 Mon |  | 551 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (Frame) | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 552 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Frame) | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 553 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (Frame) | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 554 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 555 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 556 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 557 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535-1NA -Base 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 558 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535 -Back Cushion 30 (Frame) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-15 Mon |  | 559 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Frame) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 560 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Frame) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 561 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Left Arm (Frame) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 562 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 563 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 564 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Right Arm (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 565 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Frame) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 566 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Frame) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 567 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Right Arm (Frame) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-15 Mon |  | 568 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR -Base 30 (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-15 Mon |  | 569 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536 -Back Cushion 30 (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-16 Tue |  | 570 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 12" Divan- 6FT Frame | 6FT | 2 | PC151-14 | 14 | 12 |  | 1 |  |  |  | 2026-07-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 571 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" Frame | 6FT | 1 | PC151-14 | 14 | 12 |  | 1 |  |  |  | 2026-07-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 572 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Left Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 573 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 574 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Back Cushion 30 (Frame) | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 575 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530-L(RHF) -Base 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 576 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Right Arm (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 577 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Back Cushion 30 (Frame) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 578 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-16 Tue |  | 579 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Back Cushion 30 (Frame) | 30 | 2 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-16 Tue |  | 580 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Left Arm (Frame) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING

## 6-Web
打底 Webbing — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Framing CD | Webbing DD | PIC 1 | PIC 2 | Completed Date | Overdue | Status
2026-06-02 Tue |  | 1 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 2 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 1003(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 3 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 4 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" Webbing | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 5 | SO-2605-124-01 | PO-008799 | HC9650 | Houzs Century | SRW | SO-2605-124 | 1005-(Q) | 1005-(Q) -HB 24" Webbing | 5FT | PC151-02 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 6 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 7 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 1005-(Q) -HB 21" Webbing | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 8 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 9 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 1005-(Q) -HB 25" Webbing | 5FT | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 10 | SO-2605-234-02 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1005-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge Fo Curve Divan | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 11 | SO-2605-234-02 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1005-(Q) | 1005-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge Fo Curve Divan | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 12 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 13 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 14 | SO-2605-213-01 | PO-008892 | HC10938 | Houzs Century | SRW | SO-2605-213 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 15 | SO-2605-213-01 | PO-008892 | HC10938 | Houzs Century | SRW | SO-2605-213 | 1013-(K) | 1013-(K) -HB 22" Webbing | 6FT | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 16 | SO-2605-227-01 | PO-008904 | HC10505 | Houzs Century | KL | SO-2605-227 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 17 | SO-2605-227-01 | PO-008904 | HC10505 | Houzs Century | KL | SO-2605-227 | 1013-(K) | 1013-(K) -HB 22" Webbing | 6FT | PC151-03 | 14 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 18 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 19 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 20 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 21 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 22 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 23 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 24 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-13 | 12 | 8 |  | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 25 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 1013-(SS) -HB 20" Webbing | 3.5FT | PC151-13 | 12 | 8 |  | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 26 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 27 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" Webbing | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 28 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" Webbing | 6FT | PC151-01 | 16 | 8 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue | 2026-05-25 | 29 | SO-2605-102-01 | PO-008769 | HC14275 | Houzs Century | KL | SO-2605-102 | 2006(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-17 | 14 | 8 | 4 | 1 | Front Drawer |  | 2026-05-26 | 2026-05-28 |  | THAR TIN |  | OVERDUE | WAITING
2026-06-02 Tue |  | 30 | SO-2605-162-01 | PO-008845 | HC9041 | Houzs Century | KL | SO-2605-162 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-10 | 12 | 8 | 2 | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 31 | SO-2605-162-01 | PO-008845 | HC9041 | Houzs Century | KL | SO-2605-162 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | 6FT | PC151-10 | 12 | 8 | 2 | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 32 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-04 | 12 | 10 | 1 | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 33 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 2008(A)-(K) -HB 23" Webbing | 6FT | PC151-04 | 12 | 10 | 1 | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 34 | SO-2605-234-01 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-03 | 14 | 8 |  | 1 | Divan Curve | HB Straight to Wall/Edge do Curve Divan | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 35 | SO-2605-234-01 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | 6FT | PC151-03 | 14 | 8 |  | 1 | Divan Curve | HB Straight to Wall/Edge do Curve Divan | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 36 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 37 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 2009(A)-(K) -HB 23" Webbing | 6FT | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 38 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 8" Divan- 6FT Foam | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-02 Tue |  | 39 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" Webbing | 6FT | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 40 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 41 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" Webbing | 6FT | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 42 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 43 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" Webbing | 5FT | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 44 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 45 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" Webbing | 5FT | PC151-10 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 46 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-11 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 47 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" Webbing | 3.5FT | PC151-11 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 48 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-11 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 49 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" Webbing | 5FT | PC151-11 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 50 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-14 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 51 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530-1A(LHF) -Base 30 (Webbing) | 30 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-28 | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 52 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530-2A(LHF) -Base (Webbing) |  | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 53 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) |  | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 54 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Back Cushion (Webbing) |  | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 55 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Back Cushion (Webbing) |  | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 56 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Right Arm (Webbing) |  | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 57 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530-L(RHF) -Base (Webbing) |  | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 58 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 (Webbing) | 24 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 59 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Left Arm (Webbing) | 24 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 60 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Back Cushion 24 (Webbing) | 24 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 61 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 62 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 63 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 64 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 65 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 66 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 67 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Left Arm (Webbing) | 28 | M2402-4 |  |  | 6 | 1 |  |  |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 68 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S -Base 28 (Webbing) | 28 | M2402-4 |  |  | 6 | 1 |  |  |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 69 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | 28 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 70 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 71 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 28 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 72 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 73 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 74 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-29 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 75 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Right Arm (Webbing) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-13 | 2026-06-02 |  |  |  |  | WAITING
2026-06-03 Wed |  | 76 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (Webbing) | 24 | M2402-13 |  |  | 6 | 1 |  |  | 2026-05-13 | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 77 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 78 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Back Cushion 32 (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 79 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Left Arm (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 80 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA -Base 32 (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 81 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535 -Back Cushion 32 (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 82 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (Webbing) | 30 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 83 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Back Cushion 30 (Webbing) | 30 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 84 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Left Arm (Webbing) | 30 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 85 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 86 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Back Cushion 32 (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 87 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Right Arm (Webbing) | 32 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 88 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (Webbing) | 30 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 89 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Back Cushion 30 (Webbing) | 30 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 90 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Right Arm (Webbing) | 30 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 91 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Right Arm (Webbing) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 92 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Left Arm (Webbing) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 93 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Back Cushion 30 (Webbing) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 94 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536-2S -Base 30 (Webbing) | 30 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 95 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (Webbing) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 96 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Back Cushion 28 (Webbing) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 97 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Right Arm (Webbing) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 98 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 99 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Right Arm (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 100 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Back Cushion 32 (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-04 Thu |  | 101 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (Webbing) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 102 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Back Cushion 28 (Webbing) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 103 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Left Arm (Webbing) | 28 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-19 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 104 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (Webbing) | 26 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 105 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Back Cushion 26 (Webbing) | 26 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 106 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Right Arm (Webbing) | 26 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 107 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (Webbing) |  | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 108 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL (Webbing) |  | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 109 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (Webbing) | 32 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 110 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Back Cushion 32 (Webbing) | 32 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 111 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Left Arm (Webbing) | 32 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-13 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 112 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF) -Base (Webbing) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 113 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Back Cushion (Webbing) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 114 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Left Arm (Webbing) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 115 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 116 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Left Arm (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 117 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Back Cushion 32 (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 118 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540-1A(RHF) -Base (Webbing) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 119 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Back Cushion (Webbing) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 120 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Right Arm (Webbing) |  | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 121 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540 -Back Cushion 32 (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 122 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA -Base 32 (Webbing) | 32 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 123 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 124 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 125 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 126 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 127 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 128 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 129 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 130 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 131 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 132 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 133 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 134 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 135 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 136 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 137 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 138 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 139 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 140 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 141 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-05 Fri |  | 142 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 143 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 144 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 145 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 146 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Webbing | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 147 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 148 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Webbing | 5FT | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 149 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 4" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 150 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" Webbing | 5FT | PC151-01 | 12 | 4 | 6 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-06 Sat |  | 151 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 10" Divan- 6FT Foam | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 152 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" Webbing | 6FT | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 153 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 154 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 155 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-28 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 156 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-28 | 2026-05-28 | THAR TIN |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 157 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 158 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-17 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 159 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 160 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 161 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 162 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 163 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 164 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 165 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 166 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 167 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 168 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 169 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 170 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 171 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 172 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 173 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 174 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 175 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 176 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 177 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112-2S -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 178 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 179 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 180 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 181 | SO-2605-131-04 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | DIVAN-(K) | 4" Divan- 6FT Foam | 6FT | PC151-01 | 0 | 4 | 7 | 1 |  | STEEL LEG |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 182 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 183 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" Webbing | 6FT | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 184 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 8" Divan- 6FT Foam | 6FT | PC151-13 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 185 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 1007-(K) -HB 23" Webbing | 6FT | PC151-13 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 186 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-08 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 187 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | 5FT | PC151-08 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 188 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-05-28 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 189 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 190 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 191 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 192 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 1007-(Q) -HB 21" Webbing | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 193 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 194 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 195 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 196 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 197 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 8" Divan- 3FT Foam | 3FT | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 198 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 1007-(S) -HB 22" Webbing | 3FT | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 199 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-11 | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 200 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 201 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" Webbing | 6FT | PC151-12 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 202 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 203 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" Webbing | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 204 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 205 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" Webbing | 5FT | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 206 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-03 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 207 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | 5FT | PC151-03 | 12 | 8 |  | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 208 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 209 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 210 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-03 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 211 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-03 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 212 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 213 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | 5FT | KS-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 | THAR TIN |  |  |  | WAITING
2026-06-08 Mon |  | 214 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 215 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 216 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 217 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | 5FT | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 218 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 219 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | 5FT | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 220 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 221 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" Webbing | 5FT | PC151-02 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 222 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT Foam | 3FT | PC151-09 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 223 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" Webbing | 3FT | PC151-09 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 224 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT Foam | 3FT | PC151-08 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 225 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" Webbing | 3FT | PC151-08 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 226 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 8" Divan- 3FT Foam | 3FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 227 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 1013-(S) -HB 20" Webbing | 3FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 228 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 8" Divan- 200CMX200CM Foam | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 229 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" Webbing | 200CMX200CM | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 230 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 1013-(SS) -HB 22" Webbing | 3.5FT | PC151-18 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 231 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 232 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 1013-(SS) -HB 20" Webbing | 3.5FT | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 233 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 234 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" Webbing | 3.5FT | PC151-02 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 235 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 236 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" Webbing | 3.5FT | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 237 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 238 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" Webbing | 3.5FT | PC151-11 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 239 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 240 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 241 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 242 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 243 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 244 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | 5FT | PC151-18 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 245 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 246 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 247 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-14 | 14 | 10 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 248 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Webbing | 6FT | PC151-14 | 14 | 10 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 249 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 250 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Webbing | 6FT | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 251 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 252 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 253 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-13 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 254 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | 6FT | PC151-13 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 255 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-12 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 256 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Webbing | 6FT | PC151-12 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 257 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 258 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | 6FT | PC151-10 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 259 | SO-2605-209-01 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 16 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 260 | SO-2605-209-01 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 2008(A)-(K) -HB 25" Webbing | 6FT | PC151-01 | 16 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 261 | SO-2605-209-02 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 262 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 263 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Webbing | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 264 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 265 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 266 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 267 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 268 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 269 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | 6FT | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 270 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 271 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Webbing | 6FT | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 272 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 273 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Webbing | 6FT | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 274 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 275 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | 6FT | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 276 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 277 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" Webbing | 5FT | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 278 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 279 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" Webbing | 6FT | PC151-06 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 280 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 281 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 2009(A)-(K) -HB 21" Webbing | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 282 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 283 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" Webbing | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 284 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 285 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" Webbing | 5FT | PC151-15 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 286 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 287 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 2038(A)-(K) -HB 20" Webbing | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 288 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-13 | 14 | 8 | 4 | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 289 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" Webbing | 5FT | PC151-13 | 14 | 8 | 4 | 1 |  |  | 2026-05-28 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 290 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 291 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" Webbing | 5FT | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-29 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 292 | SO-2605-209-04 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" Webbing | 5FT | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-21 | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 293 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 294 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" Webbing | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 295 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 296 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 297 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 298 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Webbing | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 299 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 300 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Webbing | 5FT | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 301 | SO-2605-051-01 | PO-008654 | ZNT6705 | Houzs Century | PG | SO-2605-051 | 5530-1A(LHF) | 5530-1A(LHF) -Base 24 (Webbing) | 24 | CH141-11 |  |  | 6 | 1 |  |  | 2026-05-28 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 302 | SO-2605-051-03 | PO-008654 | ZNT6705 | Houzs Century | PG | SO-2605-051 | 5530-1A(RHF) | 5530-1A(RHF) -Base 24 (Webbing) | 24 | CH141-11 |  |  | 6 | 1 |  |  | 2026-05-28 | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 303 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | 28 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 304 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 305 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | 28 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 306 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530-2NA -Base 28 (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 307 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 308 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Webbing) | 28 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 309 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 310 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Left Arm (Webbing) | 28 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 311 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 312 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 313 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 314 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL (Webbing) | 24 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 315 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL (Webbing) | 24 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 316 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 317 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 318 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Left Arm (Webbing) | 28 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 319 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 320 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 321 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Left Arm (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 322 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 323 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 324 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 325 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530-1NA -Base 28 (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 326 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 327 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 328 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 329 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 330 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 331 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Left Arm (Webbing) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 332 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Webbing) | 28 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 333 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Webbing) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 334 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Left Arm (Webbing) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 335 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 336 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 337 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 338 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 339 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 340 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 341 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 342 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 343 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 344 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 345 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 346 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 347 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 28 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 348 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 8" Divan- 200CMX200CM Foam | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 349 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" Webbing | 200CMX200CM | PC151-02 | 14 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 350 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-12 Fri |  | 351 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" Webbing | 5FT | PC151-03 | 12 | 10 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-12 Fri |  | 352 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 353 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" Webbing | 6FT | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 354 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 355 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 356 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 357 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 358 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 359 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" Webbing | 5FT | PC151-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 360 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 361 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" Webbing | 5FT | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 362 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 363 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" Webbing | 5FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-12 Fri |  | 364 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 365 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | 5FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-12 Fri |  | 366 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 367 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Left Arm (Webbing) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 368 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Webbing) | 28 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 369 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 370 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Webbing) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 371 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Left Arm (Webbing) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 372 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 373 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 374 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 375 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 376 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 377 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 28 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 378 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Right Arm (Webbing) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 379 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Webbing) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 380 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 381 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 382 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 383 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Left Arm (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 384 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA -Base 30 (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 385 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 386 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 387 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 388 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 389 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 390 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Right Arm (Webbing) | 30 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 391 | SO-2605-300-01 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | DIVAN-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 392 | SO-2605-296-01 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 393 | SO-2605-296-02 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 394 | SO-2605-296-03 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(S) | 8" Divan- 3FT Foam | 3FT | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 395 | SO-2605-283-01 | PO-008976 | HC10887 | Houzs Century | PG | SO-2605-283 | DIVAN-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-01 | 0 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 396 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 397 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 398 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 399 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | 5FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 400 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 401 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" Webbing | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 402 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 403 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" Webbing | 3.5FT | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 404 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat | 2026-05-11 | 405 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" Webbing | 6FT | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-13 Sat |  | 406 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 407 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" Webbing | 6FT | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 408 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 409 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" Webbing | 6FT | PC151-13 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 410 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 411 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" Webbing | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 412 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 413 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" Webbing | 6FT | PC151-17 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 414 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 415 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" Webbing | 6FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 416 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 417 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 418 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 419 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-06 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 420 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 421 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-15 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 422 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 423 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 424 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 425 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 426 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 427 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-15 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 428 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 429 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 430 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 431 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 432 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 433 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | 5FT | PC151-17 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 434 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 435 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" Webbing | 5FT | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-13 Sat |  | 436 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 8" Divan- 3FT Foam | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 437 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" Webbing | 3FT | PC151-02 | 8 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 438 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 439 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" Webbing | 6FT | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 440 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 441 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" Webbing | 5FT | PC151-17 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 442 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 443 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Webbing | 6FT | PC151-02 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 444 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 445 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" Webbing | 6FT | PC151-01 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 446 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-13 Sat |  | 447 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 448 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-15 Mon | 2026-05-11 | 449 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-15 Mon |  | 450 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 451 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 452 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-15 Mon |  | 453 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | 6FT | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-15 Mon |  | 454 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 455 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | 6FT | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 456 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 457 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | 6FT | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 458 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-15 Mon |  | 459 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | 6FT | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-15 Mon |  | 460 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 461 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Webbing | 6FT | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 462 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-15 Mon |  | 463 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" Webbing | 6FT | PC151-01 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-15 Mon |  | 464 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 465 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 466 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 8" Divan- 200CMX200CM Foam | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 467 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" Webbing | 200CMX200CM | PC151-01 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 468 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 469 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" Webbing | 6FT | PC151-02 | 14 | 10 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 470 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT Foam | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 471 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" Webbing | 3.5FT | PC151-02 | 12 | 12 |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 472 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 473 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Webbing | 5FT | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 474 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-15 Mon |  | 475 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" Webbing | 5FT | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-15 Mon |  | 476 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 8" Divan- 3.5FT Foam | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 477 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" Webbing | 3.5FT | PC151-03 | 14 | 8 |  | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 478 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 479 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 480 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 481 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Webbing) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-15 Mon |  | 482 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Webbing) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-15 Mon |  | 483 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-16 Tue |  | 484 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 485 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 486 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 28 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 487 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Webbing) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-16 Tue |  | 488 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Back Cushion 24 (Webbing) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-16 Tue |  | 489 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 24 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-16 Tue |  | 490 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Webbing) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 491 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Back Cushion 24 (Webbing) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 492 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 24 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 493 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Left Arm (Webbing) | 28 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 494 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (Webbing) | 28 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 495 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Back Cushion 28 (Webbing) | 28 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 496 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Right Arm (Webbing) | 28 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 497 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (Webbing) | 28 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 498 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Back Cushion 28 (Webbing) | 28 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 499 | SO-2605-103-03 | PO-008770 | ZNT5112 | Houzs Century | KL | SO-2605-103 | 5536-1A(RHF) | 5536 -Right Arm (Webbing) |  | BO315-32 | 0 | 0 | 1 | 1 |  |  | 2026-05-26 | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 500 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 501 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 502 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Right Arm (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 503 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S -Base 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 504 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 505 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Left Arm (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 506 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Right Arm (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 507 | SO-2605-103-02 | PO-008770 | ZNT5112 | Houzs Century | KL | SO-2605-103 | 5536-CNR | 5536-CNR -Base (Webbing) |  | BO315-32 | 0 | 0 | 1 | 1 |  |  | 2026-05-26 | 2026-06-03 |  |  |  |  | WAITING
2026-06-16 Tue |  | 508 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR -Base 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 509 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 510 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 511 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | 5FT | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 512 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-13 | 14 | 8 | 2 | 1 |  |  | 2026-05-13 | 2026-06-13 | THAR TIN |  |  |  | WAITING
2026-06-17 Wed |  | 513 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-17 Wed |  | 514 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | 5FT | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-17 Wed |  | 515 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 516 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" Webbing | 6FT | PC151-01 | 12 | 10 |  | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 517 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 8" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 518 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Webbing | 6FT | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 519 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 520 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" Webbing | 5FT | PC151-02 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 521 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 522 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" Webbing | 5FT | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 523 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 524 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 525 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Left Arm (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 526 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 527 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 528 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 529 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL (Webbing) | 28 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-17 Wed |  | 530 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Webbing) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 531 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 532 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Left Arm (Webbing) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 533 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Right Arm (Webbing) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 534 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 535 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Webbing) | 28 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 536 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 537 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 538 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Left Arm (Webbing) | 30 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 539 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 540 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 541 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 542 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | 8" Divan- 5FT Foam | 5FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 543 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | 8" Divan- 3FT Foam | 3FT | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-18 Thu |  | 544 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 10" Divan- 6FT Foam | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-18 Thu |  | 545 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" Webbing | 6FT | PC151-01 | 14 | 10 | 2 | 1 |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-18 Thu |  | 546 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-18 Thu |  | 547 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" Webbing | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-18 Thu |  | 548 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 8" Divan- 6FT Foam | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-24 |  |  |  |  | WAITING
2026-06-18 Thu |  | 549 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" Webbing | 6FT | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-24 |  |  |  |  | WAITING
2026-06-18 Thu |  | 550 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 10" Divan- 5FT Foam | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-18 Thu |  | 551 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" Webbing | 5FT | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-20 |  |  |  |  | WAITING
2026-06-18 Thu |  | 552 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (Webbing) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 553 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Webbing) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 554 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (Webbing) | 30 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 555 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 556 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 557 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 558 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 559 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 560 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 561 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 562 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 563 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (Webbing) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 564 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Back Cushion 32 (Webbing) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 565 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Right Arm (Webbing) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 566 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535-1NA -Base 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 567 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535 -Back Cushion 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 568 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535-1S -Base 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 569 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Back Cushion 30 (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 570 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Left Arm (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 571 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Right Arm (Webbing) | 30 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 572 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (Webbing) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 573 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Back Cushion 32 (Webbing) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 574 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Left Arm (Webbing) | 32 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 575 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (Webbing) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 576 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Back Cushion 32 (Webbing) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 577 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Right Arm (Webbing) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 578 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (Webbing) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 579 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Back Cushion 32 (Webbing) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 580 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Left Arm (Webbing) | 32 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 581 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Webbing) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 582 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Webbing) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 583 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Left Arm (Webbing) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 584 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Webbing) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 585 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Webbing) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-18 Thu |  | 586 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Right Arm (Webbing) | 30 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-09 |  |  |  |  | WAITING
2026-06-19 Fri |  | 587 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Webbing) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 588 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 589 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 590 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Webbing) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 591 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 592 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 593 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 594 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 595 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 596 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Webbing) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 597 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 598 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Left Arm (Webbing) | 28 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 599 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 600 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 601 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | 28 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-19 Fri |  | 602 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 603 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 604 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | 28 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 605 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Webbing) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 606 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Webbing) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 607 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 608 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S -Base 28 (Webbing) | 28 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-19 Fri |  | 609 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Back Cushion 28 (Webbing) | 28 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-19 Fri |  | 610 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Left Arm (Webbing) | 28 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-19 Fri |  | 611 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Right Arm (Webbing) | 28 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-22 |  |  |  |  | WAITING
2026-06-19 Fri |  | 612 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Webbing) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 613 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Back Cushion 24 (Webbing) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-19 Fri |  | 614 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | 24 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 |  |  |  |  | WAITING
2026-06-20 Sat |  | 615 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 12" Divan- 6FT Foam | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  |  | 2026-07-03 |  |  |  |  | WAITING
2026-06-20 Sat |  | 616 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" Webbing | 6FT | PC151-14 | 14 | 12 |  | 1 |  |  |  | 2026-07-03 |  |  |  |  | WAITING
2026-06-20 Sat |  | 617 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 618 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 619 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 620 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Right Arm (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 621 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530-L(RHF) -Base 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 622 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Back Cushion 30 (Webbing) | 30 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 623 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 624 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 625 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Right Arm (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 626 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 627 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Back Cushion 30 (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 628 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Left Arm (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 629 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR -Base 30 (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-20 Sat |  | 630 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536 -Back Cushion 30 (Webbing) | 30 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-17 |  |  |  |  | WAITING

## 7-Uphol
包面 Upholstery — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Quantity | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Fab Sewing CD | Foaming CD | Framing CD | Upholstery DD | PIC 1 | PIC 2 | Completed Date | Overdue | Status
2026-06-02 Tue |  | 1 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-05-25 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 2 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  | 2026-05-25 |  |  | 2026-06-29 |  |  |  |  | WAITING
2026-06-02 Tue |  | 3 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-20 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 4 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-20 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 5 | SO-2605-187-01 | PO-008861 | HC10725 | Houzs Century | KL | SO-2605-187 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | 5FT | 1 | PC151-14 | 12 | 8 | 2 | 1 |  |  | 2026-05-20 | 2026-05-26 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 6 | SO-2605-124-01 | PO-008799 | HC9650 | Houzs Century | SRW | SO-2605-124 | 1005-(Q) | 1005-(Q) -HB 24" | 5FT | 1 | PC151-02 | 12 | 8 | 4 | 1 |  |  | 2026-05-23 | 2026-05-28 |  | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 7 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-23 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 8 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 1005-(Q) -HB 21" | 5FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-23 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 9 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG | 2026-05-25 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 10 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 1005-(Q) -HB 25" | 5FT | 1 | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG | 2026-05-25 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 11 | SO-2605-234-02 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1005-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge Fo Curve Divan | 2026-05-26 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 12 | SO-2605-234-02 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1005-(Q) | 1005-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge Fo Curve Divan | 2026-05-26 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 13 | SO-2605-009-01 | PO-008663 |  | Houzs Century | KL | SO-2605-009 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-05-12 | 2026-05-15 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 14 | SO-2605-023-01 | PO-008684 | HC14191 | Houzs Century | KL | SO-2605-023 | 1007-(K) | 1007-(K) -HB 20" | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-11 | 2026-05-11 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 15 | SO-2605-160-02 | PO-008843 | HC9783 | Houzs Century | KL | SO-2605-160 | 1007-(Q) | 4" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 4 | 7 | 1 |  |  | 2026-05-20 | 2026-05-25 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 16 | SO-2605-160-02 | PO-008843 | HC9783 | Houzs Century | KL | SO-2605-160 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-01 | 10 | 4 | 7 | 1 |  |  | 2026-05-20 | 2026-05-25 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 17 | SO-2605-161-01 | PO-008844 | HC9782 | Houzs Century | KL | SO-2605-161 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-11 | 11 | 8 | 2 | 1 |  | Divan Legs 12pcs (Customer Request) | 2026-05-20 | 2026-05-25 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 18 | SO-2605-167-01 | KENSHO 21-01 |  | The Conts | KL | SO-2605-167 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-21 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 19 | SO-2605-167-01 | KENSHO 21-01 |  | The Conts | KL | SO-2605-167 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-21 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 20 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan | 2026-05-22 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 21 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan | 2026-05-22 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 22 | SO-2605-205-01 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-23 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 23 | SO-2605-205-01 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 1007-(S) -HB 22" | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-23 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 24 | SO-2605-205-02 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-23 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 25 | SO-2605-205-02 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 1007-(S) -HB 22" | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-23 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 26 | SO-2605-213-01 | PO-008892 | HC10938 | Houzs Century | SRW | SO-2605-213 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-28 | 2026-05-29 |  | 2026-06-29 |  |  |  |  | WAITING
2026-06-02 Tue |  | 27 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-20 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 28 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-20 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 29 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-20 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 30 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-20 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 31 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-20 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 32 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-20 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 33 | SO-2605-186-01 | PO-008860 | HC9786 | Houzs Century | KL | SO-2605-186 | 1013-(SS) | 10" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 | Right Drawer |  | 2026-05-19 | 2026-05-22 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 34 | SO-2605-186-01 | PO-008860 | HC9786 | Houzs Century | KL | SO-2605-186 | 1013-(SS) | 1013-(SS) -HB 23" | 3.5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 | Right Drawer |  | 2026-05-19 | 2026-05-22 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 35 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-13 | 12 | 8 |  | 1 |  |  | 2026-05-20 |  |  | 2026-06-29 |  |  |  |  | WAITING
2026-06-02 Tue |  | 36 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 1013-(SS) -HB 20" | 3.5FT | 1 | PC151-13 | 12 | 8 |  | 1 |  |  | 2026-05-20 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 37 | SO-2604-321-03 | PO-008610 | EGT0264+ZNT5239 | Houzs Century | KL | SO-2604-321 | 1023(HF)(W)-(SS) | 10" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 12 | 10 |  | 1 | HB Fully Cover; No Side Panel |  | 2026-05-16 | 2026-05-21 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 38 | SO-2604-321-03 | PO-008610 | EGT0264+ZNT5239 | Houzs Century | KL | SO-2604-321 | 1023(HF)(W)-(SS) | 1023(HF)(W)-(SS) -HB 22" | 3.5FT | 1 | PC151-02 | 12 | 10 |  | 1 | HB Fully Cover; No Side Panel |  | 2026-05-16 | 2026-05-21 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 39 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 40 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-02 Tue |  | 41 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 16 | 8 | 1 | 1 | [5 empty] | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 42 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" | 6FT | 1 | PC151-01 | 16 | 8 | 1 | 1 | [5 empty] | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 43 | SO-2605-102-01 | PO-008769 | HC14275 | Houzs Century | KL | SO-2605-102 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-17 | 14 | 8 | 4 | 1 | Front Drawer |  | 2026-05-22 | 2026-05-28 |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 44 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-04 | 12 | 10 | 1 | 1 |  |  | 2026-05-26 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 45 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | 6FT | 1 | PC151-04 | 12 | 10 | 1 | 1 |  |  | 2026-05-26 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-02 Tue |  | 46 | SO-2605-098-03 | PO-008764 | HC14277 | Houzs Century | KL | SO-2605-098 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | 5FT | 1 | PC151-02 | 12 | 10 |  | 1 | HB Straight |  | 2026-05-23 | 2026-05-25 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-02 Tue |  | 47 | SO-2605-098-04 | PO-008764 | HC14277 | Houzs Century | KL | SO-2605-098 | 2008(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 10 |  | 1 | HB Straight |  | 2026-05-22 | 2026-05-25 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 48 | SO-2605-234-01 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-03 | 14 | 8 |  | 1 | Divan Curve | HB Straight to Wall/Edge do Curve Divan | 2026-05-26 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 49 | SO-2605-234-01 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-03 | 14 | 8 |  | 1 | Divan Curve | HB Straight to Wall/Edge do Curve Divan | 2026-05-26 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 50 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-21 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-03 Wed |  | 51 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 2009(A)-(K) -HB 23" | 6FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  | 2026-05-21 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-03 Wed |  | 52 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 8" Divan- 6FT | 6FT | 2 | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-03 Wed |  | 53 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" | 6FT | 1 | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-03 Wed |  | 54 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  | 2026-05-26 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 55 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" | 6FT | 1 | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  | 2026-05-26 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 56 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers | 2026-05-26 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 57 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" | 5FT | 1 | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers | 2026-05-26 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 58 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-10 | 10 | 8 | 1 | 1 | [5 empty] | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 59 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" | 5FT | 1 | PC151-10 | 10 | 8 | 1 | 1 | [5 empty] | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 60 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-11 | 10 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 61 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" | 3.5FT | 1 | PC151-11 | 10 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 62 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-11 | 14 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 63 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" | 5FT | 1 | PC151-11 | 14 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-03 Wed |  | 64 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 | [5 empty] | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 65 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 | [5 empty] | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 66 | SO-2604-276-03 | PO-008557 | HC08557 | Houzs Century | PG | SO-2604-276 | 2041(A)-(SS) | 10" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 12 | 10 | 1 | 1 |  |  | 2026-05-14 | 2026-05-12 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 67 | SO-2604-276-03 | PO-008557 | HC08557 | Houzs Century | PG | SO-2604-276 | 2041(A)-(SS) | 2041(A)-(SS) -HB 23" | 3.5FT | 1 | PC151-02 | 12 | 10 | 1 | 1 |  |  | 2026-05-14 | 2026-05-12 |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 68 | SO-2604-088-01 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(LHF) | 5530-1A(LHF) -Base 32 | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  | 2026-04-16 | 2026-05-20 |  | 2026-04-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 69 | SO-2604-088-01 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(LHF) | 5530 -Back Cushion 32 | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  | 2026-04-16 | 2026-05-20 |  | 2026-04-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 70 | SO-2604-088-01 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(LHF) | 5530 -Left Arm | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  | 2026-04-16 | 2026-05-20 |  | 2026-04-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 71 | SO-2604-088-02 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(RHF) | 5530-1A(RHF) -Base 32 | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  | 2026-04-16 | 2026-05-20 |  | 2026-04-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 72 | SO-2604-088-02 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(RHF) | 5530 -Back Cushion 32 | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  | 2026-04-16 | 2026-05-20 |  | 2026-04-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 73 | SO-2604-088-02 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(RHF) | 5530 -Right Arm | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  | 2026-04-16 | 2026-05-20 |  | 2026-04-29 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 74 | SO-2604-086-01 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  | 2026-04-23 | 2026-05-20 |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 75 | SO-2604-086-01 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-2A(RHF) | 5530 -Back Cushion 28 | 28 | 2 | BO315-12 |  |  | 6 | 1 |  |  | 2026-04-23 | 2026-05-20 |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 76 | SO-2604-086-01 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-2A(RHF) | 5530 -Right Arm | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  | 2026-04-23 | 2026-05-20 |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 77 | SO-2604-265-02 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-2A(RHF) | 5530 -Right Arm | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-11 | 2026-05-16 |  | 2026-05-07 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 78 | SO-2604-265-02 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-11 | 2026-05-16 |  | 2026-05-07 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 79 | SO-2604-265-02 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-2A(RHF) | 5530 -Back Cushion 28 | 28 | 2 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-11 | 2026-05-16 |  | 2026-05-07 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 80 | SO-2604-086-02 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  | 2026-04-23 | 2026-05-20 |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 81 | SO-2604-086-02 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-L(LHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  | 2026-04-23 | 2026-05-20 |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-03 Wed |  | 82 | SO-2604-086-02 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-L(LHF) | 5530 -Left Arm | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  | 2026-04-23 | 2026-05-20 |  | 2026-05-06 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 83 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530-1A(LHF) -Base 30 | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-23 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 84 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530 -Back Cushion 30 | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-23 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 85 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530 -Left Arm | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-23 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 86 | SO-2605-050-02 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(RHF) | 5530-1A(RHF) -Base 30 | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-23 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 87 | SO-2605-050-02 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(RHF) | 5530 -Back Cushion 30 | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-23 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 88 | SO-2605-050-02 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(RHF) | 5530 -Right Arm | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  | 2026-05-23 |  |  | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 89 | SO-2605-063-05 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-1NA | 5530-1NA -Base 28 | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 90 | SO-2605-063-05 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-1NA | 5530 -Back Cushion 28 | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 91 | SO-2605-063-01 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 92 | SO-2605-063-01 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-2A(LHF) | 5530 -Back Cushion 28 | 28 | 2 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 93 | SO-2605-063-01 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-2A(LHF) | 5530 -Left Arm | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 94 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530-2A(LHF) -Base |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 95 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Back Cushion |  | 2 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 96 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530 -Left Arm |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 97 | SO-2604-265-01 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-11 | 2026-05-16 |  | 2026-05-07 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 98 | SO-2604-265-01 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-L(LHF) | 5530 -Back Cushion 28 | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-11 | 2026-05-16 |  | 2026-05-07 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 99 | SO-2604-265-01 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-L(LHF) | 5530 -Left Arm | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  | 2026-05-11 | 2026-05-16 |  | 2026-05-07 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 100 | SO-2605-063-02 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 101 | SO-2605-063-02 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-L(RHF) | 5530 -Right Arm | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 102 | SO-2605-063-02 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-L(RHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  | 2026-05-18 | 2026-05-28 |  | 2026-05-18 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 103 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530-L(RHF) -Base |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 104 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Back Cushion |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 105 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530 -Right Arm |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 106 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Back Cushion 24 | 24 | 2 | M2402-13 |  |  | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 107 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 | 24 | 1 | M2402-13 |  |  | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 108 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531 -Left Arm | 24 | 1 | M2402-13 |  |  | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 109 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 110 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 111 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 112 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-28 |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 113 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-28 |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 114 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-28 |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 115 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Right Arm | 28 | 1 | M2402-4 |  |  | 6 | 1 | [5 empty] | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 116 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Back Cushion 28 | 28 | 2 | M2402-4 |  |  | 6 | 1 | [5 empty] | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 117 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531 -Left Arm | 28 | 1 | M2402-4 |  |  | 6 | 1 | [5 empty] | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 118 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S -Base 28 | 28 | 1 | M2402-4 |  |  | 6 | 1 | [5 empty] | 2026-05-16 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 119 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Back Cushion 28 | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 120 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531 -Left Arm | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 121 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 122 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-28 |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 123 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531 -Back Cushion 28 | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-28 |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 124 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531 -Left Arm | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-28 |  | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-04 Thu |  | 125 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Right Arm | 24 | 1 | M2402-13 |  |  | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 126 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) -Base 24 | 24 | 1 | M2402-13 |  |  | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-04 Thu |  | 127 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531 -Back Cushion 24 | 24 | 1 | M2402-13 |  |  | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-05 Fri |  | 128 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 129 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 130 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 131 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 132 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531 -Back Cushion 28 | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 133 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531 -Left Arm | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  | 2026-05-20 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 134 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 135 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Back Cushion 32 | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 136 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535 -Left Arm | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 137 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA -Base 32 | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 138 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535 -Back Cushion 32 | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 139 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Left Arm | 30 | 1 | CH141-14 |  |  | 1 | 1 | [5 empty] | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 140 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 | 30 | 1 | CH141-14 |  |  | 1 | 1 | [5 empty] | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 141 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535 -Back Cushion 30 | 30 | 2 | CH141-14 |  |  | 1 | 1 | [5 empty] | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 142 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) -Base 32 | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 143 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Back Cushion 32 | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 144 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535 -Right Arm | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 145 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) -Base 30 | 30 | 1 | CH141-14 |  |  | 1 | 1 | [5 empty] | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 146 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Back Cushion 30 | 30 | 1 | CH141-14 |  |  | 1 | 1 | [5 empty] | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 147 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535 -Right Arm | 30 | 1 | CH141-14 |  |  | 1 | 1 | [5 empty] | 2026-05-25 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 148 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Left Arm | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 149 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Right Arm | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 150 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536-2S -Base 30 | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 151 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536 -Back Cushion 30 | 30 | 2 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 152 | SO-2603-207-01 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(LHF) | 5537-1A(LHF) -Base 35 | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  | 2026-05-04 | 2026-05-19 |  | 2026-05-19 | ZAW LIN |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 153 | SO-2603-207-01 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(LHF) | 5537 -Back Cushion 35 | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  | 2026-05-04 | 2026-05-19 |  | 2026-04-29 | ZAW LIN |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 154 | SO-2603-207-01 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(LHF) | 5537 -Left Arm | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  | 2026-05-04 | 2026-05-19 |  | 2026-05-19 | ZAW LIN |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 155 | SO-2603-207-02 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(RHF) | 5537 -Back Cushion 35 | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  | 2026-05-04 | 2026-05-13 |  | 2026-04-29 | ZAW LIN |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 156 | SO-2603-207-02 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(RHF) | 5537 -Right Arm | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  | 2026-05-04 | 2026-05-13 |  | 2026-05-19 | ZAW LIN |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 157 | SO-2603-207-02 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(RHF) | 5537-1A(RHF) -Base 35 | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  | 2026-05-04 | 2026-05-13 |  | 2026-05-19 | ZAW LIN |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 158 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 159 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Back Cushion 28 | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 160 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540 -Right Arm | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 161 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 162 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Back Cushion 32 | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 163 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540 -Right Arm | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 164 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540 -Back Cushion 32 | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 165 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA -Base 32 | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-05 Fri |  | 166 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 167 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Back Cushion 28 | 28 | 2 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 168 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540 -Left Arm | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-05-21 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 169 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 | 26 | 1 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 170 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Back Cushion 26 | 26 | 2 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 171 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540 -Right Arm | 26 | 1 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 172 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL |  | 1 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 173 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) -Base 32 | 32 | 1 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 174 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Back Cushion 32 | 32 | 1 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-05 Fri |  | 175 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540 -Left Arm | 32 | 1 | BO315-23 |  |  | 6 | 1 | [5 empty] | 2026-05-15 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 176 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 4" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 4 | 6 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-06 Sat |  | 177 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 4 | 6 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-06 Sat |  | 178 | SO-2605-132-01 | PO-008817 | AKHC 2431 | Houzs Century | PG | SO-2605-132 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-23 | 2026-05-26 |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 179 | SO-2605-064-01 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  | 2026-05-18 | 2026-05-23 |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 180 | SO-2605-064-01 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-1A(LHF) | 5540 -Back Cushion 30 | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  | 2026-05-18 | 2026-05-23 |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 181 | SO-2605-064-01 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-1A(LHF) | 5540 -Left Arm | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  | 2026-05-18 | 2026-05-23 |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 182 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF) -Base |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-22 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 183 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Back Cushion |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-22 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 184 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540 -Left Arm |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-22 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 185 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 186 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Back Cushion 32 | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 187 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540 -Left Arm | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-06 Sat |  | 188 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540-1A(RHF) -Base |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-22 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 189 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Right Arm |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-22 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 190 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540 -Back Cushion |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 | 2026-05-22 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 191 | SO-2605-064-02 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-2A(RHF) | 5540-2A(RHF) -Base 30 | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  | 2026-05-18 | 2026-05-23 |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 192 | SO-2605-064-02 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-2A(RHF) | 5540 -Back Cushion 30 | 30 | 2 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  | 2026-05-18 | 2026-05-23 |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 193 | SO-2605-064-02 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-2A(RHF) | 5540 -Right Arm | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  | 2026-05-18 | 2026-05-23 |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 194 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 195 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 196 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 197 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-06 Sat |  | 198 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 199 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 200 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 201 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 202 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 203 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 204 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 205 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 206 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 207 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 208 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 209 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-05-26 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 210 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 211 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 212 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 213 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 214 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 215 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 216 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 217 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-06 Sat |  | 218 | SO-2605-011-01 | PO-008666 |  | Houzs Century | KL | SO-2605-011 | DIVAN-(K) | 8" Divan- 6FT | 6FT | 2 | KS-02 |  | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-06 Sat |  | 219 | SO-2604-300-01 | PO-008585 | EGT0549 | Houzs Century | KL | SO-2604-300 | DIVAN-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 |  | 10 |  | 1 | Front Drawer |  | 2026-05-19 |  |  | 2026-05-23 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 220 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 221 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 222 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 223 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | 5FT | 1 | PC151-02 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 224 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 225 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | 5FT | 1 | PC151-02 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 226 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 227 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" | 6FT | 1 | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 228 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 14 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 229 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 1007-(K) -HB 23" | 6FT | 1 | PC151-13 | 14 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 230 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  | 2026-05-23 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 231 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  | 2026-05-23 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 232 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-08 | 10 | 8 | 4 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 233 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-08 | 10 | 8 | 4 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 234 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 235 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 236 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-23 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 237 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-17 | 12 | 8 | 2 | 1 |  |  | 2026-05-23 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 238 | SO-2605-207-01 | PO-008884 | HC10876 | Houzs Century | PG | SO-2605-207 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 239 | SO-2605-207-01 | PO-008884 | HC10876 | Houzs Century | PG | SO-2605-207 | 1007-(Q) | 1007-(Q) -HB 24" | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 240 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 10 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 241 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-17 | 10 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-08 Mon |  | 242 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-08 Mon |  | 243 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 244 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 245 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 246 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 247 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-08 Mon |  | 248 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 249 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 250 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 251 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-08 Mon |  | 252 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 253 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 254 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 255 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 256 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 257 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 258 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 259 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-23 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 260 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 261 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112-2S -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 262 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-08 Mon |  | 263 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-21 |  |  | 2026-06-05 |  |  |  |  | WAITING
2026-06-09 Tue |  | 264 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 265 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" | 6FT | 1 | PC151-01 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 266 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-23 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 267 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-23 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 268 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 269 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 270 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-23 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 271 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 1007-(S) -HB 22" | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  | 2026-05-23 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 272 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 273 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 274 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-12 | 10 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 275 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" | 6FT | 1 | PC151-12 | 10 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 276 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-10 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 277 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" | 5FT | 1 | PC151-10 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 278 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-10 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 279 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" | 5FT | 1 | PC151-10 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 280 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 12 | 8 |  | 1 |  |  | 2026-05-26 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 281 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-03 | 12 | 8 |  | 1 |  |  | 2026-05-26 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 282 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 283 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 284 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 285 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-03 | 12 | 8 | 2 | 1 |  |  | 2026-05-26 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 286 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | KS-14 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 287 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | KS-14 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 288 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 289 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 290 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 291 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 292 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 293 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 294 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 14 | 8 | 1 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 295 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" | 5FT | 1 | PC151-02 | 14 | 8 | 1 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 296 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-09 | 12 | 8 | 1 | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 297 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" | 3FT | 1 | PC151-09 | 12 | 8 | 1 | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 298 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-08 | 12 | 8 | 1 | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 299 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" | 3FT | 1 | PC151-08 | 12 | 8 | 1 | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 300 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 301 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 1013-(S) -HB 20" | 3FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 302 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 8" Divan- 200CMX200CM | 200CMX200CM | 2 | PC151-10 | 12 | 8 | 1 | 1 | [5 empty] | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 303 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" | 200CMX200CM | 1 | PC151-10 | 12 | 8 | 1 | 1 | [5 empty] | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-09 Tue |  | 304 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-18 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 305 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 1013-(SS) -HB 22" | 3.5FT | 1 | PC151-18 | 12 | 8 | 2 | 1 |  |  | 2026-05-29 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 306 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 307 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 1013-(SS) -HB 20" | 3.5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-09 Tue |  | 308 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 10 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 309 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" | 3.5FT | 1 | PC151-02 | 10 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 310 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 311 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" | 3.5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 312 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-11 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 313 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" | 3.5FT | 1 | PC151-11 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-09 Tue |  | 314 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 315 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 316 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 317 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 318 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-18 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-09 Tue |  | 319 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-18 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 320 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 321 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 322 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-14 | 14 | 10 |  | 1 |  |  | 2026-05-26 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 323 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | 6FT | 1 | PC151-14 | 14 | 10 |  | 1 |  |  | 2026-05-26 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 324 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 325 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 326 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 327 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 328 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 | 4 | 1 |  |  | 2026-05-26 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 329 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-13 | 12 | 8 | 4 | 1 |  |  | 2026-05-26 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 330 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-12 | 12 | 8 | 1 | 1 |  |  | 2026-05-26 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 331 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | 6FT | 1 | PC151-12 | 12 | 8 | 1 | 1 |  |  | 2026-05-26 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 332 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-10 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 333 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-10 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 334 | SO-2605-209-01 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 16 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-25 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 335 | SO-2605-209-01 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 2008(A)-(K) -HB 25" | 6FT | 1 | PC151-01 | 16 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-25 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 336 | SO-2605-209-02 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-26 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 337 | SO-2605-209-02 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-26 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 338 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 339 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 340 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 341 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 342 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-26 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 343 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY | 2026-05-26 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 344 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 345 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | 6FT | 1 | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-10 Wed |  | 346 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 347 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | 6FT | 1 | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-10 Wed |  | 348 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-21 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-10 Wed |  | 349 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | 5FT | 1 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall | 2026-05-21 |  |  | 2026-05-28 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 350 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 351 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | 6FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 352 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 353 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 354 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-06 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 355 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" | 6FT | 1 | PC151-06 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 356 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-28 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 357 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 2009(A)-(K) -HB 21" | 6FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  | 2026-05-28 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 358 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-28 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 359 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  | 2026-05-28 |  |  | 2026-05-31 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 360 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-15 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 361 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" | 5FT | 1 | PC151-15 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 362 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 363 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 2038(A)-(K) -HB 20" | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  | 2026-05-25 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 364 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-13 | 14 | 8 | 4 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 365 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" | 5FT | 1 | PC151-13 | 14 | 8 | 4 | 1 |  |  | 2026-05-25 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-11 Thu |  | 366 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-26 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 367 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-26 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 368 | SO-2605-209-04 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered | 2026-05-25 | 2026-05-29 |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 369 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 370 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 371 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 372 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-11 Thu |  | 373 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 374 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | 5FT | 1 | PC151-02 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 375 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 376 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | 5FT | 1 | PC151-02 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-11 Thu |  | 377 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | 28 | 1 | CH141-12 |  |  | 6 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 378 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Back Cushion 28 | 28 | 2 | CH141-12 |  |  | 6 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-11 Thu |  | 379 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530 -Right Arm | 28 | 1 | CH141-12 |  |  | 6 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 380 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 381 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 382 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530 -Left Arm | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 383 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 384 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 385 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530 -Left Arm | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 386 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 387 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 388 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530 -Right Arm | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 389 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530-1NA -Base 28 | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 390 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530 -Back Cushion 28 | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 391 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 392 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Back Cushion 28 | 28 | 2 | BO315-22 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 393 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530 -Right Arm | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 394 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530-2NA -Base 28 | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-12 Fri |  | 395 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530 -Back Cushion 28 | 28 | 2 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  | 2026-05-28 |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-12 Fri |  | 396 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | 28 | 1 | CH141-12 |  |  | 6 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 397 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Back Cushion 28 | 28 | 1 | CH141-12 |  |  | 6 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 398 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530 -Left Arm | 28 | 1 | CH141-12 |  |  | 6 | 1 | [5 empty] | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-12 Fri |  | 399 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 400 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 401 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530 -Left Arm | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 402 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-12 Fri |  | 403 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-12 Fri |  | 404 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530 -Right Arm | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-12 Fri |  | 405 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL | 24 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  | 2026-05-28 |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 406 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Back Cushion 28 | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 407 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531 -Left Arm | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 408 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 409 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Back Cushion 28 | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 410 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531 -Left Arm | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 411 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 412 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 413 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 414 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 415 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 416 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 417 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 418 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 419 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 420 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 421 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 422 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 423 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-12 Fri |  | 424 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Left Arm | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 425 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-12 Fri |  | 426 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531 -Back Cushion 28 | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 427 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 8" Divan- 200CMX200CM | 200CMX200CM | 2 | PC151-02 | 14 | 8 |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 428 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" | 200CMX200CM | 1 | PC151-02 | 14 | 8 |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-13 Sat |  | 429 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-03 | 12 | 10 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 430 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" | 5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 431 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 432 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 433 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 434 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 435 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 436 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 437 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 438 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 439 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 440 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 441 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-14 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 442 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" | 5FT | 1 | PC151-14 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 443 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 444 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" | 5FT | 1 | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 445 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 10 | 1 | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 446 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-01 | 10 | 10 | 1 | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-13 Sat |  | 447 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 448 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-13 Sat |  | 449 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 450 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 451 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 452 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-13 Sat |  | 453 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-13 Sat |  | 454 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-13 Sat |  | 455 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 456 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Back Cushion 28 | 28 | 2 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 457 | SO-2605-071-01 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-2A(LHF) | 5531 -Left Arm | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 458 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 459 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Back Cushion 28 | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 460 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531 -Left Arm | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-13 Sat |  | 461 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531-L(RHF) -Base 28 | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 462 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Back Cushion 28 | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 463 | SO-2605-071-02 | PO/2605-010 | TCF0352+CR0976 | Carress | KL | SO-2605-071 | 5531-L(RHF) | 5531 -Right Arm | 28 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  | 2026-05-16 |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 464 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 465 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Back Cushion 30 | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 466 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540 -Left Arm | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 467 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA -Base 30 | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 468 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540 -Back Cushion 30 | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 469 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-13 Sat |  | 470 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) -Base 30 | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 471 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Back Cushion 30 | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 472 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540 -Right Arm | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 473 | SO-2605-300-01 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | DIVAN-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 0 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 474 | SO-2605-296-01 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 0 | 8 | 1 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 475 | SO-2605-296-02 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 0 | 8 | 1 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 476 | SO-2605-296-03 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-03 | 0 | 8 | 1 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-13 Sat |  | 477 | SO-2605-283-01 | PO-008976 | HC10887 | Houzs Century | PG | SO-2605-283 | DIVAN-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-01 | 0 | 8 | 2 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 478 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-17 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 479 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-17 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 480 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-14 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 481 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-14 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 482 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 483 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-13 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 484 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 485 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 486 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-17 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 487 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" | 6FT | 1 | PC151-17 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 488 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 489 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" | 6FT | 1 | PC151-01 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 490 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 491 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-17 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 492 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-06 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 493 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-06 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 494 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-15 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 495 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-15 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 496 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 497 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 498 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 499 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 500 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-15 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 501 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-15 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 502 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 503 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-04 |  |  |  |  | WAITING
2026-06-15 Mon |  | 504 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 505 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-17 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 506 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 507 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-15 Mon |  | 508 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-02 | 8 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 509 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" | 3FT | 1 | PC151-02 | 8 | 8 |  | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 510 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-15 Mon |  | 511 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-15 Mon |  | 512 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 513 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" | 5FT | 1 | PC151-17 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-15 Mon |  | 514 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-02 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 515 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | 6FT | 1 | PC151-02 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-03 |  |  |  |  | WAITING
2026-06-15 Mon |  | 516 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-15 Mon |  | 517 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-15 Mon |  | 518 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 519 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  |  |  | 2026-06-07 |  |  |  |  | WAITING
2026-06-15 Mon |  | 520 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 521 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-15 Mon |  | 522 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 10 | 1 | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-15 Mon |  | 523 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | 6FT | 1 | PC151-01 | 10 | 10 | 1 | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 524 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 525 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 526 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 527 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 528 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 529 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 530 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 531 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  |  |  | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 532 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-16 Tue |  | 533 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-16 Tue |  | 534 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-16 Tue |  | 535 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" | 6FT | 1 | PC151-01 | 10 | 8 | 1 | 1 | [5 empty] | 2026-06-11 |  |  |  |  | WAITING
2026-06-16 Tue |  | 536 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 537 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 538 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 8" Divan- 200CMX200CM | 200CMX200CM | 2 | PC151-01 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-12 |  |  |  |  | WAITING
2026-06-16 Tue |  | 539 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" | 200CMX200CM | 1 | PC151-01 | 14 | 8 | 4 | 1 | [5 empty] | 2026-06-12 |  |  |  |  | WAITING
2026-06-16 Tue |  | 540 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-02 | 14 | 10 |  | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 541 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" | 6FT | 1 | PC151-02 | 14 | 10 |  | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 542 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 12 | 12 |  | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 543 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" | 3.5FT | 1 | PC151-02 | 12 | 12 |  | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-16 Tue |  | 544 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 545 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-16 Tue |  | 546 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 547 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | [5 empty] | 2026-06-06 |  |  |  |  | WAITING
2026-06-16 Tue |  | 548 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 14 | 8 |  | 1 | [5 empty] | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 549 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" | 3.5FT | 1 | PC151-03 | 14 | 8 |  | 1 | [5 empty] | 2026-05-29 |  |  |  | OVERDUE | WAITING
2026-06-16 Tue |  | 550 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 551 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 552 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530 -Right Arm | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  |  |  | 2026-06-04 |  |  |  |  | WAITING
2026-06-16 Tue |  | 553 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Back Cushion 24 | 24 | 2 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 554 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-07 |  |  |  |  | WAITING
2026-06-16 Tue |  | 555 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531 -Right Arm | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 556 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-15 |  |  |  |  | WAITING
2026-06-17 Wed |  | 557 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 | [5 empty] | 2026-06-15 |  |  |  |  | WAITING
2026-06-17 Wed |  | 558 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-13 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 559 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-13 | 14 | 8 | 2 | 1 | [5 empty] | 2026-06-14 |  |  |  |  | WAITING
2026-06-17 Wed |  | 560 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-18 |  |  |  |  | WAITING
2026-06-17 Wed |  | 561 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 | [5 empty] | 2026-06-18 |  |  |  |  | WAITING
2026-06-17 Wed |  | 562 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 10 |  | 1 | [5 empty] | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 563 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 10 |  | 1 | [5 empty] | 2026-06-13 |  |  |  |  | WAITING
2026-06-17 Wed |  | 564 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-15 |  |  |  |  | WAITING
2026-06-17 Wed |  | 565 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | [5 empty] | 2026-06-15 |  |  |  |  | WAITING
2026-06-17 Wed |  | 566 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | 28 | 1 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-05-23 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 567 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Back Cushion 28 | 28 | 2 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-05-23 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 568 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531 -Right Arm | 28 | 1 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". | 2026-05-23 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 569 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) -Base 24 | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 570 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Back Cushion 24 | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 571 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531 -Left Arm | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-07 |  |  |  |  | WAITING
2026-06-17 Wed |  | 572 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531-L(LHF) -Base 24 | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-05-23 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 573 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Back Cushion 24 | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-05-23 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 574 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531 -Left Arm | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. | 2026-05-23 |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 575 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 | 28 | 1 | PC151-01 |  |  |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-17 Wed |  | 576 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Back Cushion 28 | 28 | 2 | PC151-01 |  |  |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-17 Wed |  | 577 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535 -Left Arm | 28 | 1 | PC151-01 |  |  |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-17 Wed |  | 578 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) -Base 28 | 28 | 1 | PC151-01 |  |  |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-17 Wed |  | 579 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Back Cushion 28 | 28 | 1 | PC151-01 |  |  |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-17 Wed |  | 580 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535 -Right Arm | 28 | 1 | PC151-01 |  |  |  | 1 | [5 empty] | 2026-06-05 |  |  |  |  | WAITING
2026-06-17 Wed |  | 581 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 582 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Back Cushion 30 | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 583 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536 -Left Arm | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 584 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 585 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Back Cushion 30 | 30 | 2 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 586 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536 -Right Arm | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 587 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S -Base 30 | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 588 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Back Cushion 30 | 30 | 2 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 589 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Left Arm | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 590 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536 -Right Arm | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 591 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR -Base 30 | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 592 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536 -Back Cushion 30 | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-10 |  |  |  |  | WAITING
2026-06-17 Wed |  | 593 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 594 | SO-2605-259-01 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | DIVAN-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 14 | 8 | 4 | 1 | Divan Top(W) | Divan Only specified; product matched to DIVAN-(K) |  |  |  | 2026-06-03 |  |  |  |  | WAITING
2026-06-17 Wed |  | 595 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 0 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 596 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 0 | 8 |  | 1 | [5 empty] | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 597 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-17 Wed |  | 598 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  |  |  | 2026-06-08 |  |  |  |  | WAITING
2026-06-18 Thu |  | 599 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 600 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" | 5FT | 1 | PC151-02 | 12 | 8 | 1 | 1 | [5 empty] | 2026-06-15 |  |  |  |  | WAITING
2026-06-18 Thu |  | 601 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-18 Thu |  | 602 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" | 5FT | 1 | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  |  |  | 2026-06-13 |  |  |  |  | WAITING
2026-06-18 Thu |  | 603 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 604 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 605 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530 -Left Arm | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  |  |  | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 606 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 607 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Back Cushion 28 | 28 | 2 | BO315-21 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 608 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530 -Right Arm | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 609 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-14 |  |  |  |  | WAITING
2026-06-18 Thu |  | 610 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-18 Thu |  | 611 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Back Cushion 28 | 28 | 2 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-18 Thu |  | 612 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531 -Left Arm | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-18 Thu |  | 613 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) -Base 28 | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-18 Thu |  | 614 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Back Cushion 28 | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-18 Thu |  | 615 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531 -Right Arm | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  |  |  | 2026-06-12 |  |  |  |  | WAITING
2026-06-18 Thu |  | 616 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 617 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 618 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 619 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 620 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Back Cushion 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 621 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535 -Left Arm | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 622 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 623 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 624 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-20 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 625 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 626 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Back Cushion 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 627 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535 -Right Arm | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 628 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 629 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Back Cushion 32 | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 630 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535 -Right Arm | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 631 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535-1NA -Base 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 632 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535 -Back Cushion 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 633 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535-1S -Base 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 634 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Back Cushion 30 | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 635 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Left Arm | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 636 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535 -Right Arm | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  | 2026-05-19 |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 637 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 638 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Back Cushion 32 | 32 | 2 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 639 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535 -Left Arm | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  |  |  | 2026-06-17 |  |  |  |  | WAITING
2026-06-18 Thu |  | 640 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 641 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Back Cushion 32 | 32 | 2 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 642 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535 -Right Arm | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 643 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) -Base 32 | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 644 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Back Cushion 32 | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 645 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535 -Left Arm | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 646 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 647 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Back Cushion 30 | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-18 Thu |  | 648 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536 -Right Arm | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-19 Fri |  | 649 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 10 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-19 Fri |  | 650 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" | 6FT | 1 | PC151-01 | 14 | 10 | 2 | 1 | [5 empty] | 2026-06-02 |  |  |  |  | WAITING
2026-06-19 Fri |  | 651 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 10 | 2 | 1 | [5 empty] | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 652 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" | 5FT | 1 | PC151-02 | 12 | 10 | 2 | 1 | [5 empty] | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 653 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  |  |  | 2026-06-25 |  |  |  |  | WAITING
2026-06-19 Fri |  | 654 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" | 6FT | 1 | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  |  |  | 2026-06-25 |  |  |  |  | WAITING
2026-06-19 Fri |  | 655 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 10 | 2 | 1 | [5 empty] | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 656 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" | 5FT | 1 | PC151-02 | 12 | 10 | 2 | 1 | [5 empty] | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 657 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 658 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Back Cushion 28 | 28 | 2 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 659 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530 -Left Arm | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 660 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 661 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Back Cushion 28 | 28 | 2 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 662 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530 -Left Arm | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 663 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 664 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Back Cushion 28 | 28 | 2 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 665 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530 -Right Arm | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 666 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 667 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 668 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530 -Left Arm | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 669 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 670 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Back Cushion 28 | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 671 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530 -Right Arm | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  | 2026-05-26 |  |  | 2026-06-19 |  |  |  |  | WAITING
2026-06-19 Fri |  | 672 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 673 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Back Cushion 28 | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 674 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530 -Right Arm | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  | 2026-05-26 |  |  | 2026-06-21 |  |  |  |  | WAITING
2026-06-19 Fri |  | 675 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 676 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Back Cushion 24 | 24 | 2 | NINJA 02 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 677 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531 -Right Arm | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 678 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S -Base 28 | 28 | 1 | M2402-13 |  |  |  | 1 | [5 empty] | 2026-06-24 |  |  |  |  | WAITING
2026-06-19 Fri |  | 679 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Back Cushion 28 | 28 | 2 | M2402-13 |  |  |  | 1 | [5 empty] | 2026-06-24 |  |  |  |  | WAITING
2026-06-19 Fri |  | 680 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Left Arm | 28 | 1 | M2402-13 |  |  |  | 1 | [5 empty] | 2026-06-24 |  |  |  |  | WAITING
2026-06-19 Fri |  | 681 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531 -Right Arm | 28 | 1 | M2402-13 |  |  |  | 1 | [5 empty] | 2026-06-24 |  |  |  |  | WAITING
2026-06-19 Fri |  | 682 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) -Base 24 | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 683 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Back Cushion 24 | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 684 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531 -Left Arm | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 | [5 empty] | 2026-06-20 |  |  |  |  | WAITING
2026-06-19 Fri |  | 685 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-19 Fri |  | 686 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Back Cushion 30 | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-19 Fri |  | 687 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536 -Left Arm | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  |  |  | 2026-06-11 |  |  |  |  | WAITING
2026-06-20 Sat |  | 688 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 12" Divan- 6FT | 6FT | 2 | PC151-14 | 14 | 12 |  | 1 | [5 empty] | 2026-07-04 |  |  |  |  | WAITING
2026-06-20 Sat |  | 689 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" | 6FT | 1 | PC151-14 | 14 | 12 |  | 1 | [5 empty] | 2026-07-04 |  |  |  |  | WAITING
2026-06-20 Sat |  | 690 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Left Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 691 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530 -Back Cushion 30 | 30 | 2 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 692 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 693 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Right Arm | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 694 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530 -Back Cushion 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 695 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530-L(RHF) -Base 30 | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  | 2026-05-22 |  |  | 2026-05-30 |  |  |  | OVERDUE | WAITING
2026-06-20 Sat |  | 696 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 697 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Back Cushion 30 | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 698 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536 -Right Arm | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 699 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 700 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Back Cushion 30 | 30 | 2 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 701 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536 -Left Arm | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 702 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR -Base 30 | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING
2026-06-20 Sat |  | 703 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536 -Back Cushion 30 | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 | [5 empty] | 2026-06-19 |  |  |  |  | WAITING

## 8-Pack
包装 Packing — 工序 Plan Due 排程 (该部门要做的活,按计划到期先后;栏位跟 ERP 一样)
Plan Due 计划到期 | Sent | # | SO / PO | Customer PO ID | Customer Ref | Customer | State | Company SO ID | Model | WIP | Size | Quantity | Colour | Gap | Divan | Leg | Total | Special Order | Notes | Upholstery CD | Packing DD | PIC 1 | PIC 2 | Completed Date | Overdue | Rack | Status
2026-06-02 Tue |  | 1 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 2 | SO-2605-212-01 | PO-008891 | HC10947 | Houzs Century | SRW | SO-2605-212 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 3 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 4 | SO-2605-131-08 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 5 | SO-2605-187-01 | PO-008861 | HC10725 | Houzs Century | KL | SO-2605-187 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | 5FT | 1 | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-26 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 6 | SO-2605-124-01 | PO-008799 | HC9650 | Houzs Century | SRW | SO-2605-124 | 1005-(Q) | 1005-(Q) -HB 24" | 5FT | 1 | PC151-02 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-25 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 7 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 8 | SO-2605-131-07 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1005-(Q) | 1005-(Q) -HB 21" | 5FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 9 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 10 | SO-2605-157-01 | PO-008840 | HC9780 | Houzs Century | SBH | SO-2605-157 | 1005-(Q) | 1005-(Q) -HB 25" | 5FT | 1 | PC151-04 | 10 | 8 | 7 | 1 |  | 7" METAL LEG + SUPPORT LEG |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 11 | SO-2605-234-02 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1005-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge Fo Curve Divan |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 12 | SO-2605-234-02 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1005-(Q) | 1005-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge Fo Curve Divan |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 13 | SO-2605-009-01 | PO-008663 |  | Houzs Century | KL | SO-2605-009 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 8 | 1 | 1 |  |  | 2026-05-16 | 2026-05-14 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 14 | SO-2605-023-01 | PO-008684 | HC14191 | Houzs Century | KL | SO-2605-023 | 1007-(K) | 1007-(K) -HB 20" | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 15 | SO-2605-160-02 | PO-008843 | HC9783 | Houzs Century | KL | SO-2605-160 | 1007-(Q) | 4" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 4 | 7 | 1 |  |  |  | 2026-05-21 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 16 | SO-2605-160-02 | PO-008843 | HC9783 | Houzs Century | KL | SO-2605-160 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-01 | 10 | 4 | 7 | 1 |  |  |  | 2026-05-21 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 17 | SO-2605-161-01 | PO-008844 | HC9782 | Houzs Century | KL | SO-2605-161 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-11 | 11 | 8 | 2 | 1 |  | Divan Legs 12pcs (Customer Request) |  | 2026-05-21 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 18 | SO-2605-167-01 | KENSHO 21-01 |  | The Conts | KL | SO-2605-167 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 19 | SO-2605-167-01 | KENSHO 21-01 |  | The Conts | KL | SO-2605-167 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 20 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 21 | SO-2605-234-03 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 | Divan Curve | Edge do curve Divan |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 22 | SO-2605-205-01 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 23 | SO-2605-205-01 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 1007-(S) -HB 22" | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 24 | SO-2605-205-02 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 25 | SO-2605-205-02 | PO-008882 | HC10178 + ZNT6032 | Houzs Century | KL | SO-2605-205 | 1007-(S) | 1007-(S) -HB 22" | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 26 | SO-2605-213-01 | PO-008892 | HC10938 | Houzs Century | SRW | SO-2605-213 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 27 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 28 | SO-2605-141-01 | PO/2605-051 | CR1137 | Carress | KL | SO-2605-141 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 29 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 30 | SO-2605-166-01 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 31 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 32 | SO-2605-166-02 | SKELINE C13A-05 |  | The Conts | KL | SO-2605-166 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 33 | SO-2605-186-01 | PO-008860 | HC9786 | Houzs Century | KL | SO-2605-186 | 1013-(SS) | 10" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 | Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 34 | SO-2605-186-01 | PO-008860 | HC9786 | Houzs Century | KL | SO-2605-186 | 1013-(SS) | 1013-(SS) -HB 23" | 3.5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 | Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 35 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-13 | 12 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 36 | SO-2605-188-01 | PO-008862 | HC9787 + HC14140 | Houzs Century | KL | SO-2605-188 | 1013-(SS) | 1013-(SS) -HB 20" | 3.5FT | 1 | PC151-13 | 12 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 37 | SO-2604-321-03 | PO-008610 | EGT0264+ZNT5239 | Houzs Century | KL | SO-2604-321 | 1023(HF)(W)-(SS) | 10" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 12 | 10 |  | 1 | HB Fully Cover; No Side Panel |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 38 | SO-2604-321-03 | PO-008610 | EGT0264+ZNT5239 | Houzs Century | KL | SO-2604-321 | 1023(HF)(W)-(SS) | 1023(HF)(W)-(SS) -HB 22" | 3.5FT | 1 | PC151-02 | 12 | 10 |  | 1 | HB Fully Cover; No Side Panel |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 39 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 40 | SO-2605-131-11 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 1041-(Q) | 1041-(Q) -HB 23" | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 41 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 16 | 8 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 42 | SO-2605-131-06 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2003-(K) | 2003-(K) -HB 25" | 6FT | 1 | PC151-01 | 16 | 8 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 43 | SO-2605-102-01 | PO-008769 | HC14275 | Houzs Century | KL | SO-2605-102 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-17 | 14 | 8 | 4 | 1 | Front Drawer |  | 2026-05-29 | 2026-05-26 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 44 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-04 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 45 | SO-2605-208-01 | PO-008886 | HC14091 | Houzs Century | KL | SO-2605-208 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | 6FT | 1 | PC151-04 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 46 | SO-2605-098-03 | PO-008764 | HC14277 | Houzs Century | KL | SO-2605-098 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | 5FT | 1 | PC151-02 | 12 | 10 |  | 1 | HB Straight |  |  | 2026-05-25 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 47 | SO-2605-098-04 | PO-008764 | HC14277 | Houzs Century | KL | SO-2605-098 | 2008(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 10 |  | 1 | HB Straight |  | 2026-05-25 | 2026-05-25 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 48 | SO-2604-083-04 | PO-2603-104 | TCF0409 | Carress | KL | SO-2604-083 | LONG PILLOW | LONG PILLOW KN390-2 x2 |  | 2 | KN390-2 |  |  |  | 1 |  |  |  | 2026-04-14 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 49 | SO-2605-063-03 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | LONG PILLOW | LONG PILLOW BO315-31 x2 | 12" X 28" | 2 | BO315-31 |  |  |  | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 50 | SO-2604-088-03 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | SQUARE PILLOW | SQUARE PILLOW BO315-31 x4 |  | 4 | BO315-31 |  |  |  | 1 |  |  |  | 2026-05-03 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 51 | SO-2604-092-03 | PO-008243 | ZNT5354 | Houzs Century | KL | SO-2604-092 | SQUARE PILLOW | SQUARE PILLOW CH141-5 x2 |  | 2 | CH141-5 |  |  |  | 1 |  |  |  | 2026-04-28 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 52 | SO-2604-210-03 | PO-008436 | ZNT5309 | Houzs Century | KL | SO-2604-210 | SQUARE PILLOW | SQUARE PILLOW AM275-2 x2 |  | 2 | AM275-2 |  |  |  | 1 |  |  |  | 2026-05-02 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 53 | SO-2604-324-03 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | SQUARE PILLOW | SQUARE PILLOW BO315-22 x2 | 16" X 16" | 2 | BO315-22 |  |  |  | 1 |  |  |  | 2026-05-23 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 54 | SO-2605-104-04 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW | 16" X 16" | 1 | CH141-3 | 0 | 0 |  | 1 |  |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 55 | SO-2605-104-05 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW | 16" X 16" | 1 | CH141-3 | 0 | 0 |  | 1 |  |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 56 | SO-2605-104-06 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | SQUARE PILLOW | SQUARE PILLOW | 16" X 16" | 1 | CH141-3 | 0 | 0 |  | 1 |  |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 57 | SO-2605-222-03 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | SQUARE PILLOW | SQUARE PILLOW | 16" X 16" | 1 | CH141-7 |  |  |  | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-02 Tue |  | 58 | SO-2605-222-04 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | SQUARE PILLOW | SQUARE PILLOW | 16" X 16" | 1 | CH141-5 |  |  |  | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 59 | SO-2605-234-01 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-03 | 14 | 8 |  | 1 | Divan Curve | HB Straight to Wall/Edge do Curve Divan |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 60 | SO-2605-234-01 | PO-008911 | HC7081 | Houzs Century | KL | SO-2605-234 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-03 | 14 | 8 |  | 1 | Divan Curve | HB Straight to Wall/Edge do Curve Divan |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 61 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 62 | SO-2605-131-10 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2009(A)-(K) | 2009(A)-(K) -HB 23" | 6FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 63 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 8" Divan- 6FT | 6FT | 2 | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  | 2026-06-02 | [5 empty] | WAITING
2026-06-03 Wed |  | 64 | SO-2605-171-01 | PO-008430 | HC10184 | Houzs Century | SRW | SO-2605-171 | 2011(A)-(K) | 2011(A)-(K) -HB 20" | 6FT | 1 | KS-18 | 12 | 8 |  | 1 |  | NO LINE IN FRONT; miss out order - Pls help to rush delivery before 22/5 |  | 2026-06-02 | [5 empty] | WAITING
2026-06-03 Wed |  | 65 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 66 | SO-2605-233-01 | PO-008910 | EGT0190 | Houzs Century | SRW | SO-2605-233 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" | 6FT | 1 | PC151-12 | 12 | 8 |  | 1 | HB Fully Cover, Divan Top Fully Cover |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 67 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 68 | SO-2605-251-01 | PO-008928 | HC14141 | Houzs Century | KL | SO-2605-251 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" | 5FT | 1 | PC151-01 | 14 | 8 |  | 1 | Front Drawer | Add two front drawers |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 69 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-10 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 70 | SO-2605-204-02 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" | 5FT | 1 | PC151-10 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 71 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-11 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 72 | SO-2605-204-03 | PO-008881 | HC14207 | Houzs Century | KL | SO-2605-204 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" | 3.5FT | 1 | PC151-11 | 10 | 8 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 73 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-11 | 14 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 74 | SO-2605-010-02 | PO-008665 |  | Houzs Century | KL | SO-2605-010 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" | 5FT | 1 | PC151-11 | 14 | 8 |  | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 75 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 76 | SO-2605-131-05 | PO-008806 |  | Houzs Century | KL | SO-2605-131 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-28 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 77 | SO-2604-276-03 | PO-008557 | HC08557 | Houzs Century | PG | SO-2604-276 | 2041(A)-(SS) | 10" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-08 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 78 | SO-2604-276-03 | PO-008557 | HC08557 | Houzs Century | PG | SO-2604-276 | 2041(A)-(SS) | 2041(A)-(SS) -HB 23" | 3.5FT | 1 | PC151-02 | 12 | 10 | 1 | 1 |  |  |  | 2026-05-08 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 79 | SO-2604-088-01 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(LHF) | 5530-1A(LHF) | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  |  | 2026-05-03 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 80 | SO-2604-088-02 | PO-008196 | ZNT4339 | Houzs Century | KL | SO-2604-088 | 5530-1A(RHF) | 5530-1A(RHF) | 32 | 1 | BO315-21 |  |  | 6 | 1 |  |  |  | 2026-05-03 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 81 | SO-2604-086-01 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-2A(RHF) | 5530-2A(RHF) | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  |  | 2026-05-10 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 82 | SO-2604-265-02 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-2A(RHF) | 5530-2A(RHF) | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  |  | 2026-05-08 |  |  |  | OVERDUE |  | WAITING
2026-06-03 Wed |  | 83 | SO-2604-086-02 | PO-008290 | ZNT6013 | Houzs Century | KL | SO-2604-086 | 5530-L(LHF) | 5530-L(LHF) | 28 | 1 | BO315-12 |  |  | 6 | 1 |  |  |  | 2026-05-10 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 84 | SO-2605-050-01 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(LHF) | 5530-1A(LHF) | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 85 | SO-2605-050-02 | PO-008653 | ZNT5338 | Houzs Century | KL | SO-2605-050 | 5530-1A(RHF) | 5530-1A(RHF) | 30 | 1 | BO315-1 |  |  | 6 | 1 | Nylon Fabric; 5537 Backrest |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 86 | SO-2605-063-05 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-1NA | 5530-1NA | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 87 | SO-2605-063-01 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-2A(LHF) | 5530-2A(LHF) | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 88 | SO-2605-109-01 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-2A(LHF) | 5530-2A(LHF) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 89 | SO-2604-265-01 | PO-008464 | ZNT6009 | Houzs Century | KL | SO-2604-265 | 5530-L(LHF) | 5530-L(LHF) | 28 | 1 | CH141-13 |  |  | 6 | 1 |  |  |  | 2026-05-08 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 90 | SO-2605-063-02 | PO-008699 | ZNT5297 | Houzs Century | PG | SO-2605-063 | 5530-L(RHF) | 5530-L(RHF) | 28 | 1 | BO315-31 |  |  | 6 | 1 |  |  |  | 2026-05-24 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 91 | SO-2605-109-02 | PO-008780 | ZNT6124 | Houzs Century | KL | SO-2605-109 | 5530-L(RHF) | 5530-L(RHF) |  | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram shows model 9028 L noted above; 2R+L layout: left cluster [24][24] = 2A(RHF), right box [24] = L(LHF) |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 92 | SO-2605-079-01 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-2A(LHF) | 5531-2A(LHF) | 24 | 1 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 93 | SO-2604-327-02 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 94 | SO-2605-072-02 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 95 | SO-2604-345-03 | PO-2604-113 | TCF0467 | Carress | KL | SO-2604-345 | 5531-2S | 5531-2S | 28 | 1 | M2402-4 |  |  | 6 | 1 |  |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 96 | SO-2604-327-01 | PO-2604-104 | TCF0448 | Carress | KL | SO-2604-327 | 5531-L(LHF) | 5531-L(LHF) | 28 | 1 | NINJA 08 |  |  | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE | Rack 4 | WAITING
2026-06-04 Thu |  | 97 | SO-2605-072-01 | PO/2605-011 | TCF0473 | Carress | KL | SO-2605-072 | 5531-L(LHF) | 5531-L(LHF) | 28 | 1 | KN390-14 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-04 Thu |  | 98 | SO-2605-079-02 | PO/2605-002 | TCF0444 | Carress | KL | SO-2605-079 | 5531-L(RHF) | 5531-L(RHF) | 24 | 1 | M2402-13 |  |  | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri | 2026-05-13 | 99 | SO-2605-067-02 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri | 2026-05-13 | 100 | SO-2605-067-01 | PO/2605-003 | TCF0431 | Carress | KL | SO-2605-067 | 5531-L(LHF) | 5531-L(LHF) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 101 | SO-2605-104-01 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1A(LHF) | 5535-1A(LHF) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 102 | SO-2605-104-02 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-1NA | 5535-1NA | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 103 | SO-2605-222-01 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-2A(LHF) | 5535-2A(LHF) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 104 | SO-2605-104-03 | PO-008773 | ZNT6068 | Houzs Century | KL | SO-2605-104 | 5535-L(RHF) | 5535-L(RHF) | 32 | 1 | BO315-1 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 105 | SO-2605-222-02 | PO-008874 | SO-011868 | Houzs Century | KL | SO-2605-222 | 5535-L(RHF) | 5535-L(RHF) | 30 | 1 | CH141-14 |  |  | 1 | 1 |  |  |  | 2026-05-29 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 106 | SO-2605-220-01 | EXPO-007767 |  | Houzs Century | KL | SO-2605-220 | 5536-2S | 5536-2S | 30 | 1 | BO315-23 |  |  |  | 1 |  | BACKREST ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-05 Fri |  | 107 | SO-2603-207-01 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(LHF) | 5537-1A(LHF) | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  |  | 2026-05-03 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 108 | SO-2603-207-02 | PO-008193 | ZNT5816 | Houzs Century | KL | SO-2603-207 | 5537-1A(RHF) | 5537-1A(RHF) | 35 | 1 | CH141-1 |  |  | 1 | 1 | 1"LEG / NYLON FABRIC |  |  | 2026-05-03 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 109 | SO-2604-324-02 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-1A(RHF) | 5540-1A(RHF) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-24 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 110 | SO-2605-221-03 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(RHF) | 5540-1A(RHF) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-05 Fri |  | 111 | SO-2605-221-02 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1NA | 5540-1NA | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-05 Fri |  | 112 | SO-2604-324-01 | PO-008615 | ZNT5329 | Houzs Century | KL | SO-2604-324 | 5540-2A(LHF) | 5540-2A(LHF) | 28 | 1 | BO315-22 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-05-24 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 113 | SO-2605-078-03 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-2A(RHF) | 5540-2A(RHF) | 26 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 114 | SO-2605-078-02 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-CSL | 5540-CSL |  | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-05 Fri |  | 115 | SO-2605-078-01 | PO-008708 | ZNT5892/HC10930 | Houzs Century | KL | SO-2605-078 | 5540-L(LHF) | 5540-L(LHF) | 32 | 1 | BO315-23 |  |  | 6 | 1 |  |  |  | 2026-05-18 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 116 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 4" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 4 | 6 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-06 Sat |  | 117 | SO-2605-291-02 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1005-(Q) | 1005-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 4 | 6 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-06 Sat |  | 118 | SO-2605-132-01 | PO-008817 | AKHC 2431 | Houzs Century | PG | SO-2605-132 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 119 | SO-2605-064-01 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-1A(LHF) | 5540-1A(LHF) | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 120 | SO-2605-105-01 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(LHF) | 5540-1A(LHF) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 121 | SO-2605-221-01 | EXPO-007938 |  | Houzs Century | KL | SO-2605-221 | 5540-1A(LHF) | 5540-1A(LHF) | 32 | 1 | AM275-1 |  |  | 1 | 1 | EXTEND_5_; Nylon Fabric |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 122 | SO-2605-105-02 | PO-008774 | ZNT5883 | Houzs Century | KL | SO-2605-105 | 5540-1A(RHF) | 5540-1A(RHF) |  | 1 | BO315-31 | 0 | 0 | 6 | 1 | Nylon Fabric | firmness same with 5535 |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 123 | SO-2605-064-02 | PO-008700 | ZNT4337 | Houzs Century | KL | SO-2605-064 | 5540-2A(RHF) | 5540-2A(RHF) | 30 | 1 | CH141-3 |  |  | 1 | 1 | Nylon Fabric; EXTEND_5_ |  |  | 2026-05-27 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 124 | SO-2605-176-01 | STOCK5 |  | The Conts | KL | SO-2605-176 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 125 | SO-2605-177-01 | STOCK6 |  | The Conts | KL | SO-2605-177 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 126 | SO-2605-178-01 | STOCK7 |  | The Conts | KL | SO-2605-178 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 127 | SO-2605-179-01 | STOCK8 |  | The Conts | KL | SO-2605-179 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-06 Sat |  | 128 | SO-2605-180-01 | STOCK9 |  | The Conts | KL | SO-2605-180 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 129 | SO-2605-181-01 | STOCK10 |  | The Conts | KL | SO-2605-181 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-06 Sat |  | 130 | SO-2605-011-01 | PO-008666 |  | Houzs Century | KL | SO-2605-011 | DIVAN-(K) | 8" Divan- 6FT | 6FT | 2 | KS-02 |  | 8 |  | 1 |  |  |  | 2026-05-12 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 131 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-08 Mon |  | 132 | SO-2605-291-01 | PO-008993 | HC7186 | Houzs Century | KL | SO-2605-291 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | No Side Panel |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-08 Mon |  | 133 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 134 | SO-2605-226-01 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | 5FT | 1 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 135 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 136 | SO-2605-226-02 | PO-008903 | HC7942 | Houzs Century | KL | SO-2605-226 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | 5FT | 1 | PC151-02 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 137 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 138 | SO-2605-248-01 | PO-008924 | EGT0189 | Houzs Century | SRW | SO-2605-248 | 1007-(K) | 1007-(K) -HB 24" | 6FT | 1 | PC151-02 | 14 | 10 |  | 1 | HB Fully Cover, Right Drawer |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 139 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 140 | SO-2605-256-01 | PO-008935 | HC14327 | Houzs Century | KL | SO-2605-256 | 1007-(K) | 1007-(K) -HB 23" | 6FT | 1 | PC151-13 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 141 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 142 | SO-2605-154-01 | PO-008837 | HC7153 | Houzs Century | KL | SO-2605-154 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 | Right Drawer |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 143 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-08 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 144 | SO-2605-185-03 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-08 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 145 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 146 | SO-2605-185-04 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 147 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 148 | SO-2605-195-01 | PO/2605-068 | CR1145 | Carress | KL | SO-2605-195 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 149 | SO-2605-207-01 | PO-008884 | HC10876 | Houzs Century | PG | SO-2605-207 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 150 | SO-2605-207-01 | PO-008884 | HC10876 | Houzs Century | PG | SO-2605-207 | 1007-(Q) | 1007-(Q) -HB 24" | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 151 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 152 | SO-2605-249-01 | PO-008926 | HC14147 | Houzs Century | SRW | SO-2605-249 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-17 | 10 | 8 | 2 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 153 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 154 | SO-2605-255-01 | PO-008934 | HC14326 | Houzs Century | KL | SO-2605-255 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 155 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 156 | SO-2605-257-01 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 157 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 158 | SO-2605-257-02 | PO-008936 | HC9784 | Houzs Century | KL | SO-2605-257 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-08 Mon |  | 159 | SO-2604-307-01 | STOCK |  | The Conts | KL | SO-2604-307 | 6112-2S | 6112-2S | 30 | 10 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 160 | SO-2605-173-01 | STOCK2 |  | The Conts | KL | SO-2605-173 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 161 | SO-2605-174-01 | STOCK3 |  | The Conts | KL | SO-2605-174 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-08 Mon |  | 162 | SO-2605-175-01 | STOCK4 |  | The Conts | KL | SO-2605-175 | 6112-2S | 6112-2S | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 163 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 164 | SO-2605-203-01 | PO-008880 | PG10209 | Houzs Century | PG | SO-2605-203 | 1007-(K) | 1007-(K) -HB 24" | 6FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 165 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 166 | SO-2605-192-04 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 167 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 168 | SO-2605-215-02 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 169 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 170 | SO-2605-185-01 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1007-(S) | 1007-(S) -HB 22" | 3FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 171 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 172 | SO-2605-070-01 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 173 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-12 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 174 | SO-2605-276-01 | PO-008968 | HC10951 | Houzs Century | SRW | SO-2605-276 | 1013-(K) | 1013-(K) -HB 20" | 6FT | 1 | PC151-12 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 175 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 176 | SO-2605-096-02 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" | 5FT | 1 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 177 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 178 | SO-2605-096-03 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(Q) | 1013-(Q) -HB 21" | 5FT | 1 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 179 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 180 | SO-2605-153-02 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-03 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 181 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 182 | SO-2605-185-02 | PO-008859 | HC14006 | Houzs Century | SBH | SO-2605-185 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-14 | 10 | 8 | 4 | 1 | Divan Top Fully Cover |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 183 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 184 | SO-2605-193-01 | PO/2605-063 | CR1142 | Carress | KL | SO-2605-193 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-03 | 12 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 185 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | KS-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 186 | SO-2605-214-01 | PO-008893 | HC14149 | Houzs Century | SRW | SO-2605-214 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | KS-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 187 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 188 | SO-2605-254-01 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 189 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 190 | SO-2605-262-01 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-17 | 12 | 8 |  | 1 | Front Drawer |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 191 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 192 | SO-2605-264-01 | PO-008958 | EGT0279 | Houzs Century | SRW | SO-2605-264 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-04 | 14 | 10 |  | 1 | Divan Top Fully Cover |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 193 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 194 | SO-2605-278-01 | PO-008970 | HC10886 | Houzs Century | PG | SO-2605-278 | 1013-(Q) | 1013-(Q) -HB 23" | 5FT | 1 | PC151-02 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 195 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-09 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 196 | SO-2605-215-03 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" | 3FT | 1 | PC151-09 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 197 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-08 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 198 | SO-2605-215-04 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 1013-(S) | 1013-(S) -HB 21" | 3FT | 1 | PC151-08 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 199 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 200 | SO-2605-254-02 | PO-008933 | HC10955 | Houzs Century | SRW | SO-2605-254 | 1013-(S) | 1013-(S) -HB 20" | 3FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 201 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 8" Divan- 200CMX200CM | 200CMX200CM | 2 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 202 | SO-2605-096-01 | PO-008762 | PG10629 | Houzs Century | PG | SO-2605-096 | 1013-(SK) | 1013-(SK) -HB 21" | 200CMX200CM | 1 | PC151-10 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-09 Tue |  | 203 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-18 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 204 | SO-2605-070-02 | PO/2605-009 | CR0976+TCF0352 | Carress | KL | SO-2605-070 | 1013-(SS) | 1013-(SS) -HB 22" | 3.5FT | 1 | PC151-18 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-09 Tue |  | 205 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 206 | SO-2605-262-02 | PO-008956 | PG10696 | Houzs Century | PG | SO-2605-262 | 1013-(SS) | 1013-(SS) -HB 20" | 3.5FT | 1 | PC151-17 | 12 | 8 |  | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-09 Tue |  | 207 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 208 | SO-2605-277-01 | PO-008969 | HC14145 | Houzs Century | SRW | SO-2605-277 | 1013-(SS) | 1013-(SS) -HB 20" | 3.5FT | 1 | PC151-02 | 10 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 209 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 210 | SO-2605-285-01 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" | 3.5FT | 1 | PC151-09 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 211 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-11 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 212 | SO-2605-285-02 | PO-008978 | HC14299 | Houzs Century | KL | SO-2605-285 | 1013-(SS) | 1013-(SS) -HB 22" | 3.5FT | 1 | PC151-11 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-09 Tue |  | 213 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 214 | SO-2605-299-01 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 215 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 216 | SO-2605-299-02 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 217 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-18 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-09 Tue |  | 218 | SO-2605-299-03 | PO-009002 | EGT0576 | Houzs Century | KL | SO-2605-299 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-18 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-10 Wed |  | 219 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-10 Wed |  | 220 | SO-2605-300-02 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | 1030-(Q) | 1030-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-10 Wed |  | 221 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-14 | 14 | 10 |  | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 222 | SO-2605-210-01 | PO-008889 | HC14283 | Houzs Century | KL | SO-2605-210 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | 6FT | 1 | PC151-14 | 14 | 10 |  | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 223 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  | 2026-06-03 | [5 empty] | WAITING
2026-06-10 Wed |  | 224 | SO-2605-286-01 | PO-008925 | HC14337 | Houzs Century | KL | SO-2605-286 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 10 |  | 1 | Right Drawer | 1 PCS RIGHT DRAWER & 1 PCS LEFT DRAWER |  | 2026-06-03 | [5 empty] | WAITING
2026-06-10 Wed |  | 225 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 226 | SO-2605-099-01 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 227 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 228 | SO-2605-192-01 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-13 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 229 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-12 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 230 | SO-2605-192-02 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | 6FT | 1 | PC151-12 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 231 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-10 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 232 | SO-2605-192-03 | PO-008866 | HC9039 | Houzs Century | SBH | SO-2605-192 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-10 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 233 | SO-2605-209-01 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 16 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 234 | SO-2605-209-01 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 2008(A)-(K) -HB 25" | 6FT | 1 | PC151-01 | 16 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 235 | SO-2605-209-02 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 236 | SO-2605-209-02 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 237 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 238 | SO-2605-238-01 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 239 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 240 | SO-2605-238-02 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 241 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 242 | SO-2605-238-03 | PO-008885 | HC14294 | Houzs Century | KL | SO-2605-238 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-13 | 12 | 8 |  | 1 |  | PC151-02 CUSHION ONLY |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 243 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 244 | SO-2605-258-01 | PO-008937 | HC14325 | Houzs Century | KL | SO-2605-258 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | 6FT | 1 | PC151-04 | 14 | 8 | 4 | 1 | HB Fully Cover |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 245 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 246 | SO-2605-263-01 | PO-008957 | HC10939 | Houzs Century | SRW | SO-2605-263 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | 6FT | 1 | PC151-01 | 14 | 8 | 4 | 1 | HB Fully Cover, Divan Full Cover |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-10 Wed |  | 247 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-10 Wed |  | 248 | SO-2605-099-02 | PO-008765 | AKHC 3951 | Houzs Century | KL | SO-2605-099 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | 5FT | 1 | PC151-01 | 14 | 8 |  | 1 | HB Straight, Divan Curve | Edge do Curve Divan/HB Straight to Wall |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 249 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-11 Thu |  | 250 | SO-2605-215-01 | PO-008894 | HC6057 | Houzs Century | KL | SO-2605-215 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | 6FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-11 Thu |  | 251 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  | 2026-06-04 | [5 empty] | WAITING
2026-06-11 Thu |  | 252 | SO-2605-295-01 | PO-008997 | HC14294 | Houzs Century | KL | SO-2605-295 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-02 | 12 | 8 |  | 1 |  | Two fabric codes referenced (PC151-02 / PC151-13) — operator to confirm which applies. Spec says 'Col:follow photo/HB straight'; HB Straight is intrinsic to product 2008(A) so not extracted as specialOrder. |  | 2026-06-04 | [5 empty] | WAITING
2026-06-11 Thu |  | 253 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-06 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 254 | SO-2605-241-01 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(K) | 2009(A)-(K) -HB 20" | 6FT | 1 | PC151-06 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 255 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 256 | SO-2605-247-01 | PO-008923 | HC9790 | Houzs Century | KL | SO-2605-247 | 2009(A)-(K) | 2009(A)-(K) -HB 21" | 6FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 257 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 258 | SO-2605-239-01 | PO/2605-087 | DL0578 | Carress | KL | SO-2605-239 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-05-31 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 259 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-15 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 260 | SO-2605-241-02 | PO-008915 | HC10410 | Houzs Century | KL | SO-2605-241 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" | 5FT | 1 | PC151-15 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 261 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 262 | SO-2605-153-01 | PO-008836 | HC5613 | Houzs Century | KL | SO-2605-153 | 2038(A)-(K) | 2038(A)-(K) -HB 20" | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 263 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-13 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-11 Thu |  | 264 | SO-2605-140-01 | PO-008825 | HC10723 + HC14151(B | Houzs Century | KL | SO-2605-140 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" | 5FT | 1 | PC151-13 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-11 Thu |  | 265 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 266 | SO-2605-209-03 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 267 | SO-2605-209-04 | PO-008887 | HC8888 | Houzs Century | KL | SO-2605-209 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | 5FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Divan Full Cover, HB Fully Cover | both backboard and divan fully covered |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 268 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 269 | SO-2605-279-01 | PO-008971 | HC5317 | Houzs Century | PG | SO-2605-279 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-11 Thu |  | 270 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-11 Thu |  | 271 | SO-2605-298-01 | PO-009001 | EGT0573 | Houzs Century | KL | SO-2605-298 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-11 Thu |  | 272 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-11 Thu |  | 273 | SO-2605-280-01 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | 5FT | 1 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-11 Thu |  | 274 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-11 Thu |  | 275 | SO-2605-280-02 | PO-008972 | HC10817 | Houzs Century | PG | SO-2605-280 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | 5FT | 1 | PC151-02 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-11 Thu |  | 276 | SO-2604-293-02 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-2A(RHF) | 5530-2A(RHF) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 277 | SO-2605-080-01 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-1A(LHF) | 5530-1A(LHF) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 278 | SO-2605-130-01 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(LHF) | 5530-1A(LHF) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 279 | SO-2605-130-03 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1A(RHF) | 5530-1A(RHF) | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 280 | SO-2605-130-02 | PO-008826 | ZNT4349 | Houzs Century | KL | SO-2605-130 | 5530-1NA | 5530-1NA | 28 | 1 | BO315-1 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 281 | SO-2605-240-02 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-2A(RHF) | 5530-2A(RHF) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 282 | SO-2605-080-02 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-2NA | 5530-2NA | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 283 | SO-2604-293-01 | PO-008548 | ZNT5113 | Houzs Century | KL | SO-2604-293 | 5530-L(LHF) | 5530-L(LHF) | 28 | 1 | CH141-12 |  |  | 6 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 284 | SO-2605-240-01 | PO-008939 | ZNT5257 | Houzs Century | KL | SO-2605-240 | 5530-L(LHF) | 5530-L(LHF) | 28 | 1 | BO315-22 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 285 | SO-2605-080-03 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-L(RHF) | 5530-L(RHF) | 28 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 286 | SO-2605-080-04 | PO-008657 | ZNT5109 | Houzs Century | KL | SO-2605-080 | 5530-STOOL | 5530-STOOL | 24 | 1 | BO315-25 |  |  | 6 | 1 | 5540_BACKREST; Nylon Fabric; OTHER: 24“x24" |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 287 | SO-2605-183-01 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-1A(LHF) | 5531-1A(LHF) | 28 | 1 | M2402-18 | 0 | 0 | 6 | 1 |  | Rightmost box of three-box diagram; size shown as 26" (differs from other two at 28") — operator to confirm size. |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 288 | SO-2605-197-01 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-1A(LHF) | 5531-1A(LHF) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 289 | SO-2605-183-02 | PO/2605-061 | TCF0488 | Carress | KL | SO-2605-183 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | M2402-18 | 0 | 0 | 4 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][26"]. Printed text says '3 Seater' but diagram shows three separate rectangles. Left two boxes form the 2A cluster (diagramOrder 0,1 treated as one 2A unit at position 0), rightmost box is 1A at position 1. However the three boxes appear to be three separate rectangles: leftmost [28"], middle [28"], rightmost [26"]. Per golden rule, three separate boxes = 1A(LHF) + 1NA + 1A(RHF). But sizes differ (28"/28"/26") — noting size discrepancy on rightmost box; operator to confirm layout and sizes. |  | 2026-06-07 | [5 empty] | WAITING
2026-06-12 Fri |  | 290 | SO-2605-194-02 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 |  | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. Diagram shows TV at top. Left cluster: two joined 28" boxes (diagramOrder 0 and 1 treated as 2A). Right cluster: single 28" box with L-flap (diagramOrder 2 = L piece). Per description '2 Seater+L SHAPE': left two boxes = 2A, right box = L. |  | 2026-06-01 | [5 empty] | WAITING
2026-06-12 Fri |  | 291 | SO-2605-196-02 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Left cluster has two boxes [28"][28"] joined = 2A. Right box [28"] with L-flap = L-shape. Per diagram order left-to-right: 2A at position 0, L at position 1. |  | 2026-06-03 | [5 empty] | WAITING
2026-06-12 Fri |  | 292 | SO-2605-197-02 | PO/2605-069 | TCF0487 | Carress | KL | SO-2605-197 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | M2402-4 |  |  | 6 | 1 | OTHER: FULL COVER |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-12 Fri |  | 293 | SO-2605-194-01 | PO/2605-064 | TCF0490 | Carress | KL | SO-2605-194 | 5531-L(LHF) | 5531-L(LHF) | 28 | 1 | GARFIELD - 3 TUNDORA | 0 | 0 | 6 | 1 |  | Fabric code GARFIELD 3-TUNDORA not found in catalog — operator to confirm. L-piece is rightmost in diagram (diagramOrder 1). |  | 2026-06-02 | [5 empty] | WAITING
2026-06-13 Sat |  | 294 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 8" Divan- 200CMX200CM | 200CMX200CM | 2 | PC151-02 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-13 Sat |  | 295 | SO-2605-123-01 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" | 200CMX200CM | 1 | PC151-02 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-13 Sat |  | 296 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-03 | 12 | 10 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-13 Sat |  | 297 | SO-2605-281-01 | PO-008973 | HC9957 | Houzs Century | PG | SO-2605-281 | 1005-(Q) | 1005-(Q) -HB 23" | 5FT | 1 | PC151-03 | 12 | 10 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-13 Sat |  | 298 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-13 Sat |  | 299 | SO-2605-275-01 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(K) | 1007-(K) -HB 23" | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 | Front Drawer |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-13 Sat |  | 300 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 301 | SO-2605-243-02 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 302 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 303 | SO-2605-243-03 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 304 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 305 | SO-2605-243-04 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 306 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 307 | SO-2605-246-01 | PO-008922 | HC9234 | Houzs Century | PG | SO-2605-246 | 1007-(Q) | 1007-(Q) -HB 20" | 5FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 308 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 309 | SO-2605-259-02 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | 1007-(Q) | 1007-(Q) -HB 24" | 5FT | 1 | PC151-14 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 310 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-08 | [5 empty] | WAITING
2026-06-13 Sat |  | 311 | SO-2605-275-02 | PO-008967 | HC10853 | Houzs Century | PG | SO-2605-275 | 1007-(Q) | 1007-(Q) -HB 19" | 5FT | 1 | PC151-01 | 10 | 8 | 1 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-08 | [5 empty] | WAITING
2026-06-13 Sat |  | 312 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-13 Sat |  | 313 | SO-2605-282-02 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 1007-(Q) | 1007-(Q) -HB 21" | 5FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-13 Sat |  | 314 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-13 Sat |  | 315 | SO-2605-297-02 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-13 Sat |  | 316 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-13 Sat |  | 317 | SO-2605-292-02 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-13 Sat |  | 318 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-13 Sat |  | 319 | SO-2605-292-03 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 1007-(SS) | 1007-(SS) -HB 19" | 3.5FT | 1 | PC151-03 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-13 Sat |  | 320 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-13 Sat |  | 321 | SO-2605-269-02 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-13 Sat |  | 322 | SO-2605-196-01 | PO/2605-070 | TCF0492 | Carress | KL | SO-2605-196 | 5531-L(LHF) | 5531-L(LHF) | 28 | 1 | KN390-2 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 323 | SO-2605-077-01 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1A(LHF) | 5540-1A(LHF) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-13 Sat |  | 324 | SO-2605-077-02 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-1NA | 5540-1NA | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-13 Sat |  | 325 | SO-2605-077-03 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-CSL | 5540-CSL | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-13 Sat |  | 326 | SO-2605-077-04 | PO-008704 | ZNT6130 | Houzs Century | KL | SO-2605-077 | 5540-L(RHF) | 5540-L(RHF) | 30 | 1 | FABRIC HR805-10 |  |  | 6 | 1 | Nylon Fabric |  |  | 2026-06-01 | [5 empty] | WAITING
2026-06-13 Sat |  | 327 | SO-2605-300-01 | PO-009003 | EGT0314 | Houzs Century | KL | SO-2605-300 | DIVAN-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 328 | SO-2605-296-01 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 329 | SO-2605-296-02 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 330 | SO-2605-296-03 | PO-008998 | HC10900 | Houzs Century | KL | SO-2605-296 | DIVAN-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-03 | 0 | 8 | 1 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-13 Sat |  | 331 | SO-2605-283-01 | PO-008976 | HC10887 | Houzs Century | PG | SO-2605-283 | DIVAN-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-01 | 0 | 8 | 2 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-15 Mon |  | 332 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-15 Mon |  | 333 | SO-2605-111-02 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-15 Mon |  | 334 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 335 | SO-2605-216-01 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-14 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 336 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 337 | SO-2605-216-04 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(K) | 1013-(K) -HB 22" | 6FT | 1 | PC151-13 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 338 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-15 Mon |  | 339 | SO-2605-229-02 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 1013-(K) | 1013-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-15 Mon |  | 340 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-17 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 341 | SO-2605-271-02 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(K) | 1013-(K) -HB 26" | 6FT | 1 | PC151-17 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 342 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 343 | SO-2605-293-02 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(K) | 1013-(K) -HB 21" | 6FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 344 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 345 | SO-2605-111-01 | PO-2605-030 |  | Carress | KL | SO-2605-111 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-17 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 346 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-06 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 347 | SO-2605-216-02 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-06 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 348 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-15 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 349 | SO-2605-216-03 | PO/2605-075 | CR1147 | Carress | KL | SO-2605-216 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-15 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 350 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 351 | SO-2605-244-01 | PO-008920 | HC14456 | Houzs Century | KL | SO-2605-244 | 1013-(Q) | 1013-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 352 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 353 | SO-2605-261-01 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 354 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-15 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 355 | SO-2605-261-02 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-15 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 356 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 357 | SO-2605-269-01 | NILAI LANDED NO425 |  | The Conts | KL | SO-2605-269 | 1013-(Q) | 1013-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-04 | [5 empty] | WAITING
2026-06-15 Mon |  | 358 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 359 | SO-2605-271-01 | PO/2605-089 | CR1150 | Carress | KL | SO-2605-271 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-17 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 360 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 361 | SO-2605-293-01 | PO-008995 | HC14205 | Houzs Century | KL | SO-2605-293 | 1013-(Q) | 1013-(Q) -HB 21" | 5FT | 1 | PC151-01 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-15 Mon |  | 362 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-02 | 8 | 8 |  | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-15 Mon |  | 363 | SO-2605-245-01 | PO-008921 | HC14456 | Houzs Century | KL | SO-2605-245 | 1013-(S) | 1013-(S) -HB 16" | 3FT | 1 | PC151-02 | 8 | 8 |  | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-15 Mon |  | 364 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  | 2026-06-12 | [5 empty] | WAITING
2026-06-15 Mon |  | 365 | SO-2605-274-01 | PO-008965 | SPLIT FROM PG10158 | Houzs Century | PG | SO-2605-274 | 1023-(K) | 1023-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 10 |  | 1 |  | drawer side ambiguous — operator to confirm |  | 2026-06-12 | [5 empty] | WAITING
2026-06-15 Mon |  | 366 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-17 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-15 Mon |  | 367 | SO-2605-288-02 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 1052-(Q) | 1052-(Q) -HB 22" | 5FT | 1 | PC151-17 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-15 Mon |  | 368 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-02 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-15 Mon |  | 369 | SO-2605-261-03 | PO-008955 | HC14461 | Houzs Century | KL | SO-2605-261 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | 6FT | 1 | PC151-02 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-15 Mon |  | 370 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-15 Mon |  | 371 | SO-2605-294-01 | PO-008996 | HC12632 | Houzs Century | KL | SO-2605-294 | 2006(A)-(K) | 2006(A)-(K) -HB 23" | 6FT | 1 | PC151-01 | 14 | 8 | 1 | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-15 Mon |  | 372 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-15 Mon |  | 373 | SO-2605-297-01 | PO-009000 | HC14214 | Houzs Century | KL | SO-2605-297 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 10 | 8 | 4 | 1 | Divan Curve |  |  | 2026-06-07 | [5 empty] | WAITING
2026-06-15 Mon |  | 374 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-15 Mon |  | 375 | SO-2605-229-01 | PO-008906 | HC10718 | Houzs Century | KL | SO-2605-229 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 8 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-15 Mon |  | 376 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-15 Mon |  | 377 | SO-2605-282-01 | PO-008975 | HC9960 | Houzs Century | KL | SO-2605-282 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | 6FT | 1 | PC151-01 | 10 | 10 | 1 | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 378 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 379 | SO-2604-281-01 | PO-008563 | HC14113 | Houzs Century | KL | SO-2604-281 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 380 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 381 | SO-2605-200-01 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 382 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 383 | SO-2605-242-01 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-01 | 14 | 10 |  | 1 | Front Drawer, Divan Curve | Make corner curve and add front drawers*** |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 384 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 385 | SO-2605-242-02 | PO-008918 | HC10137 | Houzs Century | PG | SO-2605-242 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | 6FT | 1 | PC151-12 | 14 | 10 |  | 1 | Right Drawer, Left Drawer, Divan Curve | Make corner curve and add L n R drawers*** — drawer side ambiguous (both L and R specified); operator to confirm |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 386 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-16 Tue |  | 387 | SO-2605-252-01 | PO-008929 | HC14143 | Houzs Century | KL | SO-2605-252 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | 6FT | 1 | PC151-01 | 12 | 8 |  | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-16 Tue |  | 388 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-16 Tue |  | 389 | SO-2605-292-01 | PO-008994 | HC9915 | Houzs Century | KL | SO-2605-292 | 2008(A)-(K) | 2008(A)-(K) -HB 19" | 6FT | 1 | PC151-01 | 10 | 8 | 1 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-16 Tue |  | 390 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 391 | SO-2605-243-01 | PO-008919 | HC9173 | Houzs Century | KL | SO-2605-243 | 2009(A)-(K) | 2009(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 392 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 8" Divan- 200CMX200CM | 200CMX200CM | 2 | PC151-01 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-12 | [5 empty] | WAITING
2026-06-16 Tue |  | 393 | SO-2605-211-01 | PO-008890 | HC14279 | Houzs Century | KL | SO-2605-211 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" | 200CMX200CM | 1 | PC151-01 | 14 | 8 | 4 | 1 |  |  |  | 2026-06-12 | [5 empty] | WAITING
2026-06-16 Tue |  | 394 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-02 | 14 | 10 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 395 | SO-2605-202-01 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" | 6FT | 1 | PC151-02 | 14 | 10 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 396 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT | 3.5FT | 1 | PC151-02 | 12 | 12 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 397 | SO-2605-202-02 | PO-008879 | HC14466 | Houzs Century | KL | SO-2605-202 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" | 3.5FT | 1 | PC151-02 | 12 | 12 |  | 1 |  |  |  | 2026-06-03 | [5 empty] | WAITING
2026-06-16 Tue |  | 398 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 399 | SO-2605-235-01 | PO-008912 | HC14302 | Houzs Century | KL | SO-2605-235 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | 5FT | 1 | PC151-02 | 12 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 400 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-16 Tue |  | 401 | SO-2605-288-01 | PO-008930 | HC14431 | Houzs Century | KL | SO-2605-288 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" | 5FT | 1 | PC151-01 | 10 | 8 | 4 | 1 |  |  |  | 2026-06-06 | [5 empty] | WAITING
2026-06-16 Tue |  | 402 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 8" Divan- 3.5FT | 3.5FT | 1 | PC151-03 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-16 Tue |  | 403 | SO-2605-123-02 | PO-008798 | HC5988 | Houzs Century | KL | SO-2605-123 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" | 3.5FT | 1 | PC151-03 | 14 | 8 |  | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-16 Tue |  | 404 | SV-2605-003-01 | EX-PO-008255 |  | Houzs Century | KL | SV-2605-003 | 5530-L(RHF) | 5530-L(RHF) | 28 | 1 | BO315-2 |  |  |  | 1 |  | ADD 1FT FRONT L-SHAPE |  | 2026-06-08 | [5 empty] | WAITING
2026-06-16 Tue |  | 405 | SO-2605-076-02 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-2A(RHF) | 5531-2A(RHF) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-17 Wed |  | 406 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-17 Wed |  | 407 | SO-2605-284-01 | PO-008977 | HC12637 | Houzs Century | KL | SO-2605-284 | 1007-(Q) | 1007-(Q) -HB 22" | 5FT | 1 | PC151-01 | 12 | 8 | 2 | 1 |  |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-17 Wed |  | 408 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-13 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-17 Wed |  | 409 | SO-2605-069-01 | PO/2605-007 | CR1123 | Carress | KL | SO-2605-069 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-13 | 14 | 8 | 2 | 1 |  |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-17 Wed |  | 410 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-18 | [5 empty] | WAITING
2026-06-17 Wed |  | 411 | SO-2605-289-01 | PO/2605-093 | DL0543 | Carress | KL | SO-2605-289 | 1013-(Q) | 1013-(Q) -HB 24" | 5FT | 1 | PC151-01 | 12 | 8 | 4 | 1 |  |  |  | 2026-06-18 | [5 empty] | WAITING
2026-06-17 Wed |  | 412 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 12 | 10 |  | 1 |  |  |  | 2026-06-13 | [5 empty] | WAITING
2026-06-17 Wed |  | 413 | SO-2605-228-01 | PO-008905 | PG10621 | Houzs Century | PG | SO-2605-228 | 1030-(K) | 1030-(K) -HB 22" | 6FT | 1 | PC151-01 | 12 | 10 |  | 1 |  |  |  | 2026-06-13 | [5 empty] | WAITING
2026-06-17 Wed |  | 414 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-17 Wed |  | 415 | SO-2605-190-01 | PO-008864 | HC10896 | Houzs Century | KL | SO-2605-190 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | 6FT | 1 | PC151-01 | 14 | 8 |  | 1 |  |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-17 Wed |  | 416 | SO-2605-237-02 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-2A(RHF) | 5531-2A(RHF) | 28 | 1 | KN390-1 | 0 | 0 |  | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [28"][28"][24"]. Left two boxes (28"+28") form the 2A cluster at diagramOrder 0. The description says '2 Seater+L' with sizes (24'')(28'') indicating the L-piece is 24" and the 2-seater is 28". |  | 2026-06-12 | [5 empty] | WAITING
2026-06-17 Wed |  | 417 | SO-2605-076-01 | PO/2605-020 | TCF0501 | Carress | KL | SO-2605-076 | 5531-L(LHF) | 5531-L(LHF) | 24 | 1 | GARFIELD-2 CHERVRON | 0 | 0 | 6 | 1 |  |  |  | 2026-06-11 | [5 empty] | WAITING
2026-06-17 Wed |  | 418 | SO-2605-237-01 | PO/2605-079 | TCF0496 | Carress | KL | SO-2605-237 | 5531-L(LHF) | 5531-L(LHF) | 24 | 1 | KN390-1 | 0 | 0 |  | 1 |  | L-piece at rightmost position in diagram (diagramOrder 2), size 24". TV is at top so rightmost box is on viewer's left → L(LHF) per server computation; reporting as drawn. |  | 2026-06-12 | [5 empty] | WAITING
2026-06-17 Wed |  | 419 | SO-2605-270-01 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-2A(LHF) | 5535-2A(LHF) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-09 | [5 empty] | WAITING
2026-06-17 Wed |  | 420 | SO-2605-270-02 | NILAI LANDED NO.425 |  | The Conts | KL | SO-2605-270 | 5535-L(RHF) | 5535-L(RHF) | 28 | 1 | PC151-01 |  |  |  | 1 |  |  |  | 2026-06-09 | [5 empty] | WAITING
2026-06-17 Wed |  | 421 | SO-2605-223-01 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-1A(LHF) | 5536-1A(LHF) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-17 Wed |  | 422 | SO-2605-223-03 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2A(RHF) | 5536-2A(RHF) | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-17 Wed |  | 423 | SO-2605-223-04 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-2S | 5536-2S | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-17 Wed |  | 424 | SO-2605-223-02 | PO-008873 | SO-011826 | Houzs Century | KL | SO-2605-223 | 5536-CNR | 5536-CNR | 30 | 1 | FABRIC HR805-90 |  |  | 1 | 1 | Nylon Fabric |  |  | 2026-06-14 | [5 empty] | WAITING
2026-06-17 Wed |  | 425 | SO-2605-206-01 | PO-008883 | HC14103 | Houzs Century | KL | SO-2605-206 | DIVAN-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 0 | 10 |  | 1 | Divan Full Cover |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-17 Wed |  | 426 | SO-2605-259-01 | PO/2605-081 | CR1121 | Carress | KL | SO-2605-259 | DIVAN-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-13 | 14 | 8 | 4 | 1 | Divan Top(W) | Divan Only specified; product matched to DIVAN-(K) |  | 2026-06-03 | [5 empty] | WAITING
2026-06-17 Wed |  | 427 | SO-2605-200-02 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-17 Wed |  | 428 | SO-2605-200-03 | PO-008877 | HC5819 | Houzs Century | PG | SO-2605-200 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-01 | 0 | 8 |  | 1 |  |  |  | 2026-06-08 | [5 empty] | WAITING
2026-06-17 Wed |  | 429 | SO-2605-265-01 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  | 2026-06-08 | [5 empty] | WAITING
2026-06-17 Wed |  | 430 | SO-2605-265-02 | PO-008959 | HC9954 | Houzs Century | KL | SO-2605-265 | DIVAN-(S) | 8" Divan- 3FT | 3FT | 1 | PC151-14 | 0 | 8 | 7 | 1 |  | Metal Leg |  | 2026-06-08 | [5 empty] | WAITING
2026-06-18 Thu |  | 431 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 8" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-18 Thu |  | 432 | SO-2605-191-01 | PO-008865 | HC10897 | Houzs Century | KL | SO-2605-191 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" | 5FT | 1 | PC151-02 | 12 | 8 | 1 | 1 |  |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-18 Thu |  | 433 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  | 2026-06-13 | [5 empty] | WAITING
2026-06-18 Thu |  | 434 | SO-2605-260-01 | PO-008954 | HC10096 | Houzs Century | KL | SO-2605-260 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" | 5FT | 1 | PC151-10 | 10 | 10 | 4 | 1 | No Side Panel, Divan Top Fully Cover, HB Fully Cover |  |  | 2026-06-13 | [5 empty] | WAITING
2026-06-18 Thu |  | 435 | SO-2605-290-01 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-1A(LHF) | 5530-1A(LHF) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  | Diagram references model 9028/L-shape; mapped to 5530-L(LHF) as leftmost piece |  | 2026-06-18 | [5 empty] | WAITING
2026-06-18 Thu |  | 436 | SO-2605-290-02 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-2A(RHF) | 5530-2A(RHF) | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 | [5 empty] | WAITING
2026-06-18 Thu |  | 437 | SO-2605-290-03 | PO-009005 | ZNT4890 | Houzs Century | PG | SO-2605-290 | 5530-STOOL | 5530-STOOL | 28 | 1 | BO315-21 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-18 | [5 empty] | WAITING
2026-06-18 Thu |  | 438 | SO-2605-236-01 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-2A(LHF) | 5531-2A(LHF) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows two right-side boxes [28"][28"] forming the 2-seater module at diagramOrder 1. TV at top; rightmost cluster in diagram = RHF for 2A. |  | 2026-06-16 | [5 empty] | WAITING
2026-06-18 Thu |  | 439 | SO-2605-236-02 | PO/2605-078 | TCF0382 | Carress | KL | SO-2605-236 | 5531-L(RHF) | 5531-L(RHF) | 28 | 1 | M2402-1 | 0 | 0 | 6 | 1 |  | Diagram shows TV at top. Three boxes left-to-right: [26"][28"][28"]. Leftmost box is narrower with an L-flap shape (L-piece), middle and right boxes form the 2-seater cluster. Per description '2 Seater + Lshape': L-piece on left (diagramOrder 0) and 2A on right (diagramOrder 1). TV at top means viewer faces from top; leftmost in diagram = LHF for L-piece. |  | 2026-06-16 | [5 empty] | WAITING
2026-06-18 Thu |  | 440 | SO-2605-106-01 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) | 30 | 1 | M2402-4 | 0 | 0 | 1 | 1 |  | 1R+1NA+1R configuration — this item is the rightmost 1R (LHF per diagram right position) |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 441 | SO-2605-106-04 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(LHF) | 5535-1A(LHF) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1NA+1R configuration — this item is the leftmost 1R (RHF per diagram left position) |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 442 | SO-2605-106-03 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 443 | SO-2605-106-05 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1A(RHF) | 5535-1A(RHF) | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the leftmost 1R |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 444 | SO-2605-303-02 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-1A(RHF) | 5535-1A(RHF) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 445 | SO-2605-106-02 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1NA | 5535-1NA | 30 | 1 | M2402-4 |  |  | 1 | 1 |  | 1R+1R configuration — this item is the rightmost 1R |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 446 | SO-2605-106-06 | PO-008776 | ZNT5887 | Houzs Century | KL | SO-2605-106 | 5535-1S | 5535-1S | 30 | 1 | M2402-4 |  |  | 1 | 1 |  |  |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 447 | SO-2605-303-01 | PO/2605-098 | TCF0505 | Carress | KL | SO-2605-303 | 5535-2A(LHF) | 5535-2A(LHF) | 32 | 1 | KN390-3 | 0 | 0 | 1 | 1 |  | UPGRADED SEATER FROM 30" TO 32" |  | 2026-06-21 | [5 empty] | WAITING
2026-06-18 Thu |  | 448 | SO-2605-273-02 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-2A(RHF) | 5535-2A(RHF) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-18 Thu |  | 449 | SO-2605-273-01 | PO-008982 | ZNT6709 | Houzs Century | KL | SO-2605-273 | 5535-L(LHF) | 5535-L(LHF) | 32 | 1 | BO315-24 | 0 | 0 | 1 | 1 | Nylon Fabric |  |  | 2026-06-15 | [5 empty] | WAITING
2026-06-18 Thu |  | 450 | SO-2605-225-02 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(RHF) | 5536-1A(RHF) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 1 = rightmost box. |  | 2026-06-15 | [5 empty] | WAITING
2026-06-19 Fri |  | 451 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 10" Divan- 6FT | 6FT | 2 | PC151-01 | 14 | 10 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-19 Fri |  | 452 | SO-2605-189-01 | PO-008863 | HC10894 | Houzs Century | PG | SO-2605-189 | 1003(A)-(K) | 1003(A)-(K) -HB 26" | 6FT | 1 | PC151-01 | 14 | 10 | 2 | 1 |  |  |  | 2026-05-30 |  |  |  | OVERDUE |  | WAITING
2026-06-19 Fri |  | 453 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-21 | [5 empty] | WAITING
2026-06-19 Fri |  | 454 | SO-2605-231-01 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" | 5FT | 1 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-21 | [5 empty] | WAITING
2026-06-19 Fri |  | 455 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 8" Divan- 6FT | 6FT | 2 | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-25 | [5 empty] | WAITING
2026-06-19 Fri |  | 456 | SO-2605-302-01 | PO/2605-097 | CR1152 | Carress | KL | SO-2605-302 | 1007-(K) | 1007-(K) -HB 28" | 6FT | 1 | PC151-15 | 16 | 8 | 4 | 1 | Left Drawer | drawer side ambiguous — operator to confirm |  | 2026-06-25 | [5 empty] | WAITING
2026-06-19 Fri |  | 457 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 10" Divan- 5FT | 5FT | 2 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-21 | [5 empty] | WAITING
2026-06-19 Fri |  | 458 | SO-2605-231-02 | PO-008908 | HC9961 | Houzs Century | KL | SO-2605-231 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" | 5FT | 1 | PC151-02 | 12 | 10 | 2 | 1 |  |  |  | 2026-06-21 | [5 empty] | WAITING
2026-06-19 Fri |  | 459 | SO-2605-199-01 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-2A(LHF) | 5530-2A(LHF) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-23 | [5 empty] | WAITING
2026-06-19 Fri |  | 460 | SO-2605-224-01 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-2A(LHF) | 5530-2A(LHF) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-25 | [5 empty] | WAITING
2026-06-19 Fri |  | 461 | SO-2605-198-02 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-2A(RHF) | 5530-2A(RHF) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-23 | [5 empty] | WAITING
2026-06-19 Fri |  | 462 | SO-2605-198-01 | PO-008875 | ZNT5318 | Houzs Century | KL | SO-2605-198 | 5530-L(LHF) | 5530-L(LHF) | 28 | 1 | BO315-3 | 0 | 0 | 6 | 1 | Nylon Fabric |  |  | 2026-06-23 | [5 empty] | WAITING
2026-06-19 Fri |  | 463 | SO-2605-199-02 | PO-008876 | ZNT4816 | Houzs Century | PG | SO-2605-199 | 5530-L(RHF) | 5530-L(RHF) | 28 | 1 | BO315-3 | 0 | 0 |  | 1 |  |  |  | 2026-06-23 | [5 empty] | WAITING
2026-06-19 Fri |  | 464 | SO-2605-224-02 | PO-008913 | HC8341+8340 | Houzs Century | KL | SO-2605-224 | 5530-L(RHF) | 5530-L(RHF) | 28 | 1 | M2402-4 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-25 | [5 empty] | WAITING
2026-06-19 Fri |  | 465 | SO-2605-182-02 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-2A(RHF) | 5531-2A(RHF) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-24 | [5 empty] | WAITING
2026-06-19 Fri |  | 466 | SO-2605-301-01 | PO/2605-095 | TCF0504 | Carress | KL | SO-2605-301 | 5531-2S | 5531-2S | 28 | 1 | M2402-13 |  |  |  | 1 |  |  |  | 2026-06-28 | [5 empty] | WAITING
2026-06-19 Fri |  | 467 | SO-2605-182-01 | PO/2605-058 | TCF0433 | Carress | KL | SO-2605-182 | 5531-L(LHF) | 5531-L(LHF) | 24 | 1 | NINJA 02 | 0 | 0 | 6 | 1 |  |  |  | 2026-06-24 | [5 empty] | WAITING
2026-06-19 Fri |  | 468 | SO-2605-225-01 | PO-008914 | ZNT5336 | Houzs Century | KL | SO-2605-225 | 5536-1A(LHF) | 5536-1A(LHF) | 30 | 1 | NINJA 02 | 0 | 0 |  | 1 | 5537 Backrest, Nylon Fabric | Diagram shows two boxes [30][30] left-to-right. No TV marker visible. diagramOrder 0 = leftmost box. |  | 2026-06-15 | [5 empty] | WAITING
2026-06-20 Sat |  | 469 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 12" Divan- 6FT | 6FT | 2 | PC151-14 | 14 | 12 |  | 1 |  |  |  | 2026-07-04 | [5 empty] | WAITING
2026-06-20 Sat |  | 470 | SV-2605-002-01 | EX-PO-007999 |  | Houzs Century | KL | SV-2605-002 | 2006(A)-(K) | 2006(A)-(K) -HB 26" | 6FT | 1 | PC151-14 | 14 | 12 |  | 1 |  |  |  | 2026-07-04 | [5 empty] | WAITING
2026-06-20 Sat |  | 471 | CO-2605-008-01 |  |  | Houzs Century | KL |  | 5530-2A(LHF) | 5530-2A(LHF) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-20 Sat |  | 472 | CO-2605-008-02 |  |  | Houzs Century | KL |  | 5530-L(RHF) | 5530-L(RHF) | 30 | 1 | PC151-01 |  |  | 6 | 1 |  |  |  | 2026-06-02 | [5 empty] | WAITING
2026-06-20 Sat |  | 473 | SO-2605-184-03 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-1A(RHF) | 5536-1A(RHF) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-23 | [5 empty] | WAITING
2026-06-20 Sat |  | 474 | SO-2605-184-01 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-2A(LHF) | 5536-2A(LHF) | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-23 | [5 empty] | WAITING
2026-06-20 Sat |  | 475 | SO-2605-184-02 | PO-008867 | ZNT5364 | Houzs Century | KL | SO-2605-184 | 5536-CNR | 5536-CNR | 30 | 1 | BO315-5 | 0 | 0 | 1 | 1 |  |  |  | 2026-06-23 | [5 empty] | WAITING