## Summary & Notes
各部门工序 Due Date 排程 (Process Due-Date Plan, by WIP)
生成 2026-06-01 6/1 放假不排工,计划从 6/2 开始。只读,没有改动系统任何东西。
【这本表怎么看】
· Process Due Dates:一张单一行,横看 8 个部门各自要哪天做好(done=已做完,-=不需要)。
· 后面 8 页 = 8 个部门各一页(1-Cut … 8-Pack):每页列出该部门要做的 WIP 件,
按工序 due date 先后排好。最上面的先做。同一天的用底色分组。
【WIP 件 = 什么】
一张单会拆成几个 WIP 件分开做:床架=DIVAN+HEADBOARD;沙发=BASE+坐垫+扶手…
每页的『WIP Item』栏就是现场实际在做的那一件(已经做完的件不再列出)。
【due date 怎么算出来的】
按近 30 天每天真实做得出来的量,一个部门接一个部门算:上一道工序哪天做完,下一道
才那天开工;每天只能做到产能上限;周日 + 6/1 放假不排。算出来那天 = 该工序最迟做好日。
【状态 Status】
OVERDUE 已逾期 / LATE 赶不上 Customer DD / AT-RISK 破内部缓冲 Hookka DD / ON-TIME 准时 / ON-HOLD 暂停。
【结果一览】
共 327 张活跃单。 OVERDUE=61 LATE=202 AT-RISK=24 ON-TIME=37 ON-HOLD=3
【各部门:要做的 WIP 件数 / 产能(近30天实际平均)】
裁布 Fabric Cut 待做 114 件 (WIP) 产能 2321 分钟/天 ≈ 23.5 件/天
车缝 Fabric Sew 待做 421 件 (WIP) 产能 3114 分钟/天 ≈ 63.0 件/天
锯木 Wood Cut 待做 483 件 (WIP) 产能 1226 分钟/天 ≈ 61.2 件/天
粘棉 Foam 待做 470 件 (WIP) 产能 818 分钟/天 ≈ 32.8 件/天
组框 Framing 待做 580 件 (WIP) 产能 1706 分钟/天 ≈ 60.8 件/天
打底 Webbing 待做 630 件 (WIP) 产能 960 分钟/天 ≈ 57.5 件/天
包面 Upholstery 待做 703 件 (WIP) 产能 1622 分钟/天 ≈ 58.3 件/天
包装 Packing 待做 475 件 (WIP) 产能 1893 分钟/天 ≈ 79.5 件/天
瓶颈:FOAM 粘棉 818 分钟/天最低,整条线卡在这里。要把 due date 提前,先在这里加人。
注:这只是 planning 表,还没写进 ERP。你看过、确认排法 OK,我再帮你把 due date 写进系统。

## Process Due Dates
SO / PO | Customer | Model | Type | Cut | Sew | Wood | Foam | Frame | Web | Uphol | Pack | Ready | Customer DD | Hookka DD | Status
SO-2605-186-01 | Houzs Century | 1013-(SS) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-26 | 2026-05-24 | OVERDUE
SO-2605-187-01 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2605-162-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-02 | done | done | 06-02 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-161-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-160-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-124-01 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-05-29 | 2026-05-27 | OVERDUE
SO-2605-098-04 | Houzs Century | 2008(A)-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-29 | 2026-05-27 | OVERDUE
SO-2605-098-03 | Houzs Century | 2008(A)-(Q) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-29 | 2026-05-27 | OVERDUE
SO-2605-102-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2605-023-01 | Houzs Century | 1007-(K) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-18 | 2026-05-16 | OVERDUE
SO-2605-009-01 | Houzs Century | 1007-(K) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-22 | 2026-05-20 | OVERDUE
SO-2604-321-03 | Houzs Century | 1023(HF)(W)-(SS) | BEDFRAME | done | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 2026-05-21 | 2026-05-19 | OVERDUE
SO-2604-210-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | done | done | - | - | - | - | - | 06-02 | 06-02 | 2026-05-04 | 2026-05-02 | OVERDUE
SO-2604-092-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | done | done | - | - | - | - | - | 06-02 | 06-02 | 2026-04-29 | 2026-04-28 | OVERDUE
SO-2605-171-01 | Houzs Century | 2011(A)-(K) | BEDFRAME | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-010-02 | Houzs Century | 2041(A)-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2604-265-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | done | done | 06-02 | done | done | 06-03 | 06-03 | 06-03 | 2026-05-16 | 2026-05-14 | OVERDUE
SO-2604-086-02 | Houzs Century | 5530-L(LHF) | SOFA | - | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-11 | 2026-05-10 | OVERDUE
SO-2604-086-01 | Houzs Century | 5530-2A(RHF) | SOFA | done | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-11 | 2026-05-10 | OVERDUE
SO-2604-276-03 | Houzs Century | 2041(A)-(SS) | BEDFRAME | done | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-13 | 2026-05-11 | OVERDUE
SO-2605-104-06 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-072-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-02 | 06-02 | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-072-01 | Carress | 5531-L(LHF) | SOFA | done | 06-02 | 06-02 | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-05 | Houzs Century | 5530-1NA | SOFA | - | done | done | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-04 | Houzs Century | LONG PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | - | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-03 | Houzs Century | LONG PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | done | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-063-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | done | done | done | done | 06-04 | 06-04 | 06-04 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-050-02 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | done | 06-02 | done | done | 06-04 | 06-04 | 06-04 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2605-050-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | done | 06-02 | done | 06-03 | 06-04 | 06-04 | 06-04 | 2026-05-30 | 2026-05-28 | OVERDUE
SO-2604-324-04 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | - | 06-04 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2604-324-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2604-345-03 | Carress | 5531-2S | SOFA | - | 06-02 | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-05-27 | 2026-05-25 | OVERDUE
SO-2604-265-01 | Houzs Century | 5530-L(LHF) | SOFA | done | done | done | 06-02 | done | done | 06-04 | 06-04 | 06-04 | 2026-05-16 | 2026-05-14 | OVERDUE
SO-2604-083-05 | Carress | LONG PILLOW | ACCESSORY | done | 06-04 | - | - | - | - | - | - | 06-04 | 2026-04-15 | 2026-04-14 | OVERDUE
SO-2604-083-04 | Carress | LONG PILLOW | ACCESSORY | done | 06-04 | - | - | - | - | - | 06-02 | 06-04 | 2026-04-15 | 2026-04-14 | OVERDUE
SO-2605-222-04 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-222-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-222-02 | Houzs Century | 5535-L(RHF) | SOFA | - | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-222-01 | Houzs Century | 5535-2A(LHF) | SOFA | done | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-30 | 2026-05-29 | OVERDUE
SO-2605-221-03 | Houzs Century | 5540-1A(RHF) | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-221-02 | Houzs Century | 5540-1NA | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-05 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-220-01 | Houzs Century | 5536-2S | SOFA | done | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-27 | 2026-05-26 | OVERDUE
SO-2605-104-05 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-04 | Houzs Century | SQUARE PILLOW | ACCESSORY | 06-03 | 06-05 | - | - | - | - | - | 06-02 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-03 | Houzs Century | 5535-L(RHF) | SOFA | - | 06-02 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-02 | Houzs Century | 5535-1NA | SOFA | - | 06-02 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-104-01 | Houzs Century | 5535-1A(LHF) | SOFA | 06-02 | 06-02 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-108-01 | Houzs Century | 5540-2S | SOFA | done | done | done | 06-05 | done | done | done | done | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-078-03 | Houzs Century | 5540-2A(RHF) | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-078-02 | Houzs Century | 5540-CSL | SOFA | - | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2605-078-01 | Houzs Century | 5540-L(LHF) | SOFA | done | 06-03 | 06-03 | 06-05 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-24 | OVERDUE
SO-2604-324-02 | Houzs Century | 5540-1A(RHF) | SOFA | - | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2604-324-01 | Houzs Century | 5540-2A(LHF) | SOFA | 06-02 | 06-03 | 06-02 | 06-04 | 06-03 | 06-04 | 06-05 | 06-05 | 06-05 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2603-207-02 | Houzs Century | 5537-1A(RHF) | SOFA | - | done | done | done | done | done | 06-05 | 06-05 | 06-05 | 2026-05-04 | 2026-05-03 | OVERDUE
SO-2603-207-01 | Houzs Century | 5537-1A(LHF) | SOFA | done | done | done | done | done | done | 06-05 | 06-05 | 06-05 | 2026-05-04 | 2026-05-03 | OVERDUE
SO-2605-221-01 | Houzs Century | 5540-1A(LHF) | SOFA | 06-02 | 06-03 | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-064-02 | Houzs Century | 5540-2A(RHF) | SOFA | - | done | done | done | done | done | 06-06 | 06-06 | 06-06 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-064-01 | Houzs Century | 5540-1A(LHF) | SOFA | done | done | done | done | done | done | 06-06 | 06-06 | 06-06 | 2026-05-28 | 2026-05-27 | OVERDUE
SO-2605-011-01 | Houzs Century | DIVAN-(K) | BEDFRAME | done | done | done | - | done | done | 06-06 | 06-06 | 06-06 | 2026-05-18 | 2026-05-16 | OVERDUE
SO-2604-300-01 | Houzs Century | DIVAN-(Q) | BEDFRAME | done | done | done | - | done | done | 06-06 | done | 06-06 | 2026-05-25 | 2026-05-23 | OVERDUE
SO-2605-205-02 | Houzs Century | 1007-(S) | BEDFRAME | done | done | done | 06-02 | done | done | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-205-01 | Houzs Century | 1007-(S) | BEDFRAME | done | done | done | 06-02 | done | done | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-208-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-212-01 | Houzs Century | 1003(A)-(K) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-213-01 | Houzs Century | 1013-(K) | BEDFRAME | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-188-01 | Houzs Century | 1013-(SS) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-167-01 | The Conts | 1007-(Q) | BEDFRAME | done | done | done | 06-02 | done | done | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-166-02 | The Conts | 1013-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-166-01 | The Conts | 1013-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-157-01 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-11 | Houzs Century | 1041-(Q) | BEDFRAME | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-08 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-07 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-06 | Houzs Century | 2003-(K) | BEDFRAME | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-141-01 | Carress | 1013-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-251-01 | Houzs Century | 2038(A)(HF)(W)-(Q) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-233-01 | Houzs Century | 2038(A)(HF)(W)-(K) | BEDFRAME | done | done | done | 06-02 | done | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-02 | 2026-05-31 | LATE
SO-2605-234-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-02 | 06-03 | 06-03 | 06-03 | 2026-06-02 | 2026-05-31 | LATE
SO-2605-204-03 | Houzs Century | 2038(A)-(SS) | BEDFRAME | done | done | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-204-02 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-02 | 06-02 | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-10 | Houzs Century | 2009(A)-(K) | BEDFRAME | done | done | done | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-05 | Houzs Century | 2041(A)-(Q) | BEDFRAME | done | 06-02 | 06-02 | 06-02 | 06-02 | 06-03 | 06-03 | 06-03 | 06-03 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-109-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | done | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-109-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | done | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-079-02 | Carress | 5531-L(RHF) | SOFA | - | 06-02 | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-079-01 | Carress | 5531-2A(LHF) | SOFA | 06-02 | 06-02 | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-31 | LATE
SO-2604-327-02 | Carress | 5531-2A(RHF) | SOFA | - | done | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-30 | LATE
SO-2604-327-01 | Carress | 5531-L(LHF) | SOFA | done | done | 06-02 | 06-03 | 06-02 | 06-03 | 06-04 | 06-04 | 06-04 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-067-02 | Carress | 5531-2A(RHF) | SOFA | - | done | done | 06-03 | done | 06-03 | 06-05 | 06-05 | 06-05 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-067-01 | Carress | 5531-L(LHF) | SOFA | done | done | done | 06-04 | done | 06-03 | 06-05 | 06-05 | 06-05 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-176-01 | The Conts | 6112-2S | SOFA | done | done | 06-03 | 06-06 | 06-04 | 06-06 | 06-06 | 06-06 | 06-06 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-131-04 | Houzs Century | DIVAN-(K) | BEDFRAME | done | done | done | - | 06-04 | 06-06 | done | done | 06-06 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-132-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | done | done | done | done | done | 06-06 | 06-06 | 06-06 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-105-02 | Houzs Century | 5540-1A(RHF) | SOFA | - | done | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-105-01 | Houzs Century | 5540-1A(LHF) | SOFA | 06-02 | done | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-01 | 2026-05-31 | LATE
SO-2605-248-01 | Houzs Century | 1007-(K) | BEDFRAME | done | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-249-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-255-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-256-01 | Houzs Century | 1007-(K) | BEDFRAME | done | done | 06-04 | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-257-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-257-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-207-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | done | done | 06-08 | 06-08 | 06-08 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-195-01 | Carress | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-185-04 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-185-03 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | 06-05 | 06-08 | 06-08 | 06-08 | 06-08 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-175-01 | The Conts | 6112-2S | SOFA | done | done | 06-03 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-174-01 | The Conts | 6112-2S | SOFA | done | done | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-173-01 | The Conts | 6112-2S | SOFA | done | done | done | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-154-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-08 | done | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-03 | 2026-06-01 | LATE
SO-2604-307-01 | The Conts | 6112-2S | SOFA | done | done | done | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-01 | 2026-05-30 | LATE
SO-2605-299-03 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-02 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-299-02 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-02 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-299-01 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-02 | 06-06 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-276-01 | Houzs Century | 1013-(K) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-277-01 | Houzs Century | 1013-(SS) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-278-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-285-02 | Houzs Century | 1013-(SS) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-285-01 | Houzs Century | 1013-(SS) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-262-02 | Houzs Century | 1013-(SS) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-262-01 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-264-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-254-02 | Houzs Century | 1013-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-254-01 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-203-01 | Houzs Century | 1007-(K) | BEDFRAME | done | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-214-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-215-04 | Houzs Century | 1013-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-215-03 | Houzs Century | 1013-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-215-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-193-01 | Carress | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | done | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-185-02 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-185-01 | Houzs Century | 1007-(S) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-192-04 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-153-02 | Houzs Century | 1013-(Q) | BEDFRAME | done | done | done | 06-09 | done | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-096-03 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-096-02 | Houzs Century | 1013-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-096-01 | Houzs Century | 1013-(SK) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-070-02 | Carress | 1013-(SS) | BEDFRAME | 06-03 | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-070-01 | Carress | 1013-(K) | BEDFRAME | done | done | done | 06-09 | 06-05 | 06-08 | 06-09 | 06-09 | 06-09 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-300-02 | Houzs Century | 1030-(Q) | BEDFRAME | done | 06-05 | 06-05 | 06-02 | 06-06 | 06-08 | 06-10 | 06-10 | 06-10 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-286-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | 06-05 | 06-05 | 06-02 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-263-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-258-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-238-03 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-238-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-238-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-209-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-209-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | done | done | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-210-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | done | done | 06-02 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-192-03 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-03 | 06-05 | 06-05 | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-192-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-192-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-099-02 | Houzs Century | 2008(A)-(Q) | BEDFRAME | done | done | done | 06-09 | 06-06 | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-099-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-09 | done | 06-09 | 06-10 | 06-10 | 06-10 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-051-03 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | done | 06-10 | done | 06-10 | done | done | 06-10 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-051-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | done | 06-10 | done | 06-10 | done | done | 06-10 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-295-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-09 | 06-11 | 06-11 | 06-11 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-298-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-279-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-280-02 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-280-01 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-08 | 2026-06-06 | LATE
SO-2605-239-01 | Carress | 2009(A)-(Q) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-04 | 2026-06-02 | LATE
SO-2605-241-02 | Houzs Century | 2009(A)-(Q) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-09 | 2026-06-07 | LATE
SO-2605-241-01 | Houzs Century | 2009(A)-(K) | BEDFRAME | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-09 | 2026-06-07 | LATE
SO-2605-247-01 | Houzs Century | 2009(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-209-04 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | done | done | done | done | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-209-03 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | done | done | 06-10 | done | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-215-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-09 | 06-11 | 06-11 | 06-11 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-153-01 | Houzs Century | 2038(A)-(K) | BEDFRAME | done | done | done | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-140-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | done | done | done | 06-10 | done | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-05 | 2026-06-03 | LATE
SO-2604-293-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-11 | 06-11 | 06-11 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-183-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-183-01 | Carress | 5531-1A(LHF) | SOFA | done | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-197-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-06 | 06-06 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-197-01 | Carress | 5531-1A(LHF) | SOFA | done | 06-08 | 06-06 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-240-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-06 | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-240-01 | Houzs Century | 5530-L(LHF) | SOFA | 06-04 | 06-06 | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-194-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-194-01 | Carress | 5531-L(LHF) | SOFA | 06-04 | 06-08 | 06-06 | 06-12 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-196-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-130-03 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-130-02 | Houzs Century | 5530-1NA | SOFA | - | done | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-130-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | 06-05 | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-080-04 | Houzs Century | 5530-STOOL | SOFA | - | 06-06 | done | 06-10 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-080-03 | Houzs Century | 5530-L(RHF) | SOFA | - | 06-06 | done | 06-10 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-080-02 | Houzs Century | 5530-2NA | SOFA | - | 06-06 | done | 06-11 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2605-080-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | 06-06 | done | 06-11 | 06-09 | 06-11 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-02 | LATE
SO-2604-293-01 | Houzs Century | 5530-L(LHF) | SOFA | 06-04 | 06-06 | 06-05 | 06-10 | 06-08 | 06-10 | 06-12 | 06-12 | 06-12 | 2026-06-03 | 2026-06-01 | LATE
SO-2605-296-03 | Houzs Century | DIVAN-(S) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-296-02 | Houzs Century | DIVAN-(Q) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-296-01 | Houzs Century | DIVAN-(Q) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-297-02 | Houzs Century | 1007-(Q) | BEDFRAME | 06-05 | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-300-01 | Houzs Century | DIVAN-(K) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-06 | 2026-06-04 | LATE
SO-2605-275-02 | Houzs Century | 1007-(Q) | BEDFRAME | 06-05 | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-275-01 | Houzs Century | 1007-(K) | BEDFRAME | 06-05 | 06-09 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-282-02 | Houzs Century | 1007-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-283-01 | Houzs Century | DIVAN-(SS) | BEDFRAME | done | 06-08 | 06-06 | - | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-05 | 2026-06-03 | LATE
SO-2605-269-02 | The Conts | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-259-02 | Carress | 1007-(Q) | BEDFRAME | done | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-243-04 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-243-03 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-243-02 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-246-01 | Houzs Century | 1007-(Q) | BEDFRAME | done | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-196-01 | Carress | 5531-L(LHF) | SOFA | 06-05 | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-123-01 | Houzs Century | 1003(A)-(SK) | BEDFRAME | done | 06-08 | 06-06 | 06-13 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-077-04 | Houzs Century | 5540-L(RHF) | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-077-03 | Houzs Century | 5540-CSL | SOFA | - | 06-08 | 06-06 | 06-12 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-077-02 | Houzs Century | 5540-1NA | SOFA | - | 06-08 | 06-06 | 06-13 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-077-01 | Houzs Century | 5540-1A(LHF) | SOFA | 06-05 | 06-08 | 06-06 | 06-13 | 06-09 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-02 | 2026-06-01 | LATE
SO-2605-071-02 | Carress | 5531-L(RHF) | SOFA | - | done | done | 06-12 | 06-09 | 06-12 | 06-13 | done | 06-13 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-071-01 | Carress | 5531-2A(LHF) | SOFA | done | done | done | 06-12 | 06-09 | 06-12 | 06-13 | done | 06-13 | 2026-06-08 | 2026-06-07 | LATE
SO-2605-294-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | 06-05 | 06-09 | 06-09 | 06-02 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-297-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | 06-05 | 06-09 | 06-09 | 06-02 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-288-02 | Houzs Century | 1052-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-15 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-282-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-15 | 06-15 | 06-15 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-269-01 | The Conts | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-261-03 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | 06-09 | 06-09 | 06-02 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-261-02 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-261-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-244-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-245-01 | Houzs Century | 1013-(S) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-229-02 | Houzs Century | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-229-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-15 | 06-15 | 06-15 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-111-02 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-111-01 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-11 | 2026-06-09 | LATE
SO-2605-292-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-15 | 2026-06-13 | LATE
SO-2605-288-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-10 | 2026-06-08 | LATE
SV-2605-003-01 | Houzs Century | 5530-L(RHF) | SOFA | 06-06 | 06-10 | 06-10 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-09 | 2026-06-08 | LATE
SO-2605-242-02 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-242-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-243-01 | Houzs Century | 2009(A)-(K) | BEDFRAME | done | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-252-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-15 | 2026-06-13 | LATE
SO-2605-235-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-06 | 06-10 | 06-10 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-200-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-202-02 | Houzs Century | 2033(HF)(W)-(SS) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-202-01 | Houzs Century | 2033(HF)(W)-(K) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-13 | 2026-06-11 | LATE
SO-2605-123-02 | Houzs Century | 2038(A)-(SS) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-103-03 | Houzs Century | 5536-1A(RHF) | SOFA | - | done | 06-10 | 06-16 | 06-12 | 06-16 | done | done | 06-16 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-103-02 | Houzs Century | 5536-CNR | SOFA | - | done | done | 06-16 | done | 06-16 | done | done | 06-16 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-076-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-10 | 06-10 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-11 | LATE
SO-2604-281-01 | Houzs Century | 2008(A)-(K) | BEDFRAME | 06-06 | 06-09 | 06-09 | 06-15 | 06-11 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-270-02 | The Conts | 5535-L(RHF) | SOFA | - | 06-10 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-270-01 | The Conts | 5535-2A(LHF) | SOFA | 06-06 | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-10 | 2026-06-09 | LATE
SO-2605-265-02 | Houzs Century | DIVAN-(S) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-265-01 | Houzs Century | DIVAN-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-259-01 | Carress | DIVAN-(K) | BEDFRAME | done | 06-11 | 06-10 | - | 06-13 | done | 06-17 | 06-17 | 06-17 | 2026-06-10 | 2026-06-08 | LATE
SO-2605-237-02 | Carress | 5531-2A(RHF) | SOFA | - | done | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-13 | 2026-06-12 | LATE
SO-2605-237-01 | Carress | 5531-L(LHF) | SOFA | done | done | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-13 | 2026-06-12 | LATE
SO-2605-223-04 | Houzs Century | 5536-2S | SOFA | - | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-223-03 | Houzs Century | 5536-2A(RHF) | SOFA | - | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-223-02 | Houzs Century | 5536-CNR | SOFA | - | 06-11 | 06-10 | 06-16 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-223-01 | Houzs Century | 5536-1A(LHF) | SOFA | 06-08 | 06-11 | 06-10 | 06-16 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-15 | 2026-06-14 | LATE
SO-2605-200-03 | Houzs Century | DIVAN-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-200-02 | Houzs Century | DIVAN-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-206-01 | Houzs Century | DIVAN-(K) | BEDFRAME | 06-08 | 06-11 | 06-10 | - | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-10 | LATE
SO-2605-076-01 | Carress | 5531-L(LHF) | SOFA | 06-06 | 06-10 | 06-10 | 06-15 | 06-12 | 06-16 | 06-17 | 06-17 | 06-17 | 2026-06-12 | 2026-06-11 | LATE
SO-2605-273-02 | Houzs Century | 5535-2A(RHF) | SOFA | - | 06-12 | 06-11 | 06-17 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-273-01 | Houzs Century | 5535-L(LHF) | SOFA | 06-09 | 06-12 | 06-11 | 06-17 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-260-01 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-17 | 2026-06-15 | LATE
SO-2605-236-02 | Carress | 5531-L(RHF) | SOFA | - | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-17 | 2026-06-16 | LATE
SO-2605-236-01 | Carress | 5531-2A(LHF) | SOFA | 06-08 | 06-12 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-17 | 2026-06-16 | LATE
SO-2605-225-02 | Houzs Century | 5536-1A(RHF) | SOFA | - | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-225-01 | Houzs Century | 5536-1A(LHF) | SOFA | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-16 | 2026-06-15 | LATE
SO-2605-227-01 | Houzs Century | 1013-(K) | BEDFRAME | done | done | done | done | done | 06-02 | done | done | 06-02 | 2026-06-02 | 2026-05-31 | AT-RISK
SO-2605-234-03 | Houzs Century | 1007-(Q) | BEDFRAME | done | done | done | 06-02 | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-02 | 2026-05-31 | AT-RISK
SO-2605-234-02 | Houzs Century | 1005-(Q) | BEDFRAME | done | done | done | done | done | 06-02 | 06-02 | 06-02 | 06-02 | 2026-06-02 | 2026-05-31 | AT-RISK
SO-2605-181-01 | The Conts | 6112-2S | SOFA | done | 06-03 | 06-03 | 06-05 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-180-01 | The Conts | 6112-2S | SOFA | done | 06-03 | 06-03 | 06-06 | 06-03 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-179-01 | The Conts | 6112-2S | SOFA | 06-02 | 06-04 | 06-03 | 06-06 | 06-04 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-178-01 | The Conts | 6112-2S | SOFA | 06-03 | 06-04 | 06-03 | 06-06 | 06-04 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-177-01 | The Conts | 6112-2S | SOFA | 06-03 | 06-04 | 06-03 | 06-06 | 06-04 | 06-05 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-05-30 | AT-RISK
SO-2605-291-01 | Houzs Century | 1003(A)-(K) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-08 | 2026-06-06 | AT-RISK
SO-2605-226-02 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-08 | 2026-06-06 | AT-RISK
SO-2605-226-01 | Houzs Century | 1003(A)-(Q) | BEDFRAME | done | 06-05 | 06-04 | 06-08 | 06-04 | 06-06 | 06-08 | 06-08 | 06-08 | 2026-06-08 | 2026-06-06 | AT-RISK
SO-2605-293-02 | Houzs Century | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-293-01 | Houzs Century | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-271-02 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-271-01 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-274-01 | Houzs Century | 1023-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-15 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-16 | 2026-06-14 | AT-RISK
SO-2605-216-04 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-216-03 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-216-02 | Carress | 1013-(Q) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-216-01 | Carress | 1013-(K) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-11 | 06-13 | 06-15 | 06-15 | 06-15 | 2026-06-15 | 2026-06-13 | AT-RISK
SO-2605-211-01 | Houzs Century | 2009(A)-(SK) | BEDFRAME | 06-06 | 06-10 | 06-09 | 06-15 | 06-12 | 06-15 | 06-16 | 06-16 | 06-16 | 2026-06-16 | 2026-06-14 | AT-RISK
SO-2605-228-01 | Houzs Century | 1030-(K) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-02 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-17 | 2026-06-15 | AT-RISK
SO-2605-069-01 | Carress | 1013-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | 06-16 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-18 | 2026-06-16 | AT-RISK
SO-2605-191-01 | Houzs Century | 2006(A)-(Q) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-02 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-17 | AT-RISK
SO-2604-088-03 | Houzs Century | SQUARE PILLOW | ACCESSORY | done | done | - | - | - | - | - | 06-02 | 06-02 | 2026-05-04 | 2026-05-03 | ON-HOLD
SO-2604-088-02 | Houzs Century | 5530-1A(RHF) | SOFA | - | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-04 | 2026-05-03 | ON-HOLD
SO-2604-088-01 | Houzs Century | 5530-1A(LHF) | SOFA | done | done | done | done | done | done | 06-03 | 06-03 | 06-03 | 2026-05-04 | 2026-05-03 | ON-HOLD
SO-2605-291-02 | Houzs Century | 1005-(Q) | BEDFRAME | 06-03 | 06-05 | 06-04 | 06-02 | 06-04 | 06-06 | 06-06 | 06-06 | 06-06 | 2026-06-08 | 2026-06-06 | ON-TIME
SO-2605-292-03 | Houzs Century | 1007-(SS) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-15 | 2026-06-13 | ON-TIME
SO-2605-292-02 | Houzs Century | 1007-(SS) | BEDFRAME | 06-05 | 06-09 | 06-08 | 06-13 | 06-10 | 06-13 | 06-13 | 06-13 | 06-13 | 2026-06-15 | 2026-06-13 | ON-TIME
SO-2605-281-01 | Houzs Century | 1005-(Q) | BEDFRAME | 06-05 | 06-08 | 06-06 | 06-02 | 06-10 | 06-12 | 06-13 | 06-13 | 06-13 | 2026-06-15 | 2026-06-13 | ON-TIME
SO-2605-289-01 | Carress | 1013-(Q) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-22 | 2026-06-20 | ON-TIME
SO-2605-284-01 | Houzs Century | 1007-(Q) | BEDFRAME | 06-08 | 06-11 | 06-10 | 06-16 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-19 | 2026-06-17 | ON-TIME
SO-2605-190-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | 06-08 | 06-11 | 06-11 | 06-02 | 06-13 | 06-17 | 06-17 | 06-17 | 06-17 | 2026-06-19 | 2026-06-17 | ON-TIME
SO-2605-303-02 | Carress | 5535-1A(RHF) | SOFA | - | 06-12 | 06-11 | 06-17 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-303-01 | Carress | 5535-2A(LHF) | SOFA | 06-09 | 06-12 | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-290-03 | Houzs Century | 5530-STOOL | SOFA | - | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-18 | ON-TIME
SO-2605-290-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-18 | ON-TIME
SO-2605-290-01 | Houzs Century | 5530-1A(LHF) | SOFA | 06-08 | 06-11 | 06-11 | 06-17 | 06-13 | 06-17 | 06-18 | 06-18 | 06-18 | 2026-06-19 | 2026-06-18 | ON-TIME
SO-2605-106-06 | Houzs Century | 5535-1S | SOFA | - | done | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-05 | Houzs Century | 5535-1A(RHF) | SOFA | - | done | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-04 | Houzs Century | 5535-1A(LHF) | SOFA | - | done | 06-11 | 06-18 | 06-13 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-03 | Houzs Century | 5535-1A(RHF) | SOFA | - | done | 06-11 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-02 | Houzs Century | 5535-1NA | SOFA | - | done | 06-11 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-106-01 | Houzs Century | 5535-1A(LHF) | SOFA | done | done | 06-11 | 06-18 | 06-15 | 06-18 | 06-18 | 06-18 | 06-18 | 2026-06-22 | 2026-06-21 | ON-TIME
SO-2605-301-01 | Carress | 5531-2S | SOFA | 06-09 | 06-13 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-29 | 2026-06-28 | ON-TIME
SO-2605-302-01 | Carress | 1007-(K) | BEDFRAME | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-29 | 2026-06-27 | ON-TIME
SO-2605-231-02 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-23 | ON-TIME
SO-2605-231-01 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 06-09 | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-23 | ON-TIME
SO-2605-224-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-26 | 2026-06-25 | ON-TIME
SO-2605-224-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-26 | 2026-06-25 | ON-TIME
SO-2605-198-02 | Houzs Century | 5530-2A(RHF) | SOFA | - | 06-12 | 06-12 | 06-18 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-198-01 | Houzs Century | 5530-L(LHF) | SOFA | done | 06-12 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-199-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-199-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-182-02 | Carress | 5531-2A(RHF) | SOFA | - | 06-12 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-24 | ON-TIME
SO-2605-182-01 | Carress | 5531-L(LHF) | SOFA | 06-09 | 06-13 | 06-12 | 06-19 | 06-15 | 06-19 | 06-19 | 06-19 | 06-19 | 2026-06-25 | 2026-06-24 | ON-TIME
SO-2605-189-01 | Houzs Century | 1003(A)-(K) | BEDFRAME | done | 06-12 | 06-12 | 06-18 | 06-15 | 06-18 | 06-19 | 06-19 | 06-19 | 2026-06-24 | 2026-06-22 | ON-TIME
SV-2605-002-01 | Houzs Century | 2006(A)-(K) | BEDFRAME | done | 06-13 | 06-12 | 06-02 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-07-08 | 2026-07-06 | ON-TIME
CO-2605-008-02 | Houzs Century | 5530-L(RHF) | SOFA | - | done | 06-13 | 06-20 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 |  |  | ON-TIME
CO-2605-008-01 | Houzs Century | 5530-2A(LHF) | SOFA | done | done | 06-13 | 06-20 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 |  |  | ON-TIME
SO-2605-184-03 | Houzs Century | 5536-1A(RHF) | SOFA | - | 06-13 | 06-12 | 06-20 | 06-15 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-184-02 | Houzs Century | 5536-CNR | SOFA | - | 06-13 | 06-12 | 06-20 | 06-15 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-06-24 | 2026-06-23 | ON-TIME
SO-2605-184-01 | Houzs Century | 5536-2A(LHF) | SOFA | 06-09 | 06-13 | 06-12 | 06-20 | 06-16 | 06-20 | 06-20 | 06-20 | 06-20 | 2026-06-24 | 2026-06-23 | ON-TIME

## 1-Cut
裁布 Fabric Cut — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ KS-18 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (19") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF)+L(RHF) ¦ (24) ¦ M2402-13 ¦ (FC) | SOFA | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF)+1NA+L(RHF) ¦ (32) ¦ BO315-1 ¦ (FC) | SOFA | 3 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF)+1A(RHF) ¦ BO315-31 ¦ (FC) | SOFA | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF)+1NA+1A(RHF) ¦ (32) ¦ AM275-1 ¦ (FC) | SOFA | 3 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF)+1A(RHF) ¦ (28) ¦ BO315-22 ¦ (FC) | SOFA | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-179-01 | 6112-2S | 6112-2S ¦ (30) ¦ PC151-01 ¦ (FC) | SOFA | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-291-02 | 1005-(Q) | 1005-(Q) ¦ (5FT) ¦ (22") ¦ (DV 4") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-03 Wed | SO-2605-276-01 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-12 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-03 Wed | SO-2605-096-02 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-03 Wed | SO-2605-096-03 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-03 Wed | SO-2605-214-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ KS-14 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-03 Wed | SO-2605-264-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-04 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-03 Wed | SO-2605-278-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (23") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-03 Wed | SO-2605-096-01 | 1013-(SK) | 1013-(SK) ¦ (200CMX200CM) ¦ (21") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-03 Wed | SO-2605-070-02 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-18 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-08 | LATE
2026-06-03 Wed | SO-2605-277-01 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-03 Wed | SO-2605-285-01 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-09 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-03 Wed | SO-2605-285-02 | 1013-(SS) | 1013-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-11 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-03 Wed | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 8") ¦ PC151-10 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-03 Wed | SO-2605-177-01 | 6112-2S | 6112-2S ¦ (30) ¦ PC151-01 ¦ (FC) | SOFA | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-178-01 | 6112-2S | 6112-2S ¦ (30) ¦ PC151-01 ¦ (FC) | SOFA | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-063-03 | LONG PILLOW | LONG PILLOW ¦ (12" X 28") ¦ BO315-31 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-063-04 | LONG PILLOW | LONG PILLOW ¦ (12" X 28") ¦ BO315-31 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-03 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ BO315-22 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-04 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ BO315-22 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-104-04 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-3 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-05 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-3 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-06 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-3 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-222-03 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-7 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-04 | SQUARE PILLOW | SQUARE PILLOW ¦ (16" X 16") ¦ CH141-5 ¦ (FC) | ACCESSORY | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (26") ¦ (DV 8") ¦ PC151-04 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-06 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-04 Thu | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) ¦ (5FT) ¦ (20") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-04 Thu | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-04 Thu | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) ¦ (5FT) ¦ (26") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) ¦ (5FT) ¦ (26") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF)+2A(RHF) ¦ (28) ¦ CH141-12 ¦ (FC) | SOFA | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-04 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF)+2A(RHF) ¦ (28) ¦ BO315-22 ¦ (FC) | SOFA | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (28) ¦ GARFIELD - 3 TUNDORA ¦ (FC) | SOFA | 2 | Carress | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-281-01 | 1005-(Q) | 1005-(Q) ¦ (5FT) ¦ (23") ¦ (DV 10") ¦ PC151-03 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-05 Fri | SO-2605-275-01 | 1007-(K) | 1007-(K) ¦ (6FT) ¦ (23") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-05 Fri | SO-2605-275-02 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (19") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-05 Fri | SO-2605-282-02 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (21") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-05 Fri | SO-2605-297-02 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-05 Fri | SO-2605-292-02 | 1007-(SS) | 1007-(SS) ¦ (3.5FT) ¦ (19") ¦ (DV 8") ¦ PC151-03 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-05 Fri | SO-2605-292-03 | 1007-(SS) | 1007-(SS) ¦ (3.5FT) ¦ (19") ¦ (DV 8") ¦ PC151-03 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-05 Fri | SO-2605-111-02 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-11 | LATE
2026-06-05 Fri | SO-2605-216-01 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-14 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-216-04 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-13 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-229-02 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (24") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-05 Fri | SO-2605-271-02 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (26") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-293-02 | 1013-(K) | 1013-(K) ¦ (6FT) ¦ (21") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-111-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-11 | LATE
2026-06-05 Fri | SO-2605-216-02 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-06 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-216-03 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-244-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-05 Fri | SO-2605-261-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-05 Fri | SO-2605-261-02 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-05 Fri | SO-2605-269-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | The Conts | 2026-06-10 | LATE
2026-06-05 Fri | SO-2605-269-02 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | The Conts | 2026-06-10 | LATE
2026-06-05 Fri | SO-2605-271-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-293-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-05 Fri | SO-2605-245-01 | 1013-(S) | 1013-(S) ¦ (3FT) ¦ (16") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-05 Fri | SO-2605-274-01 | 1023-(K) | 1023-(K) ¦ (6FT) ¦ (22") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-05 Fri | SO-2605-288-02 | 1052-(Q) | 1052-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-17 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-05 Fri | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) ¦ (6FT) ¦ (23") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-05 Fri | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-05 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (28) ¦ KN390-2 ¦ (FC) | SOFA | 2 | Carress | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF)+1NA+CSL+L(RHF) ¦ (30) ¦ FABRIC HR805-10 ¦ (FC) | SOFA | 4 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-06 Sat | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-06 Sat | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (24") ¦ (DV 10") ¦ PC151-12 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-06 Sat | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (20") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-06 Sat | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (21") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) ¦ (6FT) ¦ (19") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-06 Sat | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) ¦ (200CMX200CM) ¦ (26") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-06 Sat | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) ¦ (6FT) ¦ (24") ¦ (DV 10") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-06 Sat | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) ¦ (3.5FT) ¦ (24") ¦ (DV 12") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-06 Sat | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (20") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-06 Sat | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) ¦ (3.5FT) ¦ (22") ¦ (DV 8") ¦ PC151-03 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-06 Sat | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) ¦ (28) ¦ BO315-2 ¦ (FC) | SOFA | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-06 Sat | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (24) ¦ GARFIELD-2 CHERVRON ¦ (FC) | SOFA | 2 | Carress | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF)+L(RHF) ¦ (28) ¦ PC151-01 ¦ (FC) | SOFA | 2 | The Conts | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-284-01 | 1007-(Q) | 1007-(Q) ¦ (5FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-08 Mon | SO-2605-069-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ PC151-13 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-18 | AT-RISK
2026-06-08 Mon | SO-2605-289-01 | 1013-(Q) | 1013-(Q) ¦ (5FT) ¦ (24") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-08 Mon | SO-2605-228-01 | 1030-(K) | 1030-(K) ¦ (6FT) ¦ (22") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-08 Mon | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) ¦ (6FT) ¦ (22") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-08 Mon | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) ¦ (5FT) ¦ (21") ¦ (DV 8") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-08 Mon | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-10 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-08 Mon | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF)+2A(RHF)+STOOL ¦ (28) ¦ BO315-21 ¦ (FC) | SOFA | 3 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-08 Mon | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF)+L(RHF) ¦ (28) ¦ M2402-1 ¦ (FC) | SOFA | 2 | Carress | 2026-06-17 | LATE
2026-06-08 Mon | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF)+CNR+2A(RHF)+2S ¦ (30) ¦ FABRIC HR805-90 ¦ (FC) | SOFA | 4 | Houzs Century | 2026-06-15 | LATE
2026-06-08 Mon | SO-2605-206-01 | DIVAN-(K) | DIVAN-(K) ¦ (6FT) ¦ (10") ¦ (DV 10") ¦ PC151-01 ¦ (FC) | BEDFRAME | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-200-02 | DIVAN-(Q) | DIVAN-(Q) ¦ (5FT) ¦ (8") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-200-03 | DIVAN-(Q) | DIVAN-(Q) ¦ (5FT) ¦ (8") ¦ (DV 8") ¦ PC151-01 ¦ (FC) | BEDFRAME | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-265-01 | DIVAN-(Q) | DIVAN-(Q) ¦ (5FT) ¦ (15") ¦ (DV 8") ¦ PC151-14 ¦ (FC) | BEDFRAME | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-265-02 | DIVAN-(S) | DIVAN-(S) ¦ (3FT) ¦ (15") ¦ (DV 8") ¦ PC151-14 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-09 Tue | SO-2605-302-01 | 1007-(K) | 1007-(K) ¦ (6FT) ¦ (28") ¦ (DV 8") ¦ PC151-15 ¦ (FC) | BEDFRAME | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-09 Tue | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) ¦ (5FT) ¦ (24") ¦ (DV 10") ¦ PC151-02 ¦ (FC) | BEDFRAME | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-09 Tue | SO-2605-301-01 | 5531-2S | 5531-2S ¦ (28) ¦ M2402-13 ¦ (FC) | SOFA | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-09 Tue | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF)+2A(RHF) ¦ (24) ¦ NINJA 02 ¦ (FC) | SOFA | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-09 Tue | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF)+1A(RHF) ¦ (32) ¦ KN390-3 ¦ (FC) | SOFA | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-09 Tue | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF)+2A(RHF) ¦ (32) ¦ BO315-24 ¦ (FC) | SOFA | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-09 Tue | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF)+1A(RHF) ¦ (30) ¦ NINJA 02 ¦ (FC) | SOFA | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-09 Tue | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF)+CNR+1A(RHF) ¦ (30) ¦ BO315-5 ¦ (FC) | SOFA | 3 | Houzs Century | 2026-06-24 | ON-TIME

## 2-Sew
车缝 Fabric Sew — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 10" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 8" Divan- 6FT KS-18 | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" KS-18 | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" PC151-10 | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 8" Divan- 5FT PC151-10 | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-05 | 2041(A)-(Q) | 10" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-05 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Left Arm M2402-13 | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 M2402-13 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Back Cushion 24 M2402-13 | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-072-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-14 | SOFA_CUSHION | 2 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-072-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 KN390-14 | SOFA_BASE | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-072-02 | 5531-2A(RHF) | 5531 -Right Arm KN390-14 | SOFA_ARMREST | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531 -Left Arm M2402-4 | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531 -Back Cushion 28 M2402-4 | SOFA_CUSHION | 2 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531-2S -Base 28 M2402-4 | SOFA_BASE | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531 -Right Arm M2402-4 | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2605-072-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 KN390-14 | SOFA_BASE | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-072-01 | 5531-L(LHF) | 5531 -Left Arm KN390-14 | SOFA_ARMREST | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-072-01 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-14 | SOFA_CUSHION | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531 -Right Arm M2402-13 | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531 -Back Cushion 24 M2402-13 | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) -Base 24 M2402-13 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 BO315-1 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Back Cushion 32 BO315-1 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Left Arm BO315-1 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-02 | 5535-1NA | 5535-1NA -Base 32 BO315-1 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-02 | 5535-1NA | 5535 -Back Cushion 32 BO315-1 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) -Base 32 BO315-1 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-03 | 5535-L(RHF) | 5535 -Back Cushion 32 BO315-1 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-03 | 5535-L(RHF) | 5535 -Right Arm BO315-1 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Left Arm CH141-14 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 CH141-14 | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Back Cushion 30 CH141-14 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) -Base 30 CH141-14 | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-02 | 5535-L(RHF) | 5535 -Right Arm CH141-14 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-02 | 5535-L(RHF) | 5535 -Back Cushion 30 CH141-14 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-220-01 | 5536-2S | 5536 -Back Cushion 30 BO315-23 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Left Arm AM275-1 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 AM275-1 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Back Cushion 32 AM275-1 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 BO315-22 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Back Cushion 28 BO315-22 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Right Arm BO315-22 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Back Cushion 32 AM275-1 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Right Arm AM275-1 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 AM275-1 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-02 | 5540-1NA | 5540-1NA -Base 32 AM275-1 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-02 | 5540-1NA | 5540 -Back Cushion 32 AM275-1 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Back Cushion 28 BO315-22 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Left Arm BO315-22 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 BO315-22 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Back Cushion 26 BO315-23 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Right Arm BO315-23 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 BO315-23 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-02 | 5540-CSL | 5540-CSL BO315-23 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-02 | 5540-CSL | 5540-CSL BO315-23 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540 -Back Cushion 32 BO315-23 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540 -Left Arm BO315-23 | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) -Base 32 BO315-23 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Left Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Right Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112-2S -Base 30 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Left Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Right Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112-2S -Base 30 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112-2S -Base 30 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112 -Right Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112 -Left Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112-2S -Base 30 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112 -Left Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112 -Right Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112-2S -Base 30 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112 -Left Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112 -Right Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2604-083-04 | LONG PILLOW | LONG PILLOW KN390-2 | SOFA_CUSHION | 1 | Carress | 2026-04-15 | OVERDUE
2026-06-04 Thu | SO-2604-083-05 | LONG PILLOW | LONG PILLOW KN390-2 | SOFA_CUSHION | 1 | Carress | 2026-04-15 | OVERDUE
2026-06-04 Thu | SO-2605-063-03 | LONG PILLOW | LONG PILLOW BO315-31 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-04 | LONG PILLOW | LONG PILLOW BO315-31 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-03 | SQUARE PILLOW | SQUARE PILLOW BO315-22 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-04 | SQUARE PILLOW | SQUARE PILLOW BO315-22 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-104-06 | SQUARE PILLOW | SQUARE PILLOW CH141-3 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-291-01 | 1003(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-226-01 | 1003(A)-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-226-02 | 1003(A)-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-291-02 | 1005-(Q) | 4" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-05 Fri | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-05 Fri | SO-2605-203-01 | 1007-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-248-01 | 1007-(K) | 10" Divan- 6FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-276-01 | 1013-(K) | 8" Divan- 6FT PC151-12 | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" PC151-12 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-096-02 | 1013-(Q) | 8" Divan- 5FT PC151-10 | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-03 | 1013-(Q) | 8" Divan- 5FT PC151-10 | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-214-01 | 1013-(Q) | 8" Divan- 5FT KS-14 | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" KS-14 | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-264-01 | 1013-(Q) | 10" Divan- 5FT PC151-04 | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-04 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-278-01 | 1013-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-01 | 1013-(SK) | 8" Divan- 200CMX200CM PC151-10 | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" PC151-10 | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-277-01 | 1013-(SS) | 8" Divan- 3.5FT PC151-02 | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-01 | 1013-(SS) | 8" Divan- 3.5FT PC151-09 | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" PC151-09 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-02 | 1013-(SS) | 8" Divan- 3.5FT PC151-11 | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" PC151-11 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-299-01 | 1030-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-02 | 1030-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" PC151-18 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-03 | 1030-(Q) | 8" Divan- 5FT PC151-18 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-300-02 | 1030-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-286-01 | 2006(A)-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-192-03 | 2008(A)-(K) | 8" Divan- 6FT PC151-10 | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-10 | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-104-04 | SQUARE PILLOW | SQUARE PILLOW CH141-3 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-05 | SQUARE PILLOW | SQUARE PILLOW CH141-3 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-222-03 | SQUARE PILLOW | SQUARE PILLOW CH141-7 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-222-04 | SQUARE PILLOW | SQUARE PILLOW CH141-5 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-06 Sat | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" PC151-04 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-258-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-04 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-295-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" PC151-06 | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-06 Sat | SO-2605-241-01 | 2009(A)-(K) | 8" Divan- 6FT PC151-06 | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-06 Sat | SO-2605-241-02 | 2009(A)-(Q) | 8" Divan- 5FT PC151-15 | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-06 Sat | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" PC151-15 | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-06 Sat | SO-2605-279-01 | 2038(A)-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-298-01 | 2038(A)-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-280-01 | 2041(A)-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-280-02 | 2041(A)-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-25 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 CH141-12 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 CH141-12 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Right Arm CH141-12 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 BO315-22 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-22 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Right Arm BO315-22 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-080-02 | 5530-2NA | 5530 -Back Cushion 28 BO315-25 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 CH141-12 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2604-293-01 | 5530-L(LHF) | 5530 -Back Cushion 28 CH141-12 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2604-293-01 | 5530-L(LHF) | 5530 -Left Arm CH141-12 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-240-01 | 5530-L(LHF) | 5530 -Left Arm BO315-22 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-240-01 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-22 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 BO315-22 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-080-03 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-25 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-080-04 | 5530-STOOL | 5530-STOOL BO315-25 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Right Arm M2402-4 | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-4 | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 M2402-4 | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-123-01 | 1003(A)-(SK) | 8" Divan- 200CMX200CM PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-281-01 | 1005-(Q) | 10" Divan- 5FT PC151-03 | DIVAN | 2 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-08 Mon | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" PC151-03 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-08 Mon | SO-2605-259-02 | 1007-(Q) | 8" Divan- 5FT PC151-14 | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" PC151-14 | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-275-02 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-297-02 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Left Arm M2402-18 | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 M2402-18 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-18 | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 M2402-4 | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Left Arm M2402-4 | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-4 | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 M2402-18 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-18 | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Right Arm M2402-18 | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 GARFIELD - 3 TUNDORA | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Right Arm GARFIELD - 3 TUNDORA | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-2 | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 KN390-2 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Right Arm KN390-2 | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-194-01 | 5531-L(LHF) | 5531 -Left Arm GARFIELD - 3 TUNDORA | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 GARFIELD - 3 TUNDORA | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-194-01 | 5531-L(LHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 KN390-2 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-196-01 | 5531-L(LHF) | 5531 -Left Arm KN390-2 | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-196-01 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-2 | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 FABRIC HR805-10 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 FABRIC HR805-10 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Left Arm FABRIC HR805-10 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-02 | 5540-1NA | 5540-1NA -Base 30 FABRIC HR805-10 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-02 | 5540-1NA | 5540 -Back Cushion 30 FABRIC HR805-10 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-03 | 5540-CSL | 5540-CSL FABRIC HR805-10 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-03 | 5540-CSL | 5540-CSL FABRIC HR805-10 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) -Base 30 FABRIC HR805-10 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-04 | 5540-L(RHF) | 5540 -Back Cushion 30 FABRIC HR805-10 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-077-04 | 5540-L(RHF) | 5540 -Right Arm FABRIC HR805-10 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-08 Mon | SO-2605-300-01 | DIVAN-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-296-01 | DIVAN-(Q) | 8" Divan- 5FT PC151-03 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-296-02 | DIVAN-(Q) | 8" Divan- 5FT PC151-03 | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-296-03 | DIVAN-(S) | 8" Divan- 3FT PC151-03 | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-283-01 | DIVAN-(SS) | 8" Divan- 3.5FT PC151-01 | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-275-01 | 1007-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-02 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-03 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-04 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-246-01 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-282-02 | 1007-(Q) | 10" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-292-02 | 1007-(SS) | 8" Divan- 3.5FT PC151-03 | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-09 Tue | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-09 Tue | SO-2605-292-03 | 1007-(SS) | 8" Divan- 3.5FT PC151-03 | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-09 Tue | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-09 Tue | SO-2605-111-02 | 1013-(K) | 8" Divan- 6FT PC151-17 | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" PC151-17 | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-216-01 | 1013-(K) | 8" Divan- 6FT PC151-14 | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" PC151-14 | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-216-04 | 1013-(K) | 8" Divan- 6FT PC151-13 | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" PC151-13 | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-229-02 | 1013-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-271-02 | 1013-(K) | 8" Divan- 6FT PC151-17 | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" PC151-17 | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-293-02 | 1013-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-111-01 | 1013-(Q) | 8" Divan- 5FT PC151-17 | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-17 | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-06 | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-216-02 | 1013-(Q) | 8" Divan- 5FT PC151-06 | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-216-03 | 1013-(Q) | 8" Divan- 5FT PC151-15 | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-244-01 | 1013-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-261-01 | 1013-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-261-02 | 1013-(Q) | 8" Divan- 5FT PC151-15 | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-269-01 | 1013-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-269-02 | 1013-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-271-01 | 1013-(Q) | 8" Divan- 5FT PC151-17 | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-17 | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-293-01 | 1013-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-09 Tue | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-245-01 | 1013-(S) | 8" Divan- 3FT PC151-02 | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-274-01 | 1023-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-09 Tue | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-09 Tue | SO-2605-288-02 | 1052-(Q) | 8" Divan- 5FT PC151-17 | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" PC151-17 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-261-03 | 2006(A)-(K) | 8" Divan- 6FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-294-01 | 2006(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-297-01 | 2006(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2604-281-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-200-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-229-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-282-01 | 2008(A)-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-242-01 | 2008(A)-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-12 | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-242-02 | 2008(A)-(K) | 10" Divan- 6FT PC151-12 | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-252-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-292-01 | 2008(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-243-01 | 2009(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-211-01 | 2009(A)-(SK) | 8" Divan- 200CMX200CM PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-10 Wed | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-10 Wed | SO-2605-202-01 | 2033(HF)(W)-(K) | 10" Divan- 6FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-202-02 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT PC151-02 | DIVAN | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-235-01 | 2038(A)-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-288-01 | 2038(A)-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" PC151-03 | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-123-02 | 2038(A)-(SS) | 8" Divan- 3.5FT PC151-03 | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) -Base 28 BO315-2 | SOFA_BASE | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SV-2605-003-01 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-2 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SV-2605-003-01 | 5530-L(RHF) | 5530 -Right Arm BO315-2 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Right Arm GARFIELD-2 CHERVRON | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON | SOFA_CUSHION | 2 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 GARFIELD-2 CHERVRON | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531 -Left Arm GARFIELD-2 CHERVRON | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON | SOFA_CUSHION | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 GARFIELD-2 CHERVRON | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) -Base 28 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535 -Back Cushion 28 PC151-01 | SOFA_CUSHION | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535 -Right Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-284-01 | 1007-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-069-01 | 1013-(Q) | 8" Divan- 5FT PC151-13 | DIVAN | 2 | Carress | 2026-06-18 | AT-RISK
2026-06-11 Thu | SO-2605-069-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-13 | HEADBOARD | 1 | Carress | 2026-06-18 | AT-RISK
2026-06-11 Thu | SO-2605-289-01 | 1013-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-01 | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-228-01 | 1030-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-11 Thu | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-11 Thu | SO-2605-190-01 | 2006(A)-(K) | 8" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-191-01 | 2006(A)-(Q) | 8" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-11 Thu | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-11 Thu | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" PC151-10 | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-260-01 | 2038(A)-(Q) | 10" Divan- 5FT PC151-10 | DIVAN | 2 | Houzs Century | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 BO315-21 | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-21 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Left Arm BO315-21 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 BO315-21 | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-21 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Right Arm BO315-21 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-03 | 5530-STOOL | 5530-STOOL BO315-21 | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 M2402-1 | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531 -Right Arm M2402-1 | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531 -Back Cushion 28 M2402-1 | SOFA_CUSHION | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Back Cushion 28 PC151-01 | SOFA_CUSHION | 2 | The Conts | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Left Arm PC151-01 | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 PC151-01 | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 FABRIC HR805-90 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 FABRIC HR805-90 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Left Arm FABRIC HR805-90 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Back Cushion 30 FABRIC HR805-90 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 FABRIC HR805-90 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Right Arm FABRIC HR805-90 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-04 | 5536-2S | 5536 -Right Arm FABRIC HR805-90 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-04 | 5536-2S | 5536-2S -Base 30 FABRIC HR805-90 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-04 | 5536-2S | 5536 -Back Cushion 30 FABRIC HR805-90 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-04 | 5536-2S | 5536 -Left Arm FABRIC HR805-90 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-02 | 5536-CNR | 5536-CNR -Base 30 FABRIC HR805-90 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-223-02 | 5536-CNR | 5536 -Back Cushion 30 FABRIC HR805-90 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-206-01 | DIVAN-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-259-01 | DIVAN-(K) | 8" Divan- 6FT PC151-13 | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-200-02 | DIVAN-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-200-03 | DIVAN-(Q) | 8" Divan- 5FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-265-01 | DIVAN-(Q) | 8" Divan- 5FT PC151-14 | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-265-02 | DIVAN-(S) | 8" Divan- 3FT PC151-14 | DIVAN | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" PC151-01 | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-189-01 | 1003(A)-(K) | 10" Divan- 6FT PC151-01 | DIVAN | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-231-01 | 1003(A)-(Q) | 10" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-302-01 | 1007-(K) | 8" Divan- 6FT PC151-15 | DIVAN | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" PC151-15 | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-231-02 | 2041(A)-(Q) | 10" Divan- 5FT PC151-02 | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" PC151-02 | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 BO315-3 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Right Arm BO315-3 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-3 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-3 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 BO315-3 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Left Arm BO315-3 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 M2402-1 | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-12 Fri | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 M2402-1 | SOFA_CUSHION | 2 | Carress | 2026-06-17 | LATE
2026-06-12 Fri | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Left Arm M2402-1 | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-12 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 NINJA 02 | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 NINJA 02 | SOFA_CUSHION | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Right Arm NINJA 02 | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 KN390-3 | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-12 Fri | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Back Cushion 32 KN390-3 | SOFA_CUSHION | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-12 Fri | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Right Arm KN390-3 | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-12 Fri | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 KN390-3 | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-12 Fri | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Back Cushion 32 KN390-3 | SOFA_CUSHION | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-12 Fri | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Left Arm KN390-3 | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-12 Fri | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 BO315-24 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Back Cushion 32 BO315-24 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Right Arm BO315-24 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) -Base 32 BO315-24 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-273-01 | 5535-L(LHF) | 5535 -Back Cushion 32 BO315-24 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-273-01 | 5535-L(LHF) | 5535 -Left Arm BO315-24 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 NINJA 02 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 NINJA 02 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Left Arm NINJA 02 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 NINJA 02 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Back Cushion 30 NINJA 02 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Right Arm NINJA 02 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SV-2605-002-01 | 2006(A)-(K) | 12" Divan- 6FT PC151-14 | DIVAN | 2 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-13 Sat | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" PC151-14 | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-13 Sat | SO-2605-301-01 | 5531-2S | 5531-2S -Base 28 M2402-13 | SOFA_BASE | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-13 Sat | SO-2605-301-01 | 5531-2S | 5531 -Back Cushion 28 M2402-13 | SOFA_CUSHION | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-13 Sat | SO-2605-301-01 | 5531-2S | 5531 -Left Arm M2402-13 | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-13 Sat | SO-2605-301-01 | 5531-2S | 5531 -Right Arm M2402-13 | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-13 Sat | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 NINJA 02 | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-13 Sat | SO-2605-182-01 | 5531-L(LHF) | 5531 -Back Cushion 24 NINJA 02 | SOFA_CUSHION | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-13 Sat | SO-2605-182-01 | 5531-L(LHF) | 5531 -Left Arm NINJA 02 | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-13 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 BO315-5 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Back Cushion 30 BO315-5 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Right Arm BO315-5 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 BO315-5 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Back Cushion 30 BO315-5 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Left Arm BO315-5 | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-02 | 5536-CNR | 5536-CNR -Base 30 BO315-5 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | SO-2605-184-02 | 5536-CNR | 5536 -Back Cushion 30 BO315-5 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME

## 3-Wood
锯木 Wood Cut — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-03 | 2038(A)-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-03 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-05 | 2041(A)-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-072-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-072-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531-2S -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-327-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-072-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (WC) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-02 | 5535-1NA | 5535-1NA -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-02 | 5535-1NA | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-03 | 5535-L(RHF) | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-03 | 5535-L(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-222-02 | 5535-L(RHF) | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-222-02 | 5535-L(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-220-01 | 5536-2S | 5536 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2605-220-01 | 5536-2S | 5536 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2605-220-01 | 5536-2S | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2605-220-01 | 5536-2S | 5536-2S -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Back Cushion (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Back Cushion (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-02 | 5540-1NA | 5540-1NA -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-02 | 5540-1NA | 5540 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Back Cushion 26 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-02 | 5540-CSL | 5540-CSL (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-02 | 5540-CSL | 5540-CSL (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-175-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-175-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-175-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-175-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-176-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-176-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-176-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-176-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-177-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-177-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-177-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-177-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-178-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-178-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-178-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-178-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-179-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-179-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-179-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-179-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-291-01 | 1003(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-01 | 1003(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-02 | 1003(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-291-02 | 1005-(Q) | 4" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-04 Thu | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-04 Thu | SO-2605-203-01 | 1007-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-248-01 | 1007-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-256-01 | 1007-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-256-01 | 1007-(K) | 1007-(K) -HB 23" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-215-02 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-215-02 | 1007-(Q) | 1007-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-249-01 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-249-01 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-255-01 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-255-01 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-257-02 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-257-02 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-276-01 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-096-02 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-096-03 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-214-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-04 Thu | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-04 Thu | SO-2605-264-01 | 1013-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-278-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-096-01 | 1013-(SK) | 8" Divan- 200CMX200CM (WD) | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-277-01 | 1013-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-285-01 | 1013-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-285-02 | 1013-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-04 Thu | SO-2605-299-01 | 1030-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-299-02 | 1030-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-299-03 | 1030-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112-2S -Base 30 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-300-02 | 1030-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-286-01 | 2006(A)-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-192-03 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-258-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-295-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-241-01 | 2009(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-05 Fri | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-05 Fri | SO-2605-241-02 | 2009(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-05 Fri | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-05 Fri | SO-2605-279-01 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-298-01 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-280-01 | 2041(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-280-02 | 2041(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-130-02 | 5530-1NA | 5530-1NA -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-130-02 | 5530-1NA | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-123-01 | 1003(A)-(SK) | 8" Divan- 200CMX200CM (WD) | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-06 Sat | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-06 Sat | SO-2605-281-01 | 1005-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-06 Sat | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-06 Sat | SO-2605-275-01 | 1007-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-259-02 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-06 Sat | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" (WD) | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-06 Sat | SO-2605-275-02 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-06 Sat | SO-2605-297-02 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-06 Sat | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-06 Sat | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-194-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-194-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-06 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-02 | 5540-1NA | 5540-1NA -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-02 | 5540-1NA | 5540 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-03 | 5540-CSL | 5540-CSL (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-03 | 5540-CSL | 5540-CSL (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-06 Sat | SO-2605-300-01 | DIVAN-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-296-01 | DIVAN-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-296-02 | DIVAN-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-296-03 | DIVAN-(S) | 8" Divan- 3FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-283-01 | DIVAN-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-243-02 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-243-03 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-243-04 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-246-01 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-282-02 | 1007-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-08 Mon | SO-2605-292-02 | 1007-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-08 Mon | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-08 Mon | SO-2605-292-03 | 1007-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-08 Mon | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-08 Mon | SO-2605-111-02 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" (WD) | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-216-01 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" (WD) | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-216-04 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" (WD) | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-229-02 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-271-02 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" (WD) | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-293-02 | 1013-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-111-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-216-02 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-216-03 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-244-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-261-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-261-02 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-08 Mon | SO-2605-269-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-269-02 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" (WD) | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-271-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-293-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-08 Mon | SO-2605-245-01 | 1013-(S) | 8" Divan- 3FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-274-01 | 1023-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-08 Mon | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-08 Mon | SO-2605-288-02 | 1052-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-08 Mon | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-261-03 | 2006(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-294-01 | 2006(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-297-01 | 2006(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-09 Tue | SO-2604-281-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-200-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-229-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-242-01 | 2008(A)-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-242-02 | 2008(A)-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-252-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-09 Tue | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-09 Tue | SO-2605-282-01 | 2008(A)-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-292-01 | 2008(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-09 Tue | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-09 Tue | SO-2605-243-01 | 2009(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-09 Tue | SO-2605-211-01 | 2009(A)-(SK) | 8" Divan- 200CMX200CM (WD) | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-09 Tue | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-09 Tue | SO-2605-202-01 | 2033(HF)(W)-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-202-02 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-09 Tue | SO-2605-288-01 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-123-02 | 2038(A)-(SS) | 8" Divan- 3.5FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-09 Tue | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-284-01 | 1007-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-10 Wed | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-10 Wed | SO-2605-069-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-18 | AT-RISK
2026-06-10 Wed | SO-2605-235-01 | 2038(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SV-2605-003-01 | 5530-L(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SV-2605-003-01 | 5530-L(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (WC) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (WC) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (WC) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-10 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (WC) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-103-03 | 5536-1A(RHF) | 5536 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-04 | 5536-2S | 5536-2S -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-04 | 5536-2S | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-04 | 5536-2S | 5536 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-04 | 5536-2S | 5536 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-02 | 5536-CNR | 5536-CNR -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-223-02 | 5536-CNR | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-10 Wed | SO-2605-206-01 | DIVAN-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-259-01 | DIVAN-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-200-02 | DIVAN-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-200-03 | DIVAN-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-265-01 | DIVAN-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-265-02 | DIVAN-(S) | 8" Divan- 3FT (WD) | DIVAN | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-289-01 | 1013-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" (WD) | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-228-01 | 1030-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-11 Thu | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-11 Thu | SO-2605-190-01 | 2006(A)-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-191-01 | 2006(A)-(Q) | 8" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-11 Thu | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-11 Thu | SO-2605-260-01 | 2038(A)-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-290-03 | 5530-STOOL | 5530-STOOL (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-11 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-11 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (WC) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-02 | 5535-1NA | 5535-1NA -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-02 | 5535-1NA | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-06 | 5535-1S | 5535-1S -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-06 | 5535-1S | 5535 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-06 | 5535-1S | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-106-06 | 5535-1S | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (WC) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-11 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-11 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-11 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-11 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-11 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535 -Back Cushion 32 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-11 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-189-01 | 1003(A)-(K) | 10" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-231-01 | 1003(A)-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-302-01 | 1007-(K) | 8" Divan- 6FT (WD) | DIVAN | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" (WD) | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SV-2605-002-01 | 2006(A)-(K) | 12" Divan- 6FT (WD) | DIVAN | 2 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-12 Fri | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" (WD) | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-12 Fri | SO-2605-231-02 | 2041(A)-(Q) | 10" Divan- 5FT (WD) | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" (WD) | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-12 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-12 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-12 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-12 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Back Cushion 28 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-12 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-12 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (WC) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-301-01 | 5531-2S | 5531-2S -Base 28 (WC) | SOFA_BASE | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-301-01 | 5531-2S | 5531 -Back Cushion 28 (WC) | SOFA_CUSHION | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-301-01 | 5531-2S | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-301-01 | 5531-2S | 5531 -Right Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-12 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (WC) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (WC) | SOFA_CUSHION | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Left Arm (WC) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-12 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-12 Fri | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-184-02 | 5536-CNR | 5536-CNR -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-12 Fri | SO-2605-184-02 | 5536-CNR | 5536 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-13 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Left Arm (WC) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-13 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-13 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Back Cushion 30 (WC) | SOFA_CUSHION | 2 | Houzs Century |  | ON-TIME
2026-06-13 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Right Arm (WC) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-13 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530-L(RHF) -Base 30 (WC) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-13 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Back Cushion 30 (WC) | SOFA_CUSHION | 1 | Houzs Century |  | ON-TIME

## 4-Foam
粘棉 Foam — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 1005-(Q) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 1005-(Q) -HB 25" PC151-04 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" PC151-03 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-02 Tue | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-02 Tue | SO-2605-167-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-205-01 | 1007-(S) | 1007-(S) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-02 | 1007-(S) | 1007-(S) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 1013-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 1013-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 1013-(SS) -HB 20" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-02 Tue | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-02 Tue | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-02 Tue | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" PC151-18 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-02 Tue | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-02 Tue | SO-2605-210-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-14 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-02 Tue | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-02 Tue | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-02 Tue | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-02 Tue | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-02 Tue | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" PC151-14 Foam | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-02 Tue | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 2008(A)-(K) -HB 23" PC151-04 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-10 | 2009(A)-(K) | 2009(A)-(K) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" KS-18 Foam | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" PC151-12 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-02 Tue | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" PC151-10 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-03 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" PC151-11 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-010-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" PC151-11 Foam | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-131-05 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-050-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-050-01 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-050-02 | 5530-1A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2604-265-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-02 Tue | SO-2604-265-02 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-02 Tue | SO-2604-265-01 | 5530-L(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-03 Wed | SO-2605-109-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Back Cushion BO315-21 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-02 | 5530-L(RHF) | 5530-L(RHF) -Base (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-02 | 5530-L(RHF) | 5530 -Back Cushion BO315-21 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-02 | 5530-L(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Back Cushion 24 M2402-13 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 NINJA 08 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-2 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-345-03 | 5531-2S | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2604-345-03 | 5531-2S | 5531-2S -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2604-345-03 | 5531-2S | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2604-327-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-01 | 5531-L(LHF) | 5531 -Back Cushion 28 NINJA 08 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-02 | 5531-L(RHF) | 5531 -Back Cushion 24 M2402-13 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-02 | 5531-L(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-067-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-067-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-067-01 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-2 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Back Cushion 32 BO315-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-02 | 5535-1NA | 5535-1NA -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-02 | 5535-1NA | 5535 -Back Cushion 32 BO315-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Back Cushion 30 CH141-14 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-03 | 5535-L(RHF) | 5535 -Back Cushion 32 BO315-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-03 | 5535-L(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-02 | 5535-L(RHF) | 5535 -Back Cushion 30 CH141-14 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-02 | 5535-L(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536 -Back Cushion 30 BO315-23 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536-2S -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Back Cushion 28 BO315-22 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Back Cushion 28 BO315-22 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Back Cushion BO315-31 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Back Cushion 32 AM275-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-105-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Back Cushion BO315-31 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Back Cushion 32 AM275-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540 -Back Cushion 32 AM275-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540-1NA -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Back Cushion 26 BO315-23 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-108-01 | 5540-2S | 5540-2S -Base (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-02 | 5540-CSL | 5540-CSL (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-02 | 5540-CSL | 5540-CSL (Foam) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540 -Back Cushion 32 BO315-23 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 1007-(K) -HB 23" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-154-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 1007-(Q) -HB 22" PC151-08 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-04 | 1007-(Q) | 1007-(Q) -HB 22" PC151-09 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-195-01 | 1007-(Q) | 1007-(Q) -HB 22" PC151-17 Foam | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-207-01 | 1007-(Q) | 1007-(Q) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-249-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-17 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-255-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-17 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 1007-(Q) -HB 20" PC151-17 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112-2S -Base 30 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-09 Tue | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-192-04 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-215-02 | 1007-(Q) | 1007-(Q) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-185-01 | 1007-(S) | 1007-(S) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-070-01 | 1013-(K) | 1013-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" PC151-12 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" PC151-10 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-153-02 | 1013-(Q) | 1013-(Q) -HB 20" PC151-03 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-185-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-14 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-193-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-03 Foam | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" KS-14 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-254-01 | 1013-(Q) | 1013-(Q) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-262-01 | 1013-(Q) | 1013-(Q) -HB 20" PC151-17 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-04 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-215-03 | 1013-(S) | 1013-(S) -HB 21" PC151-09 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-04 | 1013-(S) | 1013-(S) -HB 21" PC151-08 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-254-02 | 1013-(S) | 1013-(S) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" PC151-10 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-070-02 | 1013-(SS) | 1013-(SS) -HB 22" PC151-18 Foam | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-262-02 | 1013-(SS) | 1013-(SS) -HB 20" PC151-17 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" PC151-09 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" PC151-11 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-099-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-192-02 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-12 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-10 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-02 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-03 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-263-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-099-02 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-192-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-215-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" PC151-04 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" PC151-06 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-247-01 | 2009(A)-(K) | 2009(A)-(K) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-239-01 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Carress | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" PC151-15 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-153-01 | 2038(A)-(K) | 2038(A)-(K) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-140-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" PC151-13 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-209-03 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-051-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 24 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-10 Wed | SO-2605-051-03 | 5530-1A(RHF) | 5530-1A(RHF) -Base 24 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-10 Wed | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 CH141-12 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-01 | 5530-L(LHF) | 5530 -Back Cushion 28 CH141-12 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-01 | 5530-L(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-03 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-03 | 5530-L(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-03 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-25 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-04 | 5530-STOOL | 5530-STOOL (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-04 | 5530-STOOL | 5530-STOOL (Foam) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-25 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-130-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-03 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Back Cushion 28 BO315-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-02 | 5530-1NA | 5530-1NA -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-02 | 5530-1NA | 5530 -Back Cushion 28 BO315-1 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-22 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-080-02 | 5530-2NA | 5530-2NA -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-02 | 5530-2NA | 5530 -Back Cushion 28 BO315-25 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-22 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-4 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-4 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 M2402-18 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 NINJA 02 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 M2402-18 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA Foam | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-2 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531 -Back Cushion 28 GARFIELD - 3 TUNDORA Foam | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531 -Back Cushion 28 KN390-2 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-02 | 5531-L(RHF) | 5531 -Back Cushion 28 NINJA 02 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-02 | 5531-L(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-077-03 | 5540-CSL | 5540-CSL (Foam) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-03 | 5540-CSL | 5540-CSL (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-04 | 5540-L(RHF) | 5540 -Back Cushion 30 FABRIC HR805-10 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-04 | 5540-L(RHF) | 5540 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" PC151-14 Foam | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" PC151-03 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" PC151-17 Foam | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" PC151-14 Foam | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" PC151-13 Foam | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" PC151-17 Foam | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-17 Foam | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-06 Foam | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 Foam | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-15 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-17 Foam | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 FABRIC HR805-10 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-02 | 5540-1NA | 5540-1NA -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-02 | 5540-1NA | 5540 -Back Cushion 30 FABRIC HR805-10 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-15 Mon | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" PC151-17 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" PC151-12 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-15 Mon | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" PC151-03 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-15 Mon | SV-2605-003-01 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-2 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-15 Mon | SV-2605-003-01 | 5530-L(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-15 Mon | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON Foam | SOFA_CUSHION | 2 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-01 | 5531-L(LHF) | 5531 -Back Cushion 24 GARFIELD-2 CHERVRON Foam | SOFA_CUSHION | 1 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-16 Tue | SO-2605-069-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-13 Foam | HEADBOARD | 1 | Carress | 2026-06-18 | AT-RISK
2026-06-16 Tue | SO-2605-237-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 KN390-1 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-01 | 5531-L(LHF) | 5531 -Back Cushion 24 KN390-1 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Back Cushion 28 PC151-01 Foam | SOFA_CUSHION | 2 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-02 | 5535-L(RHF) | 5535 -Back Cushion 28 PC151-01 Foam | SOFA_CUSHION | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-02 | 5535-L(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-103-03 | 5536-1A(RHF) | 5536 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536-2S -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-103-02 | 5536-CNR | 5536-CNR -Base (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-223-02 | 5536-CNR | 5536-CNR -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-02 | 5536-CNR | 5536 -Back Cushion 30 FABRIC HR805-90 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" PC151-01 Foam | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" PC151-10 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 BO315-21 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-21 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-03 | 5530-STOOL | 5530-STOOL (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 M2402-1 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-02 | 5531-L(RHF) | 5531 -Back Cushion 28 M2402-1 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-02 | 5531-L(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Back Cushion 32 KN390-3 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-17 Wed | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Back Cushion 32 BO315-24 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-17 Wed | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-17 Wed | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-17 Wed | SO-2605-273-01 | 5535-L(LHF) | 5535 -Back Cushion 32 BO315-24 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-17 Wed | SO-2605-273-01 | 5535-L(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" PC151-01 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-18 Thu | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-18 Thu | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" PC151-15 Foam | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-18 Thu | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" PC151-02 Foam | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-18 Thu | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-18 Thu | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 BO315-3 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-18 Thu | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Back Cushion 30 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Back Cushion 30 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Back Cushion 30 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Back Cushion 30 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535-1NA -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535 -Back Cushion 30 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535-1S -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Back Cushion 30 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Back Cushion 32 KN390-3 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 NINJA 02 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Back Cushion 30 NINJA 02 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 BO315-3 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 M2402-4 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Back Cushion 28 BO315-3 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Back Cushion 28 BO315-3 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Back Cushion 28 M2402-4 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 NINJA 02 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531-2S -Base 28 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Back Cushion 28 M2402-13 Foam | SOFA_CUSHION | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Right Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Foam) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Back Cushion 24 NINJA 02 Foam | SOFA_CUSHION | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Left Arm (Foam) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 2 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Back Cushion 30 PC151-01 Foam | SOFA_CUSHION | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530-L(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Back Cushion 30 BO315-5 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Right Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Back Cushion 30 BO315-5 Foam | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Left Arm (Foam) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536-CNR -Base 30 (Foam) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536 -Back Cushion 30 BO315-5 Foam | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME

## 5-Frame
组框 Framing — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-124-01 | 1005-(Q) | 1005-(Q) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 1005-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 1013-(Q) -HB 20" Frame | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 1013-(Q) -HB 20" Frame | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-10 | 2009(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-10 | 2009(A)-(K) | 2009(A)-(K) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-03 | 2038(A)-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-204-03 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-010-02 | 2041(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-010-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-131-05 | 2041(A)-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-109-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Back Cushion (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-109-02 | 5530-L(RHF) | 5530-L(RHF) -Base (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-109-02 | 5530-L(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-109-02 | 5530-L(RHF) | 5530 -Back Cushion (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Back Cushion 24 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531-2S -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-345-03 | 5531-2S | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-02 Tue | SO-2604-327-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-327-01 | 5531-L(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-02 | 5535-1NA | 5535-1NA -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-02 | 5535-1NA | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-03 | 5535-L(RHF) | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-104-03 | 5535-L(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-02 | 5535-L(RHF) | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-222-02 | 5535-L(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-220-01 | 5536-2S | 5536 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2605-220-01 | 5536-2S | 5536 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2605-220-01 | 5536-2S | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2605-220-01 | 5536-2S | 5536-2S -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Back Cushion (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-105-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Back Cushion (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-02 | 5540-1NA | 5540-1NA -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2605-221-02 | 5540-1NA | 5540 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-03 Wed | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Back Cushion 26 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-02 | 5540-CSL | 5540-CSL (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-02 | 5540-CSL | 5540-CSL (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-078-01 | 5540-L(LHF) | 5540 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-180-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-03 Wed | SO-2605-181-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-291-01 | 1003(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-01 | 1003(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-02 | 1003(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-291-02 | 1005-(Q) | 4" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-04 Thu | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-04 Thu | SO-2605-248-01 | 1007-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-195-01 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-04 Thu | SO-2605-249-01 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-249-01 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-04 Thu | SO-2605-255-01 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2605-255-01 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-04 Thu | SO-2604-307-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-307-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-307-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-307-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-173-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-173-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-173-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-173-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-174-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-175-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-175-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-175-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-175-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-176-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-176-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-176-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-176-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-177-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-178-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112-2S -Base 30 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-179-01 | 6112-2S | 6112 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-04 Thu | SO-2605-131-04 | DIVAN-(K) | 4" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-203-01 | 1007-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-256-01 | 1007-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-256-01 | 1007-(K) | 1007-(K) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-185-03 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-185-03 | 1007-(Q) | 1007-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-185-04 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-192-04 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-192-04 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-215-02 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-215-02 | 1007-(Q) | 1007-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-257-01 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-257-01 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-257-02 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-257-02 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-185-01 | 1007-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-185-01 | 1007-(S) | 1007-(S) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-070-01 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-276-01 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-096-02 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-03 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-185-02 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-185-02 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-214-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-05 Fri | SO-2605-254-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-254-01 | 1013-(Q) | 1013-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-262-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-262-01 | 1013-(Q) | 1013-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-264-01 | 1013-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-278-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-215-03 | 1013-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-215-03 | 1013-(S) | 1013-(S) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-215-04 | 1013-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-215-04 | 1013-(S) | 1013-(S) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-254-02 | 1013-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-254-02 | 1013-(S) | 1013-(S) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-01 | 1013-(SK) | 8" Divan- 200CMX200CM Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-05 Fri | SO-2605-070-02 | 1013-(SS) | 1013-(SS) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-262-02 | 1013-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-262-02 | 1013-(SS) | 1013-(SS) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-05 Fri | SO-2605-277-01 | 1013-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-01 | 1013-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-02 | 1013-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-05 Fri | SO-2605-299-02 | 1030-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-03 | 1030-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-05 Fri | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-299-01 | 1030-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-300-02 | 1030-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-210-01 | 2006(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-210-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-286-01 | 2006(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-192-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-192-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-192-02 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-192-02 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-192-03 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-238-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-238-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-238-02 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-238-02 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-238-03 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-238-03 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-258-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-06 Sat | SO-2605-263-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-263-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-099-02 | 2008(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-099-02 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-215-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-215-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-295-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-241-01 | 2009(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-08 Mon | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-08 Mon | SO-2605-247-01 | 2009(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-247-01 | 2009(A)-(K) | 2009(A)-(K) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-239-01 | 2009(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-239-01 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" Frame | HEADBOARD | 1 | Carress | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-241-02 | 2009(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-08 Mon | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-08 Mon | SO-2605-153-01 | 2038(A)-(K) | 2038(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-279-01 | 2038(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-298-01 | 2038(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-280-01 | 2041(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-280-02 | 2041(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-02 | 5530-2NA | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-02 | 5530-2NA | 5530-2NA -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2604-293-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2604-293-01 | 5530-L(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-03 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-03 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-03 | 5530-L(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-04 | 5530-STOOL | 5530-STOOL (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-080-04 | 5530-STOOL | 5530-STOOL (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-080-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-03 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-02 | 5530-1NA | 5530-1NA -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-130-02 | 5530-1NA | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-240-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-240-01 | 5530-L(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-071-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-194-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-194-01 | 5531-L(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-196-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-196-01 | 5531-L(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-071-02 | 5531-L(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-071-02 | 5531-L(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-071-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-02 | 5540-1NA | 5540 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-02 | 5540-1NA | 5540-1NA -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-03 | 5540-CSL | 5540-CSL (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-03 | 5540-CSL | 5540-CSL (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-04 | 5540-L(RHF) | 5540 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-077-04 | 5540-L(RHF) | 5540 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-09 Tue | SO-2605-300-01 | DIVAN-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-296-01 | DIVAN-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-296-02 | DIVAN-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-296-03 | DIVAN-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-283-01 | DIVAN-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-123-01 | 1003(A)-(SK) | 8" Divan- 200CMX200CM Frame | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-281-01 | 1005-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-10 Wed | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-10 Wed | SO-2605-275-01 | 1007-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-02 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-03 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-04 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-246-01 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-259-02 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" Frame | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-275-02 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-282-02 | 1007-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-10 Wed | SO-2605-297-02 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-292-02 | 1007-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-10 Wed | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-10 Wed | SO-2605-292-03 | 1007-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-10 Wed | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-10 Wed | SO-2605-111-02 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-216-04 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-229-02 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-271-02 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" Frame | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-293-02 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-111-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-244-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-261-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-261-02 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-10 Wed | SO-2605-269-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-269-02 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-271-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" Frame | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-293-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-10 Wed | SO-2605-245-01 | 1013-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-10 Wed | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-216-01 | 1013-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-11 Thu | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-11 Thu | SO-2605-216-02 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-11 Thu | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-11 Thu | SO-2605-216-03 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-11 Thu | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" Frame | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-11 Thu | SO-2605-274-01 | 1023-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-11 Thu | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-11 Thu | SO-2605-288-02 | 1052-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-261-03 | 2006(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-11 Thu | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-11 Thu | SO-2605-294-01 | 2006(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-297-01 | 2006(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-11 Thu | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-11 Thu | SO-2604-281-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-200-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-229-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-11 Thu | SO-2605-242-01 | 2008(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-11 Thu | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-11 Thu | SO-2605-242-02 | 2008(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-11 Thu | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-11 Thu | SO-2605-282-01 | 2008(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-11 Thu | SO-2605-292-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-11 Thu | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-252-01 | 2008(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-243-01 | 2009(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-211-01 | 2009(A)-(SK) | 8" Divan- 200CMX200CM Frame | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-12 Fri | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-12 Fri | SO-2605-202-01 | 2033(HF)(W)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-202-02 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-235-01 | 2038(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-288-01 | 2038(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-123-02 | 2038(A)-(SS) | 8" Divan- 3.5FT Frame | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-12 Fri | SV-2605-003-01 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-12 Fri | SV-2605-003-01 | 5530-L(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-12 Fri | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-237-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-076-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-076-01 | 5531-L(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-237-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-237-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-237-01 | 5531-L(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-12 Fri | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | The Conts | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-270-02 | 5535-L(RHF) | 5535 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | The Conts | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-270-02 | 5535-L(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-103-03 | 5536-1A(RHF) | 5536 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-04 | 5536-2S | 5536-2S -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-04 | 5536-2S | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-04 | 5536-2S | 5536 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-04 | 5536-2S | 5536 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-02 | 5536-CNR | 5536-CNR -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-12 Fri | SO-2605-223-02 | 5536-CNR | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-13 Sat | SO-2605-284-01 | 1007-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-069-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-18 | AT-RISK
2026-06-13 Sat | SO-2605-289-01 | 1013-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" Frame | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-228-01 | 1030-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-13 Sat | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-13 Sat | SO-2605-190-01 | 2006(A)-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-191-01 | 2006(A)-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-13 Sat | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-13 Sat | SO-2605-260-01 | 2038(A)-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-290-03 | 5530-STOOL | 5530-STOOL (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-13 Sat | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-236-02 | 5531-L(RHF) | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-236-02 | 5531-L(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-13 Sat | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-05 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-06 | 5535-1S | 5535-1S -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-06 | 5535-1S | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-06 | 5535-1S | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-106-06 | 5535-1S | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-13 Sat | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SO-2605-273-01 | 5535-L(LHF) | 5535 -Back Cushion 32 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SO-2605-273-01 | 5535-L(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-13 Sat | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-13 Sat | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-13 Sat | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-13 Sat | SO-2605-206-01 | DIVAN-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-259-01 | DIVAN-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-200-02 | DIVAN-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-200-03 | DIVAN-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-265-01 | DIVAN-(Q) | 8" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-265-02 | DIVAN-(S) | 8" Divan- 3FT Frame | DIVAN | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-189-01 | 1003(A)-(K) | 10" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-231-01 | 1003(A)-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-302-01 | 1007-(K) | 8" Divan- 6FT Frame | DIVAN | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-15 Mon | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" Frame | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-15 Mon | SO-2605-231-02 | 2041(A)-(Q) | 10" Divan- 5FT Frame | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" Frame | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-199-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-224-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-15 Mon | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-15 Mon | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-15 Mon | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-198-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-198-01 | 5530-L(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-199-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-199-02 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-199-02 | 5530-L(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-224-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-15 Mon | SO-2605-224-02 | 5530-L(RHF) | 5530 -Back Cushion 28 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-15 Mon | SO-2605-224-02 | 5530-L(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-15 Mon | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-301-01 | 5531-2S | 5531-2S -Base 28 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-15 Mon | SO-2605-301-01 | 5531-2S | 5531 -Back Cushion 28 (Frame) | SOFA_CUSHION | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-15 Mon | SO-2605-301-01 | 5531-2S | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-15 Mon | SO-2605-301-01 | 5531-2S | 5531 -Right Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-15 Mon | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Frame) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-182-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (Frame) | SOFA_CUSHION | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-182-01 | 5531-L(LHF) | 5531 -Left Arm (Frame) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-15 Mon | SO-2605-106-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-03 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-02 | 5535-1NA | 5535-1NA -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-106-02 | 5535-1NA | 5535 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-15 Mon | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-15 Mon | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-15 Mon | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-15 Mon | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-15 Mon | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-15 Mon | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-15 Mon | SO-2605-184-02 | 5536-CNR | 5536-CNR -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-15 Mon | SO-2605-184-02 | 5536-CNR | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-16 Tue | SV-2605-002-01 | 2006(A)-(K) | 12" Divan- 6FT Frame | DIVAN | 2 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-16 Tue | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" Frame | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-16 Tue | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-16 Tue | CO-2605-008-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-16 Tue | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | Houzs Century |  | ON-TIME
2026-06-16 Tue | CO-2605-008-02 | 5530-L(RHF) | 5530-L(RHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-16 Tue | CO-2605-008-02 | 5530-L(RHF) | 5530 -Right Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-16 Tue | CO-2605-008-02 | 5530-L(RHF) | 5530 -Back Cushion 30 (Frame) | SOFA_CUSHION | 1 | Houzs Century |  | ON-TIME
2026-06-16 Tue | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (Frame) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-16 Tue | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Back Cushion 30 (Frame) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-16 Tue | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Left Arm (Frame) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME

## 6-Web
打底 Webbing — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-124-01 | 1005-(Q) | 1005-(Q) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 1005-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 1005-(Q) -HB 25" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-02 | 1005-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-02 | 1005-(Q) | 1005-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-213-01 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-213-01 | 1013-(K) | 1013-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-227-01 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-227-01 | 1013-(K) | 1013-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 1013-(SS) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-102-01 | 2006(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-162-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-162-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 2008(A)-(K) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-02 | LATE
2026-06-02 Tue | SO-2605-234-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-02 Tue | SO-2605-131-10 | 2009(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-10 | 2009(A)-(K) | 2009(A)-(K) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-02 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-03 | 2038(A)-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-03 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-010-02 | 2041(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-010-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-131-05 | 2041(A)-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-050-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-109-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Back Cushion (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-02 | 5530-L(RHF) | 5530 -Back Cushion (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-02 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-109-02 | 5530-L(RHF) | 5530-L(RHF) -Base (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Back Cushion 24 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-345-03 | 5531-2S | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2604-345-03 | 5531-2S | 5531-2S -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-03 Wed | SO-2604-327-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-327-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-067-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-02 | 5531-L(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-02 | 5535-1NA | 5535-1NA -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-02 | 5535-1NA | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-03 | 5535-L(RHF) | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-104-03 | 5535-L(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-02 | 5535-L(RHF) | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-222-02 | 5535-L(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2605-220-01 | 5536-2S | 5536-2S -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-04 Thu | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Back Cushion 26 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-02 | 5540-CSL | 5540-CSL (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-02 | 5540-CSL | 5540-CSL (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-01 | 5540-L(LHF) | 5540 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-078-01 | 5540-L(LHF) | 5540 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Back Cushion (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-105-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Back Cushion (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540-1NA -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-177-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-177-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-177-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-177-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-178-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-178-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-178-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-178-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-179-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-179-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-179-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-179-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-180-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-180-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-180-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-180-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-05 Fri | SO-2605-181-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-291-01 | 1003(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-226-01 | 1003(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-226-02 | 1003(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-291-02 | 1005-(Q) | 4" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-06 Sat | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-06 Sat | SO-2605-248-01 | 1007-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-154-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-154-01 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-195-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-195-01 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-06 Sat | SO-2605-249-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-249-01 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-255-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2605-255-01 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-06 Sat | SO-2604-307-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2604-307-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2604-307-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2604-307-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-173-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-173-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-173-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-173-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-174-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-174-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-174-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-174-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-175-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-175-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-175-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-175-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112-2S -Base 30 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-131-04 | DIVAN-(K) | 4" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-203-01 | 1007-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 1007-(K) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-04 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-192-04 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-192-04 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-215-02 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-215-02 | 1007-(Q) | 1007-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-01 | 1007-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-01 | 1007-(S) | 1007-(S) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-070-01 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-276-01 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-096-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-096-03 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-153-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-153-02 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-185-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-02 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-193-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-193-01 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-214-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-254-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-254-01 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-262-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-262-01 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-264-01 | 1013-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-278-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-215-03 | 1013-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-215-03 | 1013-(S) | 1013-(S) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-215-04 | 1013-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-215-04 | 1013-(S) | 1013-(S) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-254-02 | 1013-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-254-02 | 1013-(S) | 1013-(S) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-096-01 | 1013-(SK) | 8" Divan- 200CMX200CM Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-070-02 | 1013-(SS) | 1013-(SS) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-262-02 | 1013-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-262-02 | 1013-(SS) | 1013-(SS) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-277-01 | 1013-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-285-01 | 1013-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-285-02 | 1013-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-08 Mon | SO-2605-299-01 | 1030-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-299-02 | 1030-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-299-03 | 1030-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-300-02 | 1030-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-08 Mon | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-210-01 | 2006(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-210-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-286-01 | 2006(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-099-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-099-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-192-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-02 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-02 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-03 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-209-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-209-01 | 2008(A)-(K) | 2008(A)-(K) -HB 25" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-209-02 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-215-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-238-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-02 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-02 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-03 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-238-03 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-258-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-263-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-263-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-295-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-099-02 | 2008(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-099-02 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-241-01 | 2009(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-247-01 | 2009(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-247-01 | 2009(A)-(K) | 2009(A)-(K) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-239-01 | 2009(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-239-01 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" Webbing | HEADBOARD | 1 | Carress | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-241-02 | 2009(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-10 Wed | SO-2605-153-01 | 2038(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-153-01 | 2038(A)-(K) | 2038(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-140-01 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-140-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-209-03 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-03 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-04 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-279-01 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-298-01 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-280-01 | 2041(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-280-02 | 2041(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-10 Wed | SO-2605-051-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-10 Wed | SO-2605-051-03 | 5530-1A(RHF) | 5530-1A(RHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-10 Wed | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-02 | 5530-2NA | 5530-2NA -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-02 | 5530-2NA | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2604-293-01 | 5530-L(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-03 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-03 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-03 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-04 | 5530-STOOL | 5530-STOOL (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-080-04 | 5530-STOOL | 5530-STOOL (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-130-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-03 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-02 | 5530-1NA | 5530-1NA -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-130-02 | 5530-1NA | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-194-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-194-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-123-01 | 1003(A)-(SK) | 8" Divan- 200CMX200CM Foam | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-281-01 | 1005-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-12 Fri | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-12 Fri | SO-2605-275-01 | 1007-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-243-03 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-243-04 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-259-02 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" Webbing | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-12 Fri | SO-2605-275-02 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-282-02 | 1007-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-12 Fri | SO-2605-297-02 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-12 Fri | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-02 | 5531-L(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-071-02 | 5531-L(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-02 | 5540-1NA | 5540-1NA -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-02 | 5540-1NA | 5540 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-03 | 5540-CSL | 5540-CSL (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-03 | 5540-CSL | 5540-CSL (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-04 | 5540-L(RHF) | 5540 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-077-04 | 5540-L(RHF) | 5540 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-12 Fri | SO-2605-300-01 | DIVAN-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-12 Fri | SO-2605-296-01 | DIVAN-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-12 Fri | SO-2605-296-02 | DIVAN-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-12 Fri | SO-2605-296-03 | DIVAN-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-12 Fri | SO-2605-283-01 | DIVAN-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-111-02 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-216-01 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-04 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-229-02 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-271-02 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" Webbing | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-293-02 | 1013-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-111-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-216-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-03 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-244-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-261-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-261-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-269-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" Webbing | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-271-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-293-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-13 Sat | SO-2605-245-01 | 1013-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-274-01 | 1023-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-13 Sat | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-13 Sat | SO-2605-288-02 | 1052-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-261-03 | 2006(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-294-01 | 2006(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-297-01 | 2006(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2604-281-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-200-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-242-01 | 2008(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-242-02 | 2008(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-252-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-15 Mon | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-292-01 | 2008(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-15 Mon | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-15 Mon | SO-2605-243-01 | 2009(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-211-01 | 2009(A)-(SK) | 8" Divan- 200CMX200CM Foam | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-202-01 | 2033(HF)(W)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-202-02 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-15 Mon | SO-2605-235-01 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-288-01 | 2038(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-123-02 | 2038(A)-(SS) | 8" Divan- 3.5FT Foam | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-15 Mon | SV-2605-003-01 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-15 Mon | SV-2605-003-01 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-15 Mon | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-237-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-076-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-076-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-237-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-237-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-02 | 5535-L(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-270-02 | 5535-L(RHF) | 5535 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | The Conts | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-103-03 | 5536-1A(RHF) | 5536 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536-2S -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-04 | 5536-2S | 5536 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-103-02 | 5536-CNR | 5536-CNR -Base (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-223-02 | 5536-CNR | 5536-CNR -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-223-02 | 5536-CNR | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-284-01 | 1007-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-069-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-18 | AT-RISK
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" Webbing | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-228-01 | 1030-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-17 Wed | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-17 Wed | SO-2605-190-01 | 2006(A)-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-191-01 | 2006(A)-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-17 Wed | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-17 Wed | SO-2605-260-01 | 2038(A)-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-290-03 | 5530-STOOL | 5530-STOOL (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-02 | 5531-L(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-02 | 5531-L(RHF) | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-206-01 | DIVAN-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-200-02 | DIVAN-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-200-03 | DIVAN-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-265-01 | DIVAN-(Q) | 8" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-265-02 | DIVAN-(S) | 8" Divan- 3FT Foam | DIVAN | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-18 Thu | SO-2605-189-01 | 1003(A)-(K) | 10" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-18 Thu | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-18 Thu | SO-2605-231-01 | 1003(A)-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-18 Thu | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-18 Thu | SO-2605-302-01 | 1007-(K) | 8" Divan- 6FT Foam | DIVAN | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-18 Thu | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" Webbing | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-18 Thu | SO-2605-231-02 | 2041(A)-(Q) | 10" Divan- 5FT Foam | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-18 Thu | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" Webbing | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535-1NA -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535-1S -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) -Base 32 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535 -Back Cushion 32 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531-2S -Base 28 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Back Cushion 28 (Webbing) | SOFA_CUSHION | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 (Webbing) | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Back Cushion 24 (Webbing) | SOFA_CUSHION | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-20 Sat | SV-2605-002-01 | 2006(A)-(K) | 12" Divan- 6FT Foam | DIVAN | 2 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-20 Sat | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" Webbing | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530-L(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Right Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Left Arm (Webbing) | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536-CNR -Base 30 (Webbing) | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536 -Back Cushion 30 (Webbing) | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME

## 7-Uphol
包面 Upholstery — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-187-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-124-01 | 1005-(Q) | 1005-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 1005-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 1005-(Q) -HB 25" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-02 | 1005-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-02 | 1005-(Q) | 1005-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-009-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-22 | OVERDUE
2026-06-02 Tue | SO-2605-023-01 | 1007-(K) | 1007-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-05-18 | OVERDUE
2026-06-02 Tue | SO-2605-160-02 | 1007-(Q) | 4" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-160-02 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-161-01 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-167-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-167-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-205-01 | 1007-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-01 | 1007-(S) | 1007-(S) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-02 | 1007-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-02 | 1007-(S) | 1007-(S) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-213-01 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-186-01 | 1013-(SS) | 10" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-05-26 | OVERDUE
2026-06-02 Tue | SO-2605-186-01 | 1013-(SS) | 1013-(SS) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-05-26 | OVERDUE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 1013-(SS) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-321-03 | 1023(HF)(W)-(SS) | 10" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-05-21 | OVERDUE
2026-06-02 Tue | SO-2604-321-03 | 1023(HF)(W)-(SS) | 1023(HF)(W)-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-21 | OVERDUE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-102-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-098-03 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2605-098-04 | 2008(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-03 Wed | SO-2605-234-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-234-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-131-10 | 2009(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-131-10 | 2009(A)-(K) | 2009(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-171-01 | 2011(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-02 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-03 | 2038(A)-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-03 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-010-02 | 2041(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-010-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-131-05 | 2041(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-131-05 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-276-03 | 2041(A)-(SS) | 10" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-05-13 | OVERDUE
2026-06-03 Wed | SO-2604-276-03 | 2041(A)-(SS) | 2041(A)-(SS) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-05-13 | OVERDUE
2026-06-03 Wed | SO-2604-088-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-088-01 | 5530-1A(LHF) | 5530 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-088-01 | 5530-1A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-088-02 | 5530-1A(RHF) | 5530-1A(RHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-088-02 | 5530-1A(RHF) | 5530 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-088-02 | 5530-1A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-086-01 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-03 Wed | SO-2604-086-01 | 5530-2A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-03 Wed | SO-2604-086-01 | 5530-2A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-03 Wed | SO-2604-265-02 | 5530-2A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-03 Wed | SO-2604-265-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-03 Wed | SO-2604-265-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-03 Wed | SO-2604-086-02 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-03 Wed | SO-2604-086-02 | 5530-L(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-03 Wed | SO-2604-086-02 | 5530-L(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-04 Thu | SO-2605-050-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-050-01 | 5530-1A(LHF) | 5530 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-050-01 | 5530-1A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-050-02 | 5530-1A(RHF) | 5530-1A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-050-02 | 5530-1A(RHF) | 5530 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-050-02 | 5530-1A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-063-05 | 5530-1NA | 5530-1NA -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-05 | 5530-1NA | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-01 | 5530-2A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-109-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Back Cushion | SOFA_CUSHION | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-109-01 | 5530-2A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-265-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-04 Thu | SO-2604-265-01 | 5530-L(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-04 Thu | SO-2604-265-01 | 5530-L(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-04 Thu | SO-2605-063-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-02 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-02 | 5530-L(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-109-02 | 5530-L(RHF) | 5530-L(RHF) -Base | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-109-02 | 5530-L(RHF) | 5530 -Back Cushion | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-109-02 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-079-01 | 5531-2A(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-327-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-327-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-072-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-072-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-072-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-345-03 | 5531-2S | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-345-03 | 5531-2S | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-345-03 | 5531-2S | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-345-03 | 5531-2S | 5531-2S -Base 28 | SOFA_BASE | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-327-01 | 5531-L(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-327-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-327-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-072-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-072-01 | 5531-L(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-072-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-079-02 | 5531-L(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-079-02 | 5531-L(RHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-01 | 5531-L(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-01 | 5535-1A(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-02 | 5535-1NA | 5535-1NA -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-02 | 5535-1NA | 5535 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-222-01 | 5535-2A(LHF) | 5535 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-03 | 5535-L(RHF) | 5535 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-03 | 5535-L(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-222-02 | 5535-L(RHF) | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-222-02 | 5535-L(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-220-01 | 5536-2S | 5536 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-05 Fri | SO-2605-220-01 | 5536-2S | 5536 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-05 Fri | SO-2605-220-01 | 5536-2S | 5536-2S -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-05 Fri | SO-2605-220-01 | 5536-2S | 5536 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-05 Fri | SO-2603-207-01 | 5537-1A(LHF) | 5537-1A(LHF) -Base 35 | SOFA_BASE | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2603-207-01 | 5537-1A(LHF) | 5537 -Back Cushion 35 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2603-207-01 | 5537-1A(LHF) | 5537 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2603-207-02 | 5537-1A(RHF) | 5537 -Back Cushion 35 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2603-207-02 | 5537-1A(RHF) | 5537 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2603-207-02 | 5537-1A(RHF) | 5537-1A(RHF) -Base 35 | SOFA_BASE | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2604-324-02 | 5540-1A(RHF) | 5540 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540-1NA -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2604-324-01 | 5540-2A(LHF) | 5540 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) -Base 26 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Back Cushion 26 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-02 | 5540-CSL | 5540-CSL | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-06 Sat | SO-2605-291-02 | 1005-(Q) | 4" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-06 Sat | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-06 Sat | SO-2605-132-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-064-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-064-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-064-01 | 5540-1A(LHF) | 5540 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Back Cushion | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-105-01 | 5540-1A(LHF) | 5540 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-221-01 | 5540-1A(LHF) | 5540 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-105-02 | 5540-1A(RHF) | 5540-1A(RHF) -Base | SOFA_BASE | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-105-02 | 5540-1A(RHF) | 5540 -Back Cushion | SOFA_CUSHION | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-064-02 | 5540-2A(RHF) | 5540-2A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-064-02 | 5540-2A(RHF) | 5540 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-064-02 | 5540-2A(RHF) | 5540 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-181-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-181-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-181-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-181-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-011-01 | DIVAN-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-18 | OVERDUE
2026-06-06 Sat | SO-2604-300-01 | DIVAN-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-08 Mon | SO-2605-291-01 | 1003(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-01 | 1003(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-02 | 1003(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-248-01 | 1007-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 1007-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-154-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-154-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-04 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-04 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-195-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-195-01 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-207-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-207-01 | 1007-(Q) | 1007-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-249-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-249-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-255-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-255-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112-2S -Base 30 | SOFA_BASE | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112 -Back Cushion 30 | SOFA_CUSHION | 2 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-01 | LATE
2026-06-09 Tue | SO-2605-203-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-192-04 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-04 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-215-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-02 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-185-01 | 1007-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-185-01 | 1007-(S) | 1007-(S) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-070-01 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-070-01 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-276-01 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-096-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-03 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-153-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-153-02 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-185-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-185-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-193-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-193-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-214-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-254-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-254-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-262-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-262-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-264-01 | 1013-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-278-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-215-03 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-03 | 1013-(S) | 1013-(S) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-04 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-04 | 1013-(S) | 1013-(S) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-254-02 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-254-02 | 1013-(S) | 1013-(S) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-01 | 1013-(SK) | 8" Divan- 200CMX200CM | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-070-02 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-070-02 | 1013-(SS) | 1013-(SS) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-262-02 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-262-02 | 1013-(SS) | 1013-(SS) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-277-01 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-01 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-02 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-299-01 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-02 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-03 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-300-02 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-210-01 | 2006(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-210-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-286-01 | 2006(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-099-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-099-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-192-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-02 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-02 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-03 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-209-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-01 | 2008(A)-(K) | 2008(A)-(K) -HB 25" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-02 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-02 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-238-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-02 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-02 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-03 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-03 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-258-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-263-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-263-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-099-02 | 2008(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-099-02 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-215-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-215-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-295-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-241-01 | 2009(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-247-01 | 2009(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-247-01 | 2009(A)-(K) | 2009(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-239-01 | 2009(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-04 | LATE
2026-06-11 Thu | SO-2605-239-01 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-04 | LATE
2026-06-11 Thu | SO-2605-241-02 | 2009(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-153-01 | 2038(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-153-01 | 2038(A)-(K) | 2038(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-140-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-11 Thu | SO-2605-140-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-11 Thu | SO-2605-209-03 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-209-03 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-209-04 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-279-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-298-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-280-01 | 2041(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-280-02 | 2041(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2604-293-02 | 5530-2A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-01 | 5530-1A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-130-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-01 | 5530-1A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-03 | 5530-1A(RHF) | 5530-1A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-03 | 5530-1A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-02 | 5530-1NA | 5530-1NA -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-02 | 5530-1NA | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-080-02 | 5530-2NA | 5530-2NA -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-02 | 5530-2NA | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-080-03 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-03 | 5530-L(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-03 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-04 | 5530-STOOL | 5530-STOOL | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-197-01 | 5531-1A(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-197-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-03 | LATE
2026-06-13 Sat | SO-2605-123-01 | 1003(A)-(SK) | 8" Divan- 200CMX200CM | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-281-01 | 1005-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-275-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-03 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-04 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-259-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-275-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-282-02 | 1007-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-297-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-071-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-071-01 | 5531-2A(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-071-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-071-02 | 5531-L(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-071-02 | 5531-L(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-02 | 5540-1NA | 5540-1NA -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-02 | 5540-1NA | 5540 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-03 | 5540-CSL | 5540-CSL | FG | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-300-01 | DIVAN-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-296-01 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-296-02 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-296-03 | DIVAN-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-283-01 | DIVAN-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-15 Mon | SO-2605-111-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-216-01 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-04 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-229-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-271-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-111-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-216-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-03 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-244-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-261-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-269-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-271-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-245-01 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-274-01 | 1023-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-288-02 | 1052-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-261-03 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-294-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-297-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2604-281-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-200-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-242-01 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-242-02 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-252-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-292-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-243-01 | 2009(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-211-01 | 2009(A)-(SK) | 8" Divan- 200CMX200CM | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-16 Tue | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-16 Tue | SO-2605-202-01 | 2033(HF)(W)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-202-02 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-235-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-288-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-123-02 | 2038(A)-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-16 Tue | SV-2605-003-01 | 5530-L(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-16 Tue | SV-2605-003-01 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-16 Tue | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 2 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-076-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-284-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-069-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-18 | AT-RISK
2026-06-17 Wed | SO-2605-069-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-18 | AT-RISK
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-228-01 | 1030-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-17 Wed | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-17 Wed | SO-2605-190-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 1 | Carress | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 28 | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Back Cushion 28 | SOFA_CUSHION | 2 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) -Base 28 | SOFA_BASE | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535 -Back Cushion 28 | SOFA_CUSHION | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-04 | 5536-2S | 5536-2S -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-04 | 5536-2S | 5536 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-04 | 5536-2S | 5536 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-04 | 5536-2S | 5536 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-02 | 5536-CNR | 5536-CNR -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-02 | 5536-CNR | 5536 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-206-01 | DIVAN-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-259-01 | DIVAN-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-200-02 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-200-03 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-265-01 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-265-02 | DIVAN-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-18 Thu | SO-2605-191-01 | 2006(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-18 Thu | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-18 Thu | SO-2605-260-01 | 2038(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-03 | 5530-STOOL | 5530-STOOL | SOFA_BASE | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531 -Back Cushion 28 | SOFA_CUSHION | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535-1A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) -Base 32 | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Back Cushion 32 | SOFA_CUSHION | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535-1NA -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535-1S -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) -Base 32 | SOFA_BASE | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Back Cushion 32 | SOFA_CUSHION | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Back Cushion 32 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) -Base 32 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535 -Back Cushion 32 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-19 Fri | SO-2605-189-01 | 1003(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-231-01 | 1003(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-302-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-231-02 | 2041(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530-L(RHF) -Base 28 | SOFA_BASE | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Back Cushion 28 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 2 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531-2S -Base 28 | SOFA_BASE | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Back Cushion 28 | SOFA_CUSHION | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531 -Right Arm | SOFA_ARMREST | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) -Base 24 | SOFA_BASE | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Back Cushion 24 | SOFA_CUSHION | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531 -Left Arm | SOFA_ARMREST | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-19 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-19 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-20 Sat | SV-2605-002-01 | 2006(A)-(K) | 12" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-20 Sat | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Left Arm | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530-2A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Right Arm | SOFA_ARMREST | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530-L(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536 -Right Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Back Cushion 30 | SOFA_CUSHION | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536 -Left Arm | SOFA_ARMREST | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536-CNR -Base 30 | SOFA_BASE | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536 -Back Cushion 30 | SOFA_CUSHION | 1 | Houzs Century | 2026-06-24 | ON-TIME

## 8-Pack
包装 Packing — 工序 Due Date 排程 (要做的 WIP 件,按到期先后)
Process Due 工序到期 | SO / PO | Model | WIP Item 件 | Type | Qty | Customer | Customer DD | Status
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-212-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-08 | 1003(A)-(Q) | 1003(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-187-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-124-01 | 1005-(Q) | 1005-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-07 | 1005-(Q) | 1005-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-157-01 | 1005-(Q) | 1005-(Q) -HB 25" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-02 | 1005-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-02 | 1005-(Q) | 1005-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-009-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-22 | OVERDUE
2026-06-02 Tue | SO-2605-023-01 | 1007-(K) | 1007-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-05-18 | OVERDUE
2026-06-02 Tue | SO-2605-160-02 | 1007-(Q) | 4" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-160-02 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-161-01 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-167-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-167-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-234-03 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | AT-RISK
2026-06-02 Tue | SO-2605-205-01 | 1007-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-01 | 1007-(S) | 1007-(S) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-02 | 1007-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-205-02 | 1007-(S) | 1007-(S) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-213-01 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-141-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-166-02 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | The Conts | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-186-01 | 1013-(SS) | 10" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-05-26 | OVERDUE
2026-06-02 Tue | SO-2605-186-01 | 1013-(SS) | 1013-(SS) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-05-26 | OVERDUE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-188-01 | 1013-(SS) | 1013-(SS) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2604-321-03 | 1023(HF)(W)-(SS) | 10" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-05-21 | OVERDUE
2026-06-02 Tue | SO-2604-321-03 | 1023(HF)(W)-(SS) | 1023(HF)(W)-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-21 | OVERDUE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-11 | 1041-(Q) | 1041-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-131-06 | 2003-(K) | 2003-(K) -HB 25" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-102-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-208-01 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-02 Tue | SO-2605-098-03 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2605-098-04 | 2008(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-29 | OVERDUE
2026-06-02 Tue | SO-2604-083-04 | LONG PILLOW | LONG PILLOW KN390-2 x2 | FG | 2 | Carress | 2026-04-15 | OVERDUE
2026-06-02 Tue | SO-2605-063-03 | LONG PILLOW | LONG PILLOW BO315-31 x2 | FG | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2604-088-03 | SQUARE PILLOW | SQUARE PILLOW BO315-31 x4 | FG | 4 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-02 Tue | SO-2604-092-03 | SQUARE PILLOW | SQUARE PILLOW CH141-5 x2 | FG | 2 | Houzs Century | 2026-04-29 | OVERDUE
2026-06-02 Tue | SO-2604-210-03 | SQUARE PILLOW | SQUARE PILLOW AM275-2 x2 | FG | 2 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-02 Tue | SO-2604-324-03 | SQUARE PILLOW | SQUARE PILLOW BO315-22 x2 | FG | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-02 Tue | SO-2605-104-04 | SQUARE PILLOW | SQUARE PILLOW | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-05 | SQUARE PILLOW | SQUARE PILLOW | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-104-06 | SQUARE PILLOW | SQUARE PILLOW | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-02 Tue | SO-2605-222-03 | SQUARE PILLOW | SQUARE PILLOW | FG | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-02 Tue | SO-2605-222-04 | SQUARE PILLOW | SQUARE PILLOW | FG | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-234-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-234-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-131-10 | 2009(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-131-10 | 2009(A)-(K) | 2009(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-171-01 | 2011(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-171-01 | 2011(A)-(K) | 2011(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-03 Wed | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-233-01 | 2038(A)(HF)(W)-(K) | 2038(A)(HF)(W)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-03 Wed | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-251-01 | 2038(A)(HF)(W)-(Q) | 2038(A)(HF)(W)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-02 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-02 | 2038(A)-(Q) | 2038(A)-(Q) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-03 | 2038(A)-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-204-03 | 2038(A)-(SS) | 2038(A)-(SS) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-010-02 | 2041(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-010-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-03 Wed | SO-2605-131-05 | 2041(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2605-131-05 | 2041(A)-(Q) | 2041(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-03 Wed | SO-2604-276-03 | 2041(A)-(SS) | 10" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-05-13 | OVERDUE
2026-06-03 Wed | SO-2604-276-03 | 2041(A)-(SS) | 2041(A)-(SS) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-05-13 | OVERDUE
2026-06-03 Wed | SO-2604-088-01 | 5530-1A(LHF) | 5530-1A(LHF) | FG | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-088-02 | 5530-1A(RHF) | 5530-1A(RHF) | FG | 1 | Houzs Century | 2026-05-04 | ON-HOLD
2026-06-03 Wed | SO-2604-086-01 | 5530-2A(RHF) | 5530-2A(RHF) | FG | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-03 Wed | SO-2604-265-02 | 5530-2A(RHF) | 5530-2A(RHF) | FG | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-03 Wed | SO-2604-086-02 | 5530-L(LHF) | 5530-L(LHF) | FG | 1 | Houzs Century | 2026-05-11 | OVERDUE
2026-06-04 Thu | SO-2605-050-01 | 5530-1A(LHF) | 5530-1A(LHF) | FG | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-050-02 | 5530-1A(RHF) | 5530-1A(RHF) | FG | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-04 Thu | SO-2605-063-05 | 5530-1NA | 5530-1NA | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-063-01 | 5530-2A(LHF) | 5530-2A(LHF) | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-109-01 | 5530-2A(LHF) | 5530-2A(LHF) | FG | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-265-01 | 5530-L(LHF) | 5530-L(LHF) | FG | 1 | Houzs Century | 2026-05-16 | OVERDUE
2026-06-04 Thu | SO-2605-063-02 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-109-02 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-079-01 | 5531-2A(LHF) | 5531-2A(LHF) | FG | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2604-327-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-072-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2604-345-03 | 5531-2S | 5531-2S | FG | 1 | Carress | 2026-05-27 | OVERDUE
2026-06-04 Thu | SO-2604-327-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-01 | LATE
2026-06-04 Thu | SO-2605-072-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-05-25 | OVERDUE
2026-06-04 Thu | SO-2605-079-02 | 5531-L(RHF) | 5531-L(RHF) | FG | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-067-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-01 | LATE
2026-06-05 Fri | SO-2605-104-01 | 5535-1A(LHF) | 5535-1A(LHF) | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-104-02 | 5535-1NA | 5535-1NA | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-222-01 | 5535-2A(LHF) | 5535-2A(LHF) | FG | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-104-03 | 5535-L(RHF) | 5535-L(RHF) | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-222-02 | 5535-L(RHF) | 5535-L(RHF) | FG | 1 | Houzs Century | 2026-05-30 | OVERDUE
2026-06-05 Fri | SO-2605-220-01 | 5536-2S | 5536-2S | FG | 1 | Houzs Century | 2026-05-27 | OVERDUE
2026-06-05 Fri | SO-2603-207-01 | 5537-1A(LHF) | 5537-1A(LHF) | FG | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2603-207-02 | 5537-1A(RHF) | 5537-1A(RHF) | FG | 1 | Houzs Century | 2026-05-04 | OVERDUE
2026-06-05 Fri | SO-2604-324-02 | 5540-1A(RHF) | 5540-1A(RHF) | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-221-03 | 5540-1A(RHF) | 5540-1A(RHF) | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2605-221-02 | 5540-1NA | 5540-1NA | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-05 Fri | SO-2604-324-01 | 5540-2A(LHF) | 5540-2A(LHF) | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-03 | 5540-2A(RHF) | 5540-2A(RHF) | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-02 | 5540-CSL | 5540-CSL | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-05 Fri | SO-2605-078-01 | 5540-L(LHF) | 5540-L(LHF) | FG | 1 | Houzs Century | 2026-05-25 | OVERDUE
2026-06-06 Sat | SO-2605-291-02 | 1005-(Q) | 4" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-06 Sat | SO-2605-291-02 | 1005-(Q) | 1005-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | ON-TIME
2026-06-06 Sat | SO-2605-132-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-06 Sat | SO-2605-064-01 | 5540-1A(LHF) | 5540-1A(LHF) | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-105-01 | 5540-1A(LHF) | 5540-1A(LHF) | FG | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-221-01 | 5540-1A(LHF) | 5540-1A(LHF) | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-105-02 | 5540-1A(RHF) | 5540-1A(RHF) | FG | 1 | Houzs Century | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-064-02 | 5540-2A(RHF) | 5540-2A(RHF) | FG | 1 | Houzs Century | 2026-05-28 | OVERDUE
2026-06-06 Sat | SO-2605-176-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-01 | LATE
2026-06-06 Sat | SO-2605-177-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-178-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-179-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-180-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-181-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-08 | AT-RISK
2026-06-06 Sat | SO-2605-011-01 | DIVAN-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-05-18 | OVERDUE
2026-06-08 Mon | SO-2605-291-01 | 1003(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-291-01 | 1003(A)-(K) | 1003(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-01 | 1003(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-02 | 1003(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-226-02 | 1003(A)-(Q) | 1003(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | AT-RISK
2026-06-08 Mon | SO-2605-248-01 | 1007-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-248-01 | 1007-(K) | 1007-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-256-01 | 1007-(K) | 1007-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-154-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-154-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-03 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-04 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-185-04 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-195-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-195-01 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-207-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-207-01 | 1007-(Q) | 1007-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-08 Mon | SO-2605-249-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-249-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-08 Mon | SO-2605-255-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-255-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2605-257-02 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-08 Mon | SO-2604-307-01 | 6112-2S | 6112-2S | FG | 10 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-173-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-174-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-01 | LATE
2026-06-08 Mon | SO-2605-175-01 | 6112-2S | 6112-2S | FG | 1 | The Conts | 2026-06-01 | LATE
2026-06-09 Tue | SO-2605-203-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-203-01 | 1007-(K) | 1007-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-192-04 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-192-04 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-215-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-02 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-185-01 | 1007-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-185-01 | 1007-(S) | 1007-(S) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-070-01 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-070-01 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-276-01 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-276-01 | 1013-(K) | 1013-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-096-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-02 | 1013-(Q) | 1013-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-03 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-03 | 1013-(Q) | 1013-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-153-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-153-02 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-185-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-185-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-193-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-193-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-214-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-214-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-09 Tue | SO-2605-254-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-254-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-262-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-262-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-264-01 | 1013-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-264-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-278-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-278-01 | 1013-(Q) | 1013-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-215-03 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-03 | 1013-(S) | 1013-(S) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-04 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-215-04 | 1013-(S) | 1013-(S) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-254-02 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-254-02 | 1013-(S) | 1013-(S) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-01 | 1013-(SK) | 8" Divan- 200CMX200CM | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-096-01 | 1013-(SK) | 1013-(SK) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-09 Tue | SO-2605-070-02 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-070-02 | 1013-(SS) | 1013-(SS) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-262-02 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-262-02 | 1013-(SS) | 1013-(SS) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-09 Tue | SO-2605-277-01 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-277-01 | 1013-(SS) | 1013-(SS) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-01 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-01 | 1013-(SS) | 1013-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-02 | 1013-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-285-02 | 1013-(SS) | 1013-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-09 Tue | SO-2605-299-01 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-01 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-02 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-02 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-03 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-09 Tue | SO-2605-299-03 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-300-02 | 1030-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-300-02 | 1030-(Q) | 1030-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-210-01 | 2006(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-210-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-04 | LATE
2026-06-10 Wed | SO-2605-286-01 | 2006(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-286-01 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-099-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-099-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-192-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-02 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-02 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-03 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-192-03 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-209-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-01 | 2008(A)-(K) | 2008(A)-(K) -HB 25" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-02 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-209-02 | 2008(A)-(K) | 2008(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-238-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-02 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-02 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-03 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-238-03 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-258-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-258-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-10 Wed | SO-2605-263-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-263-01 | 2008(A)-(K) | 2008(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-10 Wed | SO-2605-099-02 | 2008(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-10 Wed | SO-2605-099-02 | 2008(A)-(Q) | 2008(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-215-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-215-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-295-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-295-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-241-01 | 2009(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-241-01 | 2009(A)-(K) | 2009(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-247-01 | 2009(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-247-01 | 2009(A)-(K) | 2009(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-239-01 | 2009(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-04 | LATE
2026-06-11 Thu | SO-2605-239-01 | 2009(A)-(Q) | 2009(A)-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-04 | LATE
2026-06-11 Thu | SO-2605-241-02 | 2009(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-241-02 | 2009(A)-(Q) | 2009(A)-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-11 Thu | SO-2605-153-01 | 2038(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-153-01 | 2038(A)-(K) | 2038(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-140-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-05 | LATE
2026-06-11 Thu | SO-2605-140-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-11 Thu | SO-2605-209-03 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-209-03 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-209-04 | 2038(A)-(Q) | 2038(A)-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-279-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-279-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-11 Thu | SO-2605-298-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-298-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-11 Thu | SO-2605-280-01 | 2041(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-280-01 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-280-02 | 2041(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2605-280-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-11 Thu | SO-2604-293-02 | 5530-2A(RHF) | 5530-2A(RHF) | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-01 | 5530-1A(LHF) | 5530-1A(LHF) | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-130-01 | 5530-1A(LHF) | 5530-1A(LHF) | FG | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-03 | 5530-1A(RHF) | 5530-1A(RHF) | FG | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-130-02 | 5530-1NA | 5530-1NA | FG | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-240-02 | 5530-2A(RHF) | 5530-2A(RHF) | FG | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-080-02 | 5530-2NA | 5530-2NA | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2604-293-01 | 5530-L(LHF) | 5530-L(LHF) | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-240-01 | 5530-L(LHF) | 5530-L(LHF) | FG | 1 | Houzs Century | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-080-03 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-080-04 | 5530-STOOL | 5530-STOOL | FG | 1 | Houzs Century | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-183-01 | 5531-1A(LHF) | 5531-1A(LHF) | FG | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-197-01 | 5531-1A(LHF) | 5531-1A(LHF) | FG | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-183-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-194-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-196-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-08 | LATE
2026-06-12 Fri | SO-2605-197-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-03 | LATE
2026-06-12 Fri | SO-2605-194-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-03 | LATE
2026-06-13 Sat | SO-2605-123-01 | 1003(A)-(SK) | 8" Divan- 200CMX200CM | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-123-01 | 1003(A)-(SK) | 1003(A)-(SK) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-281-01 | 1005-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-281-01 | 1005-(Q) | 1005-(Q) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-275-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-275-01 | 1007-(K) | 1007-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-02 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-03 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-03 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-04 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-243-04 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-246-01 | 1007-(Q) | 1007-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-259-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-259-02 | 1007-(Q) | 1007-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-275-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-275-02 | 1007-(Q) | 1007-(Q) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-282-02 | 1007-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-282-02 | 1007-(Q) | 1007-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-13 Sat | SO-2605-297-02 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-297-02 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-02 | 1007-(SS) | 1007-(SS) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-292-03 | 1007-(SS) | 1007-(SS) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | ON-TIME
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-269-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-13 Sat | SO-2605-196-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-08 | LATE
2026-06-13 Sat | SO-2605-077-01 | 5540-1A(LHF) | 5540-1A(LHF) | FG | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-02 | 5540-1NA | 5540-1NA | FG | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-03 | 5540-CSL | 5540-CSL | FG | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-077-04 | 5540-L(RHF) | 5540-L(RHF) | FG | 1 | Houzs Century | 2026-06-02 | LATE
2026-06-13 Sat | SO-2605-300-01 | DIVAN-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-296-01 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-296-02 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-296-03 | DIVAN-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-06 | LATE
2026-06-13 Sat | SO-2605-283-01 | DIVAN-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-05 | LATE
2026-06-15 Mon | SO-2605-111-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-111-02 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-216-01 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-01 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-04 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-04 | 1013-(K) | 1013-(K) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-229-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-229-02 | 1013-(K) | 1013-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-271-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-271-02 | 1013-(K) | 1013-(K) -HB 26" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-02 | 1013-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-02 | 1013-(K) | 1013-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-111-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-111-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-216-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-03 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-216-03 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-244-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-244-01 | 1013-(Q) | 1013-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-261-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-02 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-02 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-269-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | The Conts | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-269-01 | 1013-(Q) | 1013-(Q) -HB 22" | HEADBOARD | 1 | The Conts | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-271-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-271-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-293-01 | 1013-(Q) | 1013-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | AT-RISK
2026-06-15 Mon | SO-2605-245-01 | 1013-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-245-01 | 1013-(S) | 1013-(S) -HB 16" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-274-01 | 1023-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-274-01 | 1023-(K) | 1023-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-15 Mon | SO-2605-288-02 | 1052-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-288-02 | 1052-(Q) | 1052-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-261-03 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-261-03 | 2006(A)-(K) | 2006(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-294-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-294-01 | 2006(A)-(K) | 2006(A)-(K) -HB 23" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-297-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-297-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-11 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-229-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-15 Mon | SO-2605-282-01 | 2008(A)-(K) | 2008(A)-(K) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2604-281-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2604-281-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-200-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-200-01 | 2008(A)-(K) | 2008(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-242-01 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-242-01 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-242-02 | 2008(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-242-02 | 2008(A)-(K) | 2008(A)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-252-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-252-01 | 2008(A)-(K) | 2008(A)-(K) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-292-01 | 2008(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-292-01 | 2008(A)-(K) | 2008(A)-(K) -HB 19" | HEADBOARD | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-16 Tue | SO-2605-243-01 | 2009(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-243-01 | 2009(A)-(K) | 2009(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-211-01 | 2009(A)-(SK) | 8" Divan- 200CMX200CM | DIVAN | 2 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-16 Tue | SO-2605-211-01 | 2009(A)-(SK) | 2009(A)-(SK) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-16 | AT-RISK
2026-06-16 Tue | SO-2605-202-01 | 2033(HF)(W)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-202-01 | 2033(HF)(W)-(K) | 2033(HF)(W)-(K) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-202-02 | 2033(HF)(W)-(SS) | 12" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-202-02 | 2033(HF)(W)-(SS) | 2033(HF)(W)-(SS) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-13 | LATE
2026-06-16 Tue | SO-2605-235-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-235-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 20" | HEADBOARD | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-16 Tue | SO-2605-288-01 | 2038(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-288-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-123-02 | 2038(A)-(SS) | 8" Divan- 3.5FT | DIVAN | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SO-2605-123-02 | 2038(A)-(SS) | 2038(A)-(SS) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-10 | LATE
2026-06-16 Tue | SV-2605-003-01 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century | 2026-06-09 | LATE
2026-06-16 Tue | SO-2605-076-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-284-01 | 1007-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-284-01 | 1007-(Q) | 1007-(Q) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-069-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-18 | AT-RISK
2026-06-17 Wed | SO-2605-069-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-18 | AT-RISK
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 8" Divan- 5FT | DIVAN | 2 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-289-01 | 1013-(Q) | 1013-(Q) -HB 24" | HEADBOARD | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-17 Wed | SO-2605-228-01 | 1030-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-17 Wed | SO-2605-228-01 | 1030-(K) | 1030-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-17 | AT-RISK
2026-06-17 Wed | SO-2605-190-01 | 2006(A)-(K) | 8" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-190-01 | 2006(A)-(K) | 2006(A)-(K) -HB 22" | HEADBOARD | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-17 Wed | SO-2605-237-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-076-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-237-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-13 | LATE
2026-06-17 Wed | SO-2605-270-01 | 5535-2A(LHF) | 5535-2A(LHF) | FG | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-270-02 | 5535-L(RHF) | 5535-L(RHF) | FG | 1 | The Conts | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-223-01 | 5536-1A(LHF) | 5536-1A(LHF) | FG | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-03 | 5536-2A(RHF) | 5536-2A(RHF) | FG | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-04 | 5536-2S | 5536-2S | FG | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-223-02 | 5536-CNR | 5536-CNR | FG | 1 | Houzs Century | 2026-06-15 | LATE
2026-06-17 Wed | SO-2605-206-01 | DIVAN-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-259-01 | DIVAN-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-10 | LATE
2026-06-17 Wed | SO-2605-200-02 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-200-03 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-265-01 | DIVAN-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-12 | LATE
2026-06-17 Wed | SO-2605-265-02 | DIVAN-(S) | 8" Divan- 3FT | DIVAN | 1 | Houzs Century | 2026-06-12 | LATE
2026-06-18 Thu | SO-2605-191-01 | 2006(A)-(Q) | 8" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-18 Thu | SO-2605-191-01 | 2006(A)-(Q) | 2006(A)-(Q) -HB 21" | HEADBOARD | 1 | Houzs Century | 2026-06-19 | AT-RISK
2026-06-18 Thu | SO-2605-260-01 | 2038(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-260-01 | 2038(A)-(Q) | 2038(A)-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-290-01 | 5530-1A(LHF) | 5530-1A(LHF) | FG | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-02 | 5530-2A(RHF) | 5530-2A(RHF) | FG | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-290-03 | 5530-STOOL | 5530-STOOL | FG | 1 | Houzs Century | 2026-06-19 | ON-TIME
2026-06-18 Thu | SO-2605-236-01 | 5531-2A(LHF) | 5531-2A(LHF) | FG | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-236-02 | 5531-L(RHF) | 5531-L(RHF) | FG | 1 | Carress | 2026-06-17 | LATE
2026-06-18 Thu | SO-2605-106-01 | 5535-1A(LHF) | 5535-1A(LHF) | FG | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-04 | 5535-1A(LHF) | 5535-1A(LHF) | FG | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-03 | 5535-1A(RHF) | 5535-1A(RHF) | FG | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-05 | 5535-1A(RHF) | 5535-1A(RHF) | FG | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-02 | 5535-1A(RHF) | 5535-1A(RHF) | FG | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-02 | 5535-1NA | 5535-1NA | FG | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-106-06 | 5535-1S | 5535-1S | FG | 1 | Houzs Century | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-303-01 | 5535-2A(LHF) | 5535-2A(LHF) | FG | 1 | Carress | 2026-06-22 | ON-TIME
2026-06-18 Thu | SO-2605-273-02 | 5535-2A(RHF) | 5535-2A(RHF) | FG | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-273-01 | 5535-L(LHF) | 5535-L(LHF) | FG | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-18 Thu | SO-2605-225-02 | 5536-1A(RHF) | 5536-1A(RHF) | FG | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-19 Fri | SO-2605-189-01 | 1003(A)-(K) | 10" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-189-01 | 1003(A)-(K) | 1003(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-231-01 | 1003(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-231-01 | 1003(A)-(Q) | 1003(A)-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-302-01 | 1007-(K) | 8" Divan- 6FT | DIVAN | 2 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-302-01 | 1007-(K) | 1007-(K) -HB 28" | HEADBOARD | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-231-02 | 2041(A)-(Q) | 10" Divan- 5FT | DIVAN | 2 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-231-02 | 2041(A)-(Q) | 2041(A)-(Q) -HB 24" | HEADBOARD | 1 | Houzs Century | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-199-01 | 5530-2A(LHF) | 5530-2A(LHF) | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-01 | 5530-2A(LHF) | 5530-2A(LHF) | FG | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-198-02 | 5530-2A(RHF) | 5530-2A(RHF) | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-198-01 | 5530-L(LHF) | 5530-L(LHF) | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-199-02 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-19 Fri | SO-2605-224-02 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century | 2026-06-26 | ON-TIME
2026-06-19 Fri | SO-2605-182-02 | 5531-2A(RHF) | 5531-2A(RHF) | FG | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-301-01 | 5531-2S | 5531-2S | FG | 1 | Carress | 2026-06-29 | ON-TIME
2026-06-19 Fri | SO-2605-182-01 | 5531-L(LHF) | 5531-L(LHF) | FG | 1 | Carress | 2026-06-25 | ON-TIME
2026-06-19 Fri | SO-2605-225-01 | 5536-1A(LHF) | 5536-1A(LHF) | FG | 1 | Houzs Century | 2026-06-16 | LATE
2026-06-20 Sat | SV-2605-002-01 | 2006(A)-(K) | 12" Divan- 6FT | DIVAN | 2 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-20 Sat | SV-2605-002-01 | 2006(A)-(K) | 2006(A)-(K) -HB 26" | HEADBOARD | 1 | Houzs Century | 2026-07-08 | ON-TIME
2026-06-20 Sat | CO-2605-008-01 | 5530-2A(LHF) | 5530-2A(LHF) | FG | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | CO-2605-008-02 | 5530-L(RHF) | 5530-L(RHF) | FG | 1 | Houzs Century |  | ON-TIME
2026-06-20 Sat | SO-2605-184-03 | 5536-1A(RHF) | 5536-1A(RHF) | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-01 | 5536-2A(LHF) | 5536-2A(LHF) | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME
2026-06-20 Sat | SO-2605-184-02 | 5536-CNR | 5536-CNR | FG | 1 | Houzs Century | 2026-06-24 | ON-TIME