## Summary & Notes
生产计划表 Production Planning
生成日期 Generated: 2026-06-01 第一个开工天 First working day: 2026-06-02
【这张表的规矩 The rules you set】
1. 数量一律算 1 —— 一行 = 一套 = 一件。订单本来每一行就是数量 1,这里全部照 1 走。
2. 一套不拆开 —— 沙发的角位 / 1A / 2A / 凳 / L 位… 已经併成一行(就是你切料时併好的那一排)。
3. 同款排在一起 —— 按款号(Model)分组排序,方便一次过看同款有几单。
4. 两个日期分两栏 —— Customer DD = 顾客要的交货日;Our Expected DD = 我们内部预计做好的日。
(这两个不一样,所以分开放,不会再混成一栏。)
【这次发现的 Bug — 你问的「为什么 Quantity 会有 2、3、4」】
系统旧的「Qty」栏,拿错了数字:
· 它显示的不是『订单数量』,而是『切料要切几片 / 几个格』。
· 沙发:你把整套(角位+1A+2A+凳…)併成一排切,系统却把『併进来的格数』当成数量 ——
所以 5540-1A(LHF)+1NA+CSL+L(RHF) 这种一套,会显示成 4;有六个格的显示成 6。
· 床架:Queen / King 一张床要两片布,系统又把『布的片数 2』当成数量。
· 真相:这些其实全部都是『一套』『一张』—— 数量就是 1。你查的那张 D1 就是这样:只有一个数量,却被叫去切两片。
· 全部 262 行里,有 55 行被系统显示成多过 1。这 55 行列在「Qty Bug」那一页,你可以逐张对。
· 这张计划表已经把它改回正确的 1。系统里那一栏要不要也跟着改,我先不动,等你点头(因为那个数字还连着贴纸张数、用布、工时,要一起想清楚)。
【数字一览 Headline】
在排的总行数 Active rows: 262 (PENDING + ON_HOLD,做好的和取消的不算)
款号种类 Models: 28
分类 By category: 床架 Bedframe 189 / 沙发 Sofa 59 / 配件 Accessory 14
系统旧 Qty 分布 (本应全是 1): {1: 207, 2: 42, 3: 8, 4: 4, 6: 1}
没填 Customer DD 的: 1 行 (那张寄卖单 CO 没有顾客交期)
【分页说明 Sheets】
· Production Planning:正式计划表 —— 数量全 1、一套一行、同款一起、两个日期分栏。
· Qty Bug (system mis-count):被系统数错的那几行,左边是系统现在显示的错数字,右边是正确的 1。
注:这张表只读了线上资料来做,没有改动系统任何东西。

## Production Planning
Model | SO / CO No | Customer | Item (one set per row) | Category | Fabric | Qty | Customer DD | Our Expected DD | Status
1003(A) | SO-2605-187-01 | Houzs Century | 1003(A)-(Q) | Bedframe | PC151-14 | 1 | 2026-05-30 | 2026-05-28 | PENDING
1003(A) | SO-2605-131-08 | Houzs Century | 1003(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1003(A) | SO-2605-212-01 | Houzs Century | 1003(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1003(A) | SO-2605-226-01 | Houzs Century | 1003(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1003(A) | SO-2605-226-02 | Houzs Century | 1003(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1003(A) | SO-2605-291-01 | Houzs Century | 1003(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1003(A) | SO-2605-123-01 | Houzs Century | 1003(A)-(SK) | Bedframe | PC151-02 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1003(A) | SO-2605-189-01 | Houzs Century | 1003(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-24 | 2026-06-22 | PENDING
1003(A) | SO-2605-231-01 | Houzs Century | 1003(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-25 | 2026-06-23 | PENDING
1005 | SO-2605-124-01 | Houzs Century | 1005-(Q) | Bedframe | PC151-02 | 1 | 2026-05-29 | 2026-05-27 | PENDING
1005 | SO-2605-131-07 | Houzs Century | 1005-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1005 | SO-2605-157-01 | Houzs Century | 1005-(Q) | Bedframe | PC151-04 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1005 | SO-2605-234-02 | Houzs Century | 1005-(Q) | Bedframe | PC151-01 | 1 | 2026-06-02 | 2026-05-31 | PENDING
1005 | SO-2605-291-02 | Houzs Century | 1005-(Q) | Bedframe | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1005 | SO-2605-281-01 | Houzs Century | 1005-(Q) | Bedframe | PC151-03 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1007 | SO-2605-023-01 | Houzs Century | 1007-(K) | Bedframe | PC151-01 | 1 | 2026-05-18 | 2026-05-16 | PENDING
1007 | SO-2605-009-01 | Houzs Century | 1007-(K) | Bedframe | PC151-01 | 1 | 2026-05-22 | 2026-05-20 | PENDING
1007 | SO-2605-160-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-05-25 | 2026-05-23 | PENDING
1007 | SO-2605-161-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-11 | 1 | 2026-05-25 | 2026-05-23 | PENDING
1007 | SO-2605-167-01 | The Conts | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1007 | SO-2605-205-01 | Houzs Century | 1007-(S) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1007 | SO-2605-205-02 | Houzs Century | 1007-(S) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1007 | SO-2605-234-03 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-02 | 2026-05-31 | PENDING
1007 | SO-2605-154-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-02 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1007 | SO-2605-195-01 | Carress | 1007-(Q) | Bedframe | PC151-17 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1007 | SO-2605-207-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1007 | SO-2605-248-01 | Houzs Century | 1007-(K) | Bedframe | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1007 | SO-2605-249-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-17 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1007 | SO-2605-185-01 | Houzs Century | 1007-(S) | Bedframe | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-185-03 | Houzs Century | 1007-(Q) | Bedframe | PC151-08 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-185-04 | Houzs Century | 1007-(Q) | Bedframe | PC151-09 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-192-04 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-255-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-256-01 | Houzs Century | 1007-(K) | Bedframe | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-257-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-257-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1007 | SO-2605-215-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1007 | SO-2605-203-01 | Houzs Century | 1007-(K) | Bedframe | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1007 | SO-2605-259-02 | Carress | 1007-(Q) | Bedframe | PC151-14 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1007 | SO-2605-297-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-11 | 2026-06-09 | PENDING
1007 | SO-2605-243-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-243-03 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-243-04 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-246-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-275-01 | Houzs Century | 1007-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-275-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-282-02 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
1007 | SO-2605-292-02 | Houzs Century | 1007-(SS) | Bedframe | PC151-03 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1007 | SO-2605-292-03 | Houzs Century | 1007-(SS) | Bedframe | PC151-03 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1007 | SO-2605-284-01 | Houzs Century | 1007-(Q) | Bedframe | PC151-01 | 1 | 2026-06-19 | 2026-06-17 | PENDING
1007 | SO-2605-302-01 | Carress | 1007-(K) | Bedframe | PC151-15 | 1 | 2026-06-29 | 2026-06-27 | PENDING
1013 | SO-2605-186-01 | Houzs Century | 1013-(SS) | Bedframe | PC151-03 | 1 | 2026-05-26 | 2026-05-24 | PENDING
1013 | SO-2605-141-01 | Carress | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1013 | SO-2605-166-01 | The Conts | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1013 | SO-2605-166-02 | The Conts | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1013 | SO-2605-188-01 | Houzs Century | 1013-(SS) | Bedframe | PC151-13 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1013 | SO-2605-213-01 | Houzs Century | 1013-(K) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1013 | SO-2605-227-01 | Houzs Century | 1013-(K) | Bedframe | PC151-03 | 1 | 2026-06-02 | 2026-05-31 | PENDING
1013 | SO-2605-153-02 | Houzs Century | 1013-(Q) | Bedframe | PC151-03 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1013 | SO-2605-193-01 | Carress | 1013-(Q) | Bedframe | PC151-03 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1013 | SO-2605-214-01 | Houzs Century | 1013-(Q) | Bedframe | KS-14 | 1 | 2026-06-03 | 2026-06-01 | PENDING
1013 | SO-2605-096-01 | Houzs Century | 1013-(SK) | Bedframe | PC151-10 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1013 | SO-2605-096-02 | Houzs Century | 1013-(Q) | Bedframe | PC151-10 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1013 | SO-2605-096-03 | Houzs Century | 1013-(Q) | Bedframe | PC151-10 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1013 | SO-2605-254-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1013 | SO-2605-254-02 | Houzs Century | 1013-(S) | Bedframe | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1013 | SO-2605-278-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-02 | 1 | 2026-06-04 | 2026-06-02 | PENDING
1013 | SO-2605-185-02 | Houzs Century | 1013-(Q) | Bedframe | PC151-14 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1013 | SO-2605-262-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1013 | SO-2605-262-02 | Houzs Century | 1013-(SS) | Bedframe | PC151-17 | 1 | 2026-06-05 | 2026-06-03 | PENDING
1013 | SO-2605-215-03 | Houzs Century | 1013-(S) | Bedframe | PC151-09 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1013 | SO-2605-215-04 | Houzs Century | 1013-(S) | Bedframe | PC151-08 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1013 | SO-2605-070-01 | Carress | 1013-(K) | Bedframe | PC151-01 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-070-02 | Carress | 1013-(SS) | Bedframe | PC151-18 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-264-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-04 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-276-01 | Houzs Century | 1013-(K) | Bedframe | PC151-12 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-277-01 | Houzs Century | 1013-(SS) | Bedframe | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-285-01 | Houzs Century | 1013-(SS) | Bedframe | PC151-09 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-285-02 | Houzs Century | 1013-(SS) | Bedframe | PC151-11 | 1 | 2026-06-08 | 2026-06-06 | PENDING
1013 | SO-2605-229-02 | Houzs Century | 1013-(K) | Bedframe | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1013 | SO-2605-244-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-02 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1013 | SO-2605-245-01 | Houzs Century | 1013-(S) | Bedframe | PC151-02 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1013 | SO-2605-269-01 | The Conts | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1013 | SO-2605-269-02 | The Conts | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
1013 | SO-2605-111-01 | Carress | 1013-(Q) | Bedframe | PC151-17 | 1 | 2026-06-11 | 2026-06-09 | PENDING
1013 | SO-2605-111-02 | Carress | 1013-(K) | Bedframe | PC151-17 | 1 | 2026-06-11 | 2026-06-09 | PENDING
1013 | SO-2605-261-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-11 | 2026-06-09 | PENDING
1013 | SO-2605-261-02 | Houzs Century | 1013-(Q) | Bedframe | PC151-15 | 1 | 2026-06-11 | 2026-06-09 | PENDING
1013 | SO-2605-216-01 | Carress | 1013-(K) | Bedframe | PC151-14 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-216-02 | Carress | 1013-(Q) | Bedframe | PC151-06 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-216-03 | Carress | 1013-(Q) | Bedframe | PC151-15 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-216-04 | Carress | 1013-(K) | Bedframe | PC151-13 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-271-01 | Carress | 1013-(Q) | Bedframe | PC151-17 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-271-02 | Carress | 1013-(K) | Bedframe | PC151-17 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-293-01 | Houzs Century | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-293-02 | Houzs Century | 1013-(K) | Bedframe | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
1013 | SO-2605-069-01 | Carress | 1013-(Q) | Bedframe | PC151-13 | 1 | 2026-06-18 | 2026-06-16 | PENDING
1013 | SO-2605-289-01 | Carress | 1013-(Q) | Bedframe | PC151-01 | 1 | 2026-06-22 | 2026-06-20 | PENDING
1023 | SO-2605-274-01 | Houzs Century | 1023-(K) | Bedframe | PC151-01 | 1 | 2026-06-16 | 2026-06-14 | PENDING
1023(HF)(W) | SO-2604-321-03 | Houzs Century | 1023(HF)(W)-(SS) | Bedframe | PC151-02 | 1 | 2026-05-21 | 2026-05-19 | PENDING
1030 | SO-2605-299-01 | Houzs Century | 1030-(Q) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1030 | SO-2605-299-02 | Houzs Century | 1030-(Q) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1030 | SO-2605-299-03 | Houzs Century | 1030-(Q) | Bedframe | PC151-18 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1030 | SO-2605-300-02 | Houzs Century | 1030-(Q) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
1030 | SO-2605-228-01 | Houzs Century | 1030-(K) | Bedframe | PC151-01 | 1 | 2026-06-17 | 2026-06-15 | PENDING
1041 | SO-2605-131-11 | Houzs Century | 1041-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
1052 | SO-2605-288-02 | Houzs Century | 1052-(Q) | Bedframe | PC151-17 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2003 | SO-2605-131-06 | Houzs Century | 2003-(K) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2006(A) | SO-2605-102-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-17 | 1 | 2026-05-30 | 2026-05-28 | PENDING
2006(A) | SO-2605-132-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-04 | 2026-06-02 | PENDING
2006(A) | SO-2605-210-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-14 | 1 | 2026-06-04 | 2026-06-02 | PENDING
2006(A) | SO-2605-286-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
2006(A) | SO-2605-261-03 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-02 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2006(A) | SO-2605-297-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-11 | 2026-06-09 | PENDING
2006(A) | SO-2605-294-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2006(A) | SO-2605-190-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-19 | 2026-06-17 | PENDING
2006(A) | SO-2605-191-01 | Houzs Century | 2006(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-19 | 2026-06-17 | PENDING
2006(A) | SV-2605-002-01 | Houzs Century | 2006(A)-(K) | Bedframe | PC151-14 | 1 | 2026-07-08 | 2026-07-06 | PENDING
2008(A) | SO-2605-162-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-10 | 1 | 2026-05-25 | 2026-05-23 | PENDING
2008(A) | SO-2605-098-03 | Houzs Century | 2008(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-05-29 | 2026-05-27 | PENDING
2008(A) | SO-2605-098-04 | Houzs Century | 2008(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-05-29 | 2026-05-27 | PENDING
2008(A) | SO-2605-208-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-04 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2008(A) | SO-2605-234-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-03 | 1 | 2026-06-02 | 2026-05-31 | PENDING
2008(A) | SO-2605-099-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2008(A) | SO-2605-099-02 | Houzs Century | 2008(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2008(A) | SO-2605-209-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2008(A) | SO-2605-209-02 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2008(A) | SO-2605-192-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-192-02 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-12 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-192-03 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-10 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-238-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-238-02 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-238-03 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-263-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2008(A) | SO-2605-215-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
2008(A) | SO-2605-258-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-04 | 1 | 2026-06-06 | 2026-06-04 | PENDING
2008(A) | SO-2605-295-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
2008(A) | SO-2605-229-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2008(A) | SO-2604-281-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2008(A) | SO-2605-200-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2008(A) | SO-2605-282-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2008(A) | SO-2605-242-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2008(A) | SO-2605-242-02 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-12 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2008(A) | SO-2605-252-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2008(A) | SO-2605-292-01 | Houzs Century | 2008(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-15 | 2026-06-13 | PENDING
2009(A) | SO-2605-131-10 | Houzs Century | 2009(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2009(A) | SO-2605-247-01 | Houzs Century | 2009(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2009(A) | SO-2605-239-01 | Carress | 2009(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-04 | 2026-06-02 | PENDING
2009(A) | SO-2605-241-01 | Houzs Century | 2009(A)-(K) | Bedframe | PC151-06 | 1 | 2026-06-09 | 2026-06-07 | PENDING
2009(A) | SO-2605-241-02 | Houzs Century | 2009(A)-(Q) | Bedframe | PC151-15 | 1 | 2026-06-09 | 2026-06-07 | PENDING
2009(A) | SO-2605-243-01 | Houzs Century | 2009(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2009(A) | SO-2605-211-01 | Houzs Century | 2009(A)-(SK) | Bedframe | PC151-01 | 1 | 2026-06-16 | 2026-06-14 | PENDING
2011(A) | SO-2605-171-01 | Houzs Century | 2011(A)-(K) | Bedframe | KS-18 | 1 | 2026-05-25 | 2026-05-23 | PENDING
2033(HF)(W) | SO-2605-202-01 | Houzs Century | 2033(HF)(W)-(K) | Bedframe | PC151-02 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2033(HF)(W) | SO-2605-202-02 | Houzs Century | 2033(HF)(W)-(SS) | Bedframe | PC151-02 | 1 | 2026-06-13 | 2026-06-11 | PENDING
2038(A) | SO-2605-204-02 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-10 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2038(A) | SO-2605-204-03 | Houzs Century | 2038(A)-(SS) | Bedframe | PC151-11 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2038(A) | SO-2605-153-01 | Houzs Century | 2038(A)-(K) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2038(A) | SO-2605-209-03 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2038(A) | SO-2605-209-04 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2038(A) | SO-2605-279-01 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-03 | 2026-06-01 | PENDING
2038(A) | SO-2605-140-01 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-13 | 1 | 2026-06-05 | 2026-06-03 | PENDING
2038(A) | SO-2605-298-01 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
2038(A) | SO-2605-123-02 | Houzs Century | 2038(A)-(SS) | Bedframe | PC151-03 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2038(A) | SO-2605-288-01 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-10 | 2026-06-08 | PENDING
2038(A) | SO-2605-235-01 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-12 | 2026-06-10 | PENDING
2038(A) | SO-2605-260-01 | Houzs Century | 2038(A)-(Q) | Bedframe | PC151-10 | 1 | 2026-06-17 | 2026-06-15 | PENDING
2038(A)(HF)(W) | SO-2605-251-01 | Houzs Century | 2038(A)(HF)(W)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2038(A)(HF)(W) | SO-2605-233-01 | Houzs Century | 2038(A)(HF)(W)-(K) | Bedframe | PC151-12 | 1 | 2026-06-02 | 2026-05-31 | PENDING
2041(A) | SO-2604-276-03 | Houzs Century | 2041(A)-(SS) | Bedframe | PC151-02 | 1 | 2026-05-13 | 2026-05-11 | PENDING
2041(A) | SO-2605-010-02 | Houzs Century | 2041(A)-(Q) | Bedframe | PC151-11 | 1 | 2026-05-30 | 2026-05-28 | PENDING
2041(A) | SO-2605-131-05 | Houzs Century | 2041(A)-(Q) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
2041(A) | SO-2605-280-01 | Houzs Century | 2041(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
2041(A) | SO-2605-280-02 | Houzs Century | 2041(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-08 | 2026-06-06 | PENDING
2041(A) | SO-2605-231-02 | Houzs Century | 2041(A)-(Q) | Bedframe | PC151-02 | 1 | 2026-06-25 | 2026-06-23 | PENDING
5530 | SO-2604-088-01 | Houzs Century | 5530-1A(LHF)+1A(RHF)+1A(LHF)+1A(RHF) | Sofa | BO315-21 | 1 | 2026-05-04 | 2026-05-03 | ON_HOLD
5530 | SO-2604-086-01 | Houzs Century | 5530-2A(RHF)+L(LHF) | Sofa | BO315-12 | 1 | 2026-05-11 | 2026-05-10 | PENDING
5530 | SO-2604-265-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | Sofa | CH141-13 | 1 | 2026-05-16 | 2026-05-14 | PENDING
5530 | CO-2605-008-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | Sofa | PC151-01 | 1 |  | 2026-05-15 | PENDING
5530 | SO-2605-063-01 | Houzs Century | 5530-2A(LHF)+L(RHF)+1NA | Sofa | BO315-31 | 1 | 2026-05-25 | 2026-05-24 | PENDING
5530 | SO-2605-050-01 | Houzs Century | 5530-1A(LHF)+1A(RHF) | Sofa | BO315-1 | 1 | 2026-05-30 | 2026-05-28 | PENDING
5530 | SO-2605-109-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | Sofa | BO315-21 | 1 | 2026-06-01 | 2026-05-31 | PENDING
5530 | SO-2604-293-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | Sofa | CH141-12 | 1 | 2026-06-03 | 2026-06-01 | PENDING
5530 | SO-2605-051-01 | Houzs Century | 5530-1A(LHF)+1NA+1A(RHF) | Sofa | CH141-11 | 1 | 2026-06-02 | 2026-06-01 | PENDING
5530 | SO-2605-080-01 | Houzs Century | 5530-1A(LHF)+2NA+L(RHF)+STOOL | Sofa | BO315-25 | 1 | 2026-06-03 | 2026-06-02 | PENDING
5530 | SO-2605-130-01 | Houzs Century | 5530-1A(LHF)+1NA+1A(RHF) | Sofa | BO315-1 | 1 | 2026-06-08 | 2026-06-07 | PENDING
5530 | SO-2605-240-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | Sofa | BO315-22 | 1 | 2026-06-08 | 2026-06-07 | PENDING
5530 | SV-2605-003-01 | Houzs Century | 5530-L(RHF) | Sofa | BO315-2 | 1 | 2026-06-09 | 2026-06-08 | PENDING
5530 | SO-2605-290-01 | Houzs Century | 5530-1A(LHF)+2A(RHF)+STOOL | Sofa | BO315-21 | 1 | 2026-06-19 | 2026-06-18 | PENDING
5530 | SO-2605-198-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | Sofa | BO315-3 | 1 | 2026-06-24 | 2026-06-23 | PENDING
5530 | SO-2605-199-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | Sofa | BO315-3 | 1 | 2026-06-24 | 2026-06-23 | PENDING
5530 | SO-2605-224-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | Sofa | M2402-4 | 1 | 2026-06-26 | 2026-06-25 | PENDING
5531 | SO-2605-072-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | KN390-14 | 1 | 2026-05-25 | 2026-05-24 | PENDING
5531 | SO-2604-327-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | NINJA 08 | 1 | 2026-06-01 | 2026-05-30 | PENDING
5531 | SO-2605-067-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | KN390-2 | 1 | 2026-06-01 | 2026-05-31 | PENDING
5531 | SO-2605-079-01 | Carress | 5531-2A(LHF)+L(RHF) | Sofa | M2402-13 | 1 | 2026-06-01 | 2026-05-31 | PENDING
5531 | SO-2605-194-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | GARFIELD - 3 TUNDORA | 1 | 2026-06-03 | 2026-06-02 | PENDING
5531 | SO-2605-197-01 | Carress | 5531-1A(LHF)+2A(RHF) | Sofa | M2402-4 | 1 | 2026-06-03 | 2026-06-02 | PENDING
5531 | SO-2605-071-01 | Carress | 5531-2A(LHF)+L(RHF) | Sofa | NINJA 02 | 1 | 2026-06-08 | 2026-06-07 | PENDING
5531 | SO-2605-183-01 | Carress | 5531-1A(LHF)+2A(RHF) | Sofa | M2402-18 | 1 | 2026-06-08 | 2026-06-07 | PENDING
5531 | SO-2605-196-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | KN390-2 | 1 | 2026-06-08 | 2026-06-07 | PENDING
5531 | SO-2605-076-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | GARFIELD-2 CHERVRON | 1 | 2026-06-12 | 2026-06-11 | PENDING
5531 | SO-2605-237-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | KN390-1 | 1 | 2026-06-13 | 2026-06-12 | PENDING
5531 | SO-2605-236-01 | Carress | 5531-2A(LHF)+L(RHF) | Sofa | M2402-1 | 1 | 2026-06-17 | 2026-06-16 | PENDING
5531 | SO-2605-182-01 | Carress | 5531-L(LHF)+2A(RHF) | Sofa | NINJA 02 | 1 | 2026-06-25 | 2026-06-24 | PENDING
5531 | SO-2605-301-01 | Carress | 5531-2S | Sofa | M2402-13 | 1 | 2026-06-29 | 2026-06-28 | PENDING
5535 | SO-2605-104-01 | Houzs Century | 5535-1A(LHF)+1NA+L(RHF) | Sofa | BO315-1 | 1 | 2026-05-28 | 2026-05-27 | PENDING
5535 | SO-2605-222-01 | Houzs Century | 5535-2A(LHF)+L(RHF) | Sofa | CH141-14 | 1 | 2026-05-30 | 2026-05-29 | PENDING
5535 | SO-2605-270-01 | The Conts | 5535-2A(LHF)+L(RHF) | Sofa | PC151-01 | 1 | 2026-06-10 | 2026-06-09 | PENDING
5535 | SO-2605-273-01 | Houzs Century | 5535-L(LHF)+2A(RHF) | Sofa | BO315-24 | 1 | 2026-06-16 | 2026-06-15 | PENDING
5535 | SO-2605-106-01 | Houzs Century | 5535-1A(LHF)+1NA+1A(RHF)+1A(LHF)+1A(RHF)+1S | Sofa | M2402-4 | 1 | 2026-06-22 | 2026-06-21 | PENDING
5535 | SO-2605-303-01 | Carress | 5535-2A(LHF)+1A(RHF) | Sofa | KN390-3 | 1 | 2026-06-22 | 2026-06-21 | PENDING
5536 | SO-2605-220-01 | Houzs Century | 5536-2S | Sofa | BO315-23 | 1 | 2026-05-27 | 2026-05-26 | PENDING
5536 | SO-2605-223-01 | Houzs Century | 5536-1A(LHF)+CNR+2A(RHF)+2S | Sofa | FABRIC HR805-90 | 1 | 2026-06-15 | 2026-06-14 | PENDING
5536 | SO-2605-225-01 | Houzs Century | 5536-1A(LHF)+1A(RHF) | Sofa | NINJA 02 | 1 | 2026-06-16 | 2026-06-15 | PENDING
5536 | SO-2605-184-01 | Houzs Century | 5536-2A(LHF)+CNR+1A(RHF) | Sofa | BO315-5 | 1 | 2026-06-24 | 2026-06-23 | PENDING
5537 | SO-2603-207-01 | Houzs Century | 5537-1A(LHF)+1A(RHF) | Sofa | CH141-1 | 1 | 2026-05-04 | 2026-05-03 | PENDING
5540 | SO-2604-324-01 | Houzs Century | 5540-2A(LHF)+1A(RHF) | Sofa | BO315-22 | 1 | 2026-05-25 | 2026-05-23 | PENDING
5540 | SO-2605-078-01 | Houzs Century | 5540-L(LHF)+CSL+2A(RHF) | Sofa | BO315-23 | 1 | 2026-05-25 | 2026-05-24 | PENDING
5540 | SO-2605-108-01 | Houzs Century | 5540-2S | Sofa | BO315-21 | 1 | 2026-05-25 | 2026-05-24 | PENDING
5540 | SO-2605-064-01 | Houzs Century | 5540-1A(LHF)+2A(RHF) | Sofa | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
5540 | SO-2605-221-01 | Houzs Century | 5540-1A(LHF)+1NA+1A(RHF) | Sofa | AM275-1 | 1 | 2026-05-28 | 2026-05-27 | PENDING
5540 | SO-2605-105-01 | Houzs Century | 5540-1A(LHF)+1A(RHF) | Sofa | BO315-31 | 1 | 2026-06-01 | 2026-05-31 | PENDING
5540 | SO-2605-077-01 | Houzs Century | 5540-1A(LHF)+1NA+CSL+L(RHF) | Sofa | FABRIC HR805-10 | 1 | 2026-06-02 | 2026-06-01 | PENDING
6112 | SO-2604-307-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
6112 | SO-2605-173-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
6112 | SO-2605-174-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
6112 | SO-2605-175-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
6112 | SO-2605-176-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
6112 | SO-2605-177-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
6112 | SO-2605-178-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
6112 | SO-2605-179-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
6112 | SO-2605-180-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
6112 | SO-2605-181-01 | The Conts | 6112-2S | Sofa | PC151-01 | 1 | 2026-06-08 | 2026-05-30 | PENDING
DIVAN | SO-2605-011-01 | Houzs Century | DIVAN-(K) | Bedframe | KS-02 | 1 | 2026-05-18 | 2026-05-16 | PENDING
DIVAN | SO-2604-300-01 | Houzs Century | DIVAN-(Q) | Bedframe | PC151-01 | 1 | 2026-05-25 | 2026-05-23 | PENDING
DIVAN | SO-2605-131-04 | Houzs Century | DIVAN-(K) | Bedframe | PC151-01 | 1 | 2026-06-01 | 2026-05-30 | PENDING
DIVAN | SO-2605-283-01 | Houzs Century | DIVAN-(SS) | Bedframe | PC151-01 | 1 | 2026-06-05 | 2026-06-03 | PENDING
DIVAN | SO-2605-296-01 | Houzs Century | DIVAN-(Q) | Bedframe | PC151-03 | 1 | 2026-06-06 | 2026-06-04 | PENDING
DIVAN | SO-2605-296-02 | Houzs Century | DIVAN-(Q) | Bedframe | PC151-03 | 1 | 2026-06-06 | 2026-06-04 | PENDING
DIVAN | SO-2605-296-03 | Houzs Century | DIVAN-(S) | Bedframe | PC151-03 | 1 | 2026-06-06 | 2026-06-04 | PENDING
DIVAN | SO-2605-300-01 | Houzs Century | DIVAN-(K) | Bedframe | PC151-01 | 1 | 2026-06-06 | 2026-06-04 | PENDING
DIVAN | SO-2605-259-01 | Carress | DIVAN-(K) | Bedframe | PC151-13 | 1 | 2026-06-10 | 2026-06-08 | PENDING
DIVAN | SO-2605-200-02 | Houzs Century | DIVAN-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
DIVAN | SO-2605-200-03 | Houzs Century | DIVAN-(Q) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
DIVAN | SO-2605-206-01 | Houzs Century | DIVAN-(K) | Bedframe | PC151-01 | 1 | 2026-06-12 | 2026-06-10 | PENDING
DIVAN | SO-2605-265-01 | Houzs Century | DIVAN-(Q) | Bedframe | PC151-14 | 1 | 2026-06-12 | 2026-06-10 | PENDING
DIVAN | SO-2605-265-02 | Houzs Century | DIVAN-(S) | Bedframe | PC151-14 | 1 | 2026-06-12 | 2026-06-10 | PENDING
LONG PILLOW | SO-2604-083-04 | Carress | LONG PILLOW | Accessory | KN390-2 | 1 | 2026-04-15 | 2026-04-14 | PENDING
LONG PILLOW | SO-2604-083-05 | Carress | LONG PILLOW | Accessory | KN390-2 | 1 | 2026-04-15 | 2026-04-14 | PENDING
LONG PILLOW | SO-2605-063-03 | Houzs Century | LONG PILLOW | Accessory | BO315-31 | 1 | 2026-05-25 | 2026-05-24 | PENDING
LONG PILLOW | SO-2605-063-04 | Houzs Century | LONG PILLOW | Accessory | BO315-31 | 1 | 2026-05-25 | 2026-05-24 | PENDING
SQUARE PILLOW | SO-2604-092-03 | Houzs Century | SQUARE PILLOW | Accessory | CH141-5 | 1 | 2026-04-29 | 2026-04-28 | PENDING
SQUARE PILLOW | SO-2604-210-03 | Houzs Century | SQUARE PILLOW | Accessory | AM275-2 | 1 | 2026-05-04 | 2026-05-02 | PENDING
SQUARE PILLOW | SO-2604-088-03 | Houzs Century | SQUARE PILLOW | Accessory | BO315-31 | 1 | 2026-05-04 | 2026-05-03 | ON_HOLD
SQUARE PILLOW | SO-2604-324-03 | Houzs Century | SQUARE PILLOW | Accessory | BO315-22 | 1 | 2026-05-25 | 2026-05-23 | PENDING
SQUARE PILLOW | SO-2604-324-04 | Houzs Century | SQUARE PILLOW | Accessory | BO315-22 | 1 | 2026-05-25 | 2026-05-23 | PENDING
SQUARE PILLOW | SO-2605-104-04 | Houzs Century | SQUARE PILLOW | Accessory | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
SQUARE PILLOW | SO-2605-104-05 | Houzs Century | SQUARE PILLOW | Accessory | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
SQUARE PILLOW | SO-2605-104-06 | Houzs Century | SQUARE PILLOW | Accessory | CH141-3 | 1 | 2026-05-28 | 2026-05-27 | PENDING
SQUARE PILLOW | SO-2605-222-03 | Houzs Century | SQUARE PILLOW | Accessory | CH141-7 | 1 | 2026-05-30 | 2026-05-29 | PENDING
SQUARE PILLOW | SO-2605-222-04 | Houzs Century | SQUARE PILLOW | Accessory | CH141-5 | 1 | 2026-05-30 | 2026-05-29 | PENDING

## Qty Bug (system mis-count)
Model | SO / CO No | Customer | Item (one set per row) | System shows (WRONG) | Should be | What the system counted
5530 | SO-2604-088-01 | Houzs Century | 5530-1A(LHF)+1A(RHF)+1A(LHF)+1A(RHF) | 4 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2604-086-01 | Houzs Century | 5530-2A(RHF)+L(LHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2604-265-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | CO-2605-008-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-063-01 | Houzs Century | 5530-2A(LHF)+L(RHF)+1NA | 3 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-050-01 | Houzs Century | 5530-1A(LHF)+1A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-109-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2604-293-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-051-01 | Houzs Century | 5530-1A(LHF)+1NA+1A(RHF) | 3 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-080-01 | Houzs Century | 5530-1A(LHF)+2NA+L(RHF)+STOOL | 4 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-130-01 | Houzs Century | 5530-1A(LHF)+1NA+1A(RHF) | 3 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-240-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-290-01 | Houzs Century | 5530-1A(LHF)+2A(RHF)+STOOL | 3 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-198-01 | Houzs Century | 5530-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-199-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5530 | SO-2605-224-01 | Houzs Century | 5530-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-072-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2604-327-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-067-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-079-01 | Carress | 5531-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-194-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-197-01 | Carress | 5531-1A(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-071-01 | Carress | 5531-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-183-01 | Carress | 5531-1A(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-196-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-076-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-237-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-236-01 | Carress | 5531-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5531 | SO-2605-182-01 | Carress | 5531-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5535 | SO-2605-104-01 | Houzs Century | 5535-1A(LHF)+1NA+L(RHF) | 3 | 1 | Counted the merged compartments / pieces, not the set
5535 | SO-2605-222-01 | Houzs Century | 5535-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5535 | SO-2605-270-01 | The Conts | 5535-2A(LHF)+L(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5535 | SO-2605-273-01 | Houzs Century | 5535-L(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5535 | SO-2605-106-01 | Houzs Century | 5535-1A(LHF)+1NA+1A(RHF)+1A(LHF)+1A(RHF)+1S | 6 | 1 | Counted the merged compartments / pieces, not the set
5535 | SO-2605-303-01 | Carress | 5535-2A(LHF)+1A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5536 | SO-2605-223-01 | Houzs Century | 5536-1A(LHF)+CNR+2A(RHF)+2S | 4 | 1 | Counted the merged compartments / pieces, not the set
5536 | SO-2605-225-01 | Houzs Century | 5536-1A(LHF)+1A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5536 | SO-2605-184-01 | Houzs Century | 5536-2A(LHF)+CNR+1A(RHF) | 3 | 1 | Counted the merged compartments / pieces, not the set
5537 | SO-2603-207-01 | Houzs Century | 5537-1A(LHF)+1A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5540 | SO-2604-324-01 | Houzs Century | 5540-2A(LHF)+1A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5540 | SO-2605-078-01 | Houzs Century | 5540-L(LHF)+CSL+2A(RHF) | 3 | 1 | Counted the merged compartments / pieces, not the set
5540 | SO-2605-064-01 | Houzs Century | 5540-1A(LHF)+2A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5540 | SO-2605-221-01 | Houzs Century | 5540-1A(LHF)+1NA+1A(RHF) | 3 | 1 | Counted the merged compartments / pieces, not the set
5540 | SO-2605-105-01 | Houzs Century | 5540-1A(LHF)+1A(RHF) | 2 | 1 | Counted the merged compartments / pieces, not the set
5540 | SO-2605-077-01 | Houzs Century | 5540-1A(LHF)+1NA+CSL+L(RHF) | 4 | 1 | Counted the merged compartments / pieces, not the set
DIVAN | SO-2605-011-01 | Houzs Century | DIVAN-(K) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-131-04 | Houzs Century | DIVAN-(K) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-296-01 | Houzs Century | DIVAN-(Q) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-296-02 | Houzs Century | DIVAN-(Q) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-300-01 | Houzs Century | DIVAN-(K) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-259-01 | Carress | DIVAN-(K) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-200-02 | Houzs Century | DIVAN-(Q) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-200-03 | Houzs Century | DIVAN-(Q) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-206-01 | Houzs Century | DIVAN-(K) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)
DIVAN | SO-2605-265-01 | Houzs Century | DIVAN-(Q) | 2 | 1 | Counted fabric panels (e.g. Queen/King = 2 panels)