## Summary & Notes
生产排期总览 Production Schedule Forecast
生成日期 Generated: 2026-05-31 第一个开工天 First working day: 2026-06-02
【关键数字 Headline】
总生产单 Production lines (incomplete, waiting): 328
能排进表里的 Scheduled with a ready date: 317
排不进的 No capacity data (Accessory): 11
最后一单做好 Everything cleared by: 2026-07-11
【准时 vs 迟 On-time vs Late】
准时/提早 On time or early: 13
今天已经过期 Already past due today: 89
会迟交（未来到期）Will miss a future due date: 215
迟 1-7 天: 176 迟 8-14 天: 50 迟 15-30 天: 77 迟 30 天以上: 1
【裁布 Cutting (shared crew, concurrent)】
一组人，每天同时开床架 + 沙发（不是先切完床架才切沙发）。
床架 6 款/天，沙发 2 款/天；床架清完后沙发提速到全力。
Bedframe 6 models/day + sofa 2 models/day, both run every day from day 1;
once bedframe backlog clears (~6 working days) sofa jumps to full force.
只剩 ~115 张裁布单要切，约 6 个开工天清完——裁布不是瓶颈。
【这张表怎么算的 How dates are computed】
1. 只算「还没做完、还在等」的单（Status = WAITING）；做好的 (COMPLETED) 全部跳过。
2. 一张单要全部 8 个站做完才算「做好」：裁布→车缝→锯木→钉框→织带→海绵→包皮→包装。
3. 每个站每天有产能上限，多张单抢同一个站要排队（先到期的先做 EDD）。
4. 「切几天」只是第一站；「Planned Ready」是全部 8 站跑完的日期——所以比单看裁布长很多。
5. 真正塞车的是后段（包皮/织带/钉框），不是裁布。
6. 不放安全余量（现场判断值）。星期日 + 公假不开工，星期六照常。
【还要你确认 Still pending your input】
· 全力切沙发一天几款？现在暂用 4 款/天（假设）。你给真实数，沙发日期会再准一点。
· 后面 7 个站的「每天产能」现在用最近开工天量出来的平均；还没一站一站跟你核对。
· Accessory 类没有产能数据，所以排不进（表里标 No capacity data）。

## Schedule
SO No | Customer | Product Code | Category | Qty | Cut Done | Planned Ready | Customer DD | Status | Days Late
SO-2604-088 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | 2026-06-02 | 2026-05-04 | Already overdue | 29
SO-2604-092 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | 2026-06-02 | 2026-04-29 | Already overdue | 34
SO-2604-210 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | 2026-06-02 | 2026-05-04 | Already overdue | 29
SO-2604-300 | Houzs Century | DIVAN-(Q) | BEDFRAME | 1 |  | 2026-06-02 | 2026-05-25 | Already overdue | 8
SO-2605-108 | Houzs Century | 5540-2S | SOFA | 1 |  | 2026-06-02 | 2026-05-25 | Already overdue | 8
SO-2605-162 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-02 | 2026-05-25 | Already overdue | 8
SO-2605-227 | Houzs Century | 1013-(K) | BEDFRAME | 1 |  | 2026-06-02 | 2026-06-02 | On time
SO-2603-207 | Houzs Century | 5537-1A(RHF) | SOFA | 1 |  | 2026-06-03 | 2026-05-04 | Already overdue | 30
SO-2603-207 | Houzs Century | 5537-1A(LHF) | SOFA | 1 |  | 2026-06-03 | 2026-05-04 | Already overdue | 30
SO-2604-086 | Houzs Century | 5530-L(LHF) | SOFA | 1 |  | 2026-06-03 | 2026-05-11 | Already overdue | 23
SO-2604-088 | Houzs Century | 5530-1A(RHF) | SOFA | 1 |  | 2026-06-03 | 2026-05-04 | Already overdue | 30
SO-2604-088 | Houzs Century | 5530-1A(LHF) | SOFA | 1 |  | 2026-06-03 | 2026-05-04 | Already overdue | 30
SO-2604-276 | Houzs Century | 2041(A)-(SS) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-13 | Already overdue | 21
SO-2604-321 | Houzs Century | 1023(HF)(W)-(SS) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-21 | Already overdue | 13
SO-2605-009 | Houzs Century | 1007-(K) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-22 | Already overdue | 12
SO-2605-011 | Houzs Century | DIVAN-(K) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-18 | Already overdue | 16
SO-2605-023 | Houzs Century | 1007-(K) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-18 | Already overdue | 16
SO-2605-051 | Houzs Century | 5530-1A(RHF) | SOFA | 1 |  | 2026-06-03 | 2026-06-02 | Late | 1
SO-2605-051 | Houzs Century | 5530-1A(LHF) | SOFA | 1 |  | 2026-06-03 | 2026-06-02 | Late | 1
SO-2605-098 | Houzs Century | 2008(A)-(Q) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-29 | Already overdue | 5
SO-2605-098 | Houzs Century | 2008(A)-(Q) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-29 | Already overdue | 5
SO-2605-103 | Houzs Century | 5536-CNR | SOFA | 1 |  | 2026-06-03 | 2026-06-10 | On time
SO-2605-131 | Houzs Century | DIVAN-(K) | BEDFRAME | 1 |  | 2026-06-03 | 2026-06-01 | Already overdue | 2
SO-2605-132 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 |  | 2026-06-03 | 2026-06-04 | On time
SO-2605-160 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-25 | Already overdue | 9
SO-2605-161 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-25 | Already overdue | 9
SO-2605-186 | Houzs Century | 1013-(SS) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-26 | Already overdue | 8
SO-2605-187 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 1 |  | 2026-06-03 | 2026-05-30 | Already overdue | 4
SO-2604-086 | Houzs Century | 5530-2A(RHF) | SOFA | 1 |  | 2026-06-04 | 2026-05-11 | Already overdue | 24
SO-2604-265 | Houzs Century | 5530-2A(RHF) | SOFA | 1 |  | 2026-06-04 | 2026-05-16 | Already overdue | 19
SO-2604-265 | Houzs Century | 5530-L(LHF) | SOFA | 1 |  | 2026-06-04 | 2026-05-16 | Already overdue | 19
SO-2605-063 | Houzs Century | 5530-1NA | SOFA | 1 |  | 2026-06-04 | 2026-05-25 | Already overdue | 10
SO-2605-063 | Houzs Century | 5530-L(RHF) | SOFA | 1 |  | 2026-06-04 | 2026-05-25 | Already overdue | 10
SO-2605-063 | Houzs Century | 5530-2A(LHF) | SOFA | 1 |  | 2026-06-04 | 2026-05-25 | Already overdue | 10
SO-2605-102 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 |  | 2026-06-04 | 2026-05-30 | Already overdue | 5
SO-2605-157 | Houzs Century | 1005-(Q) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-01 | Already overdue | 3
SO-2605-167 | The Conts | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-01 | Already overdue | 3
SO-2605-205 | Houzs Century | 1007-(S) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-01 | Already overdue | 3
SO-2605-205 | Houzs Century | 1007-(S) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-01 | Already overdue | 3
SO-2605-209 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-03 | Late | 1
SO-2605-209 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-03 | Late | 1
SO-2605-209 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-03 | Late | 1
SO-2605-213 | Houzs Century | 1013-(K) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-01 | Already overdue | 3
SO-2605-234 | Houzs Century | 1005-(Q) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-02 | Late | 2
SO-2605-234 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-04 | 2026-06-02 | Late | 2
SO-2605-050 | Houzs Century | 5530-1A(RHF) | SOFA | 1 |  | 2026-06-05 | 2026-05-30 | Already overdue | 6
SO-2605-064 | Houzs Century | 5540-2A(RHF) | SOFA | 1 |  | 2026-06-05 | 2026-05-28 | Already overdue | 8
SO-2605-064 | Houzs Century | 5540-1A(LHF) | SOFA | 1 |  | 2026-06-05 | 2026-05-28 | Already overdue | 8
SO-2605-072 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-05 | 2026-05-25 | Already overdue | 11
SO-2605-072 | Carress | 5531-L(LHF) | SOFA | 1 |  | 2026-06-05 | 2026-05-25 | Already overdue | 11
SO-2605-124 | Houzs Century | 1005-(Q) | BEDFRAME | 1 |  | 2026-06-05 | 2026-05-29 | Already overdue | 7
SO-2605-131 | Houzs Century | 1005-(Q) | BEDFRAME | 1 |  | 2026-06-05 | 2026-06-01 | Already overdue | 4
SO-2605-188 | Houzs Century | 1013-(SS) | BEDFRAME | 1 |  | 2026-06-05 | 2026-06-01 | Already overdue | 4
SO-2605-208 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-05 | 2026-06-01 | Already overdue | 4
SO-2605-210 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 |  | 2026-06-05 | 2026-06-04 | Late | 1
SO-2605-010 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-05-30 | Already overdue | 7
SO-2605-050 | Houzs Century | 5530-1A(LHF) | SOFA | 1 |  | 2026-06-06 | 2026-05-30 | Already overdue | 7
SO-2605-099 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-03 | Late | 3
SO-2605-131 | Houzs Century | 2009(A)-(K) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-01 | Already overdue | 5
SO-2605-131 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-01 | Already overdue | 5
SO-2605-141 | Carress | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-01 | Already overdue | 5
SO-2605-153 | Houzs Century | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-03 | Late | 3
SO-2605-166 | The Conts | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-01 | Already overdue | 5
SO-2605-166 | The Conts | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-01 | Already overdue | 5
SO-2605-207 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-03 | Late | 3
SO-2605-212 | Houzs Century | 1003(A)-(K) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-01 | Already overdue | 5
SO-2605-233 | Houzs Century | 2038(A)(HF)(W)-(K) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-02 | Late | 4
SO-2605-234 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-02 | Late | 4
SO-2605-259 | Carress | DIVAN-(K) | BEDFRAME | 1 |  | 2026-06-06 | 2026-06-10 | On time
SO-2604-307 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2604-327 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2604-327 | Carress | 5531-L(LHF) | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-052 | Houzs Century | 5530-1A(LHF) | SOFA | 1 | 2026-06-06 | 2026-06-08 | 2026-06-03 | Late | 5
SO-2605-067 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-067 | Carress | 5531-L(LHF) | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-099 | Houzs Century | 2008(A)-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-03 | Late | 5
SO-2605-105 | Houzs Century | 5540-1A(RHF) | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-109 | Houzs Century | 5530-L(RHF) | SOFA | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-154 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-03 | Late | 5
SO-2605-193 | Carress | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-03 | Late | 5
SO-2605-204 | Houzs Century | 2038(A)-(SS) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-209 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-03 | Late | 5
SO-2605-251 | Houzs Century | 2038(A)(HF)(W)-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-01 | Already overdue | 7
SO-2605-283 | Houzs Century | DIVAN-(SS) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-05 | Late | 3
SO-2605-286 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-06 | Late | 2
SO-2605-296 | Houzs Century | DIVAN-(S) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-06 | Late | 2
SO-2605-296 | Houzs Century | DIVAN-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-06 | Late | 2
SO-2605-296 | Houzs Century | DIVAN-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-06 | Late | 2
SO-2605-299 | Houzs Century | 1030-(Q) | BEDFRAME | 1 |  | 2026-06-08 | 2026-06-06 | Late | 2
SO-2604-324 | Houzs Century | 5540-1A(RHF) | SOFA | 1 |  | 2026-06-09 | 2026-05-25 | Already overdue | 15
SO-2605-078 | Houzs Century | 5540-2A(RHF) | SOFA | 1 |  | 2026-06-09 | 2026-05-25 | Already overdue | 15
SO-2605-109 | Houzs Century | 5530-2A(LHF) | SOFA | 1 |  | 2026-06-09 | 2026-06-01 | Already overdue | 8
SO-2605-131 | Houzs Century | 1041-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-01 | Already overdue | 8
SO-2605-131 | Houzs Century | 2003-(K) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-01 | Already overdue | 8
SO-2605-131 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-01 | Already overdue | 8
SO-2605-140 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-05 | Late | 4
SO-2605-153 | Houzs Century | 2038(A)-(K) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-03 | Late | 6
SO-2605-195 | Carress | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-03 | Late | 6
SO-2605-239 | Carress | 2009(A)-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-04 | Late | 5
SO-2605-247 | Houzs Century | 2009(A)-(K) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-03 | Late | 6
SO-2605-254 | Houzs Century | 1013-(S) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-04 | Late | 5
SO-2605-254 | Houzs Century | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-04 | Late | 5
SO-2605-299 | Houzs Century | 1030-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-06 | Late | 3
SO-2605-299 | Houzs Century | 1030-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-06 | Late | 3
SO-2605-300 | Houzs Century | 1030-(Q) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-06 | Late | 3
SO-2605-300 | Houzs Century | DIVAN-(K) | BEDFRAME | 1 |  | 2026-06-09 | 2026-06-06 | Late | 3
SO-2604-324 | Houzs Century | 5540-2A(LHF) | SOFA | 1 | 2026-06-02 | 2026-06-10 | 2026-05-25 | Already overdue | 16
SO-2605-078 | Houzs Century | 5540-CSL | SOFA | 1 |  | 2026-06-10 | 2026-05-25 | Already overdue | 16
SO-2605-078 | Houzs Century | 5540-L(LHF) | SOFA | 1 |  | 2026-06-10 | 2026-05-25 | Already overdue | 16
SO-2605-096 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-10 | 2026-06-04 | Late | 6
SO-2605-096 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-10 | 2026-06-04 | Late | 6
SO-2605-171 | Houzs Century | 2011(A)-(K) | BEDFRAME | 1 | 2026-06-02 | 2026-06-10 | 2026-05-25 | Already overdue | 16
SO-2605-185 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-10 | 2026-06-05 | Late | 5
SO-2605-185 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-10 | 2026-06-05 | Late | 5
SO-2605-185 | Houzs Century | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-10 | 2026-06-05 | Late | 5
SO-2605-185 | Houzs Century | 1007-(S) | BEDFRAME | 1 |  | 2026-06-10 | 2026-06-05 | Late | 5
SO-2605-204 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-10 | 2026-06-01 | Already overdue | 9
SO-2605-214 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-10 | 2026-06-03 | Late | 7
SO-2605-248 | Houzs Century | 1007-(K) | BEDFRAME | 1 |  | 2026-06-10 | 2026-06-04 | Late | 6
SO-2605-249 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-10 | 2026-06-04 | Late | 6
SO-2605-279 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-10 | 2026-06-03 | Late | 7
SO-2604-345 | Carress | 5531-2S | SOFA | 1 |  | 2026-06-11 | 2026-05-27 | Already overdue | 15
SO-2605-096 | Houzs Century | 1013-(SK) | BEDFRAME | 1 | 2026-06-03 | 2026-06-11 | 2026-06-04 | Late | 7
SO-2605-104 | Houzs Century | 5535-L(RHF) | SOFA | 1 |  | 2026-06-11 | 2026-05-28 | Already overdue | 14
SO-2605-192 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-192 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-192 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-192 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-220 | Houzs Century | 5536-2S | SOFA | 1 |  | 2026-06-11 | 2026-05-27 | Already overdue | 15
SO-2605-238 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-238 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-238 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-257 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-257 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-11 | 2026-06-05 | Late | 6
SO-2605-278 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-11 | 2026-06-04 | Late | 7
SO-2605-070 | Carress | 1013-(SS) | BEDFRAME | 1 | 2026-06-04 | 2026-06-12 | 2026-06-08 | Late | 4
SO-2605-070 | Carress | 1013-(K) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-08 | Late | 4
SO-2605-104 | Houzs Century | 5535-1NA | SOFA | 1 |  | 2026-06-12 | 2026-05-28 | Already overdue | 15
SO-2605-104 | Houzs Century | 5535-1A(LHF) | SOFA | 1 | 2026-06-04 | 2026-06-12 | 2026-05-28 | Already overdue | 15
SO-2605-215 | Houzs Century | 1013-(S) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-06 | Late | 6
SO-2605-215 | Houzs Century | 1013-(S) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-06 | Late | 6
SO-2605-215 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-06 | Late | 6
SO-2605-221 | Houzs Century | 5540-1A(RHF) | SOFA | 1 |  | 2026-06-12 | 2026-05-28 | Already overdue | 15
SO-2605-221 | Houzs Century | 5540-1NA | SOFA | 1 |  | 2026-06-12 | 2026-05-28 | Already overdue | 15
SO-2605-226 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-08 | Late | 4
SO-2605-255 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-05 | Late | 7
SO-2605-256 | Houzs Century | 1007-(K) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-05 | Late | 7
SO-2605-258 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-12 | 2026-06-06 | Late | 6
SO-2605-262 | Houzs Century | 1013-(SS) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-05 | Late | 7
SO-2605-262 | Houzs Century | 1013-(Q) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-05 | Late | 7
SO-2605-263 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-05 | Late | 7
SO-2605-298 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 |  | 2026-06-12 | 2026-06-06 | Late | 6
SO-2605-200 | Houzs Century | DIVAN-(Q) | BEDFRAME | 1 | 2026-06-06 | 2026-06-13 | 2026-06-12 | Late | 1
SO-2605-200 | Houzs Century | DIVAN-(Q) | BEDFRAME | 1 | 2026-06-06 | 2026-06-13 | 2026-06-12 | Late | 1
SO-2605-203 | Houzs Century | 1007-(K) | BEDFRAME | 1 |  | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-206 | Houzs Century | DIVAN-(K) | BEDFRAME | 1 | 2026-06-06 | 2026-06-13 | 2026-06-12 | Late | 1
SO-2605-215 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-13 | 2026-06-06 | Late | 7
SO-2605-221 | Houzs Century | 5540-1A(LHF) | SOFA | 1 | 2026-06-03 | 2026-06-13 | 2026-05-28 | Already overdue | 16
SO-2605-222 | Houzs Century | 5535-L(RHF) | SOFA | 1 |  | 2026-06-13 | 2026-05-30 | Already overdue | 14
SO-2605-222 | Houzs Century | 5535-2A(LHF) | SOFA | 1 |  | 2026-06-13 | 2026-05-30 | Already overdue | 14
SO-2605-226 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 1 |  | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-261 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 |  | 2026-06-13 | 2026-06-11 | Late | 2
SO-2605-265 | Houzs Century | DIVAN-(S) | BEDFRAME | 1 | 2026-06-06 | 2026-06-13 | 2026-06-12 | Late | 1
SO-2605-265 | Houzs Century | DIVAN-(Q) | BEDFRAME | 1 | 2026-06-06 | 2026-06-13 | 2026-06-12 | Late | 1
SO-2605-276 | Houzs Century | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-277 | Houzs Century | 1013-(SS) | BEDFRAME | 1 | 2026-06-04 | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-285 | Houzs Century | 1013-(SS) | BEDFRAME | 1 | 2026-06-04 | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-291 | Houzs Century | 1005-(Q) | BEDFRAME | 1 | 2026-06-03 | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-295 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-13 | 2026-06-08 | Late | 5
SO-2605-297 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 | 2026-06-05 | 2026-06-13 | 2026-06-11 | Late | 2
SO-2605-079 | Carress | 5531-L(RHF) | SOFA | 1 |  | 2026-06-15 | 2026-06-01 | Already overdue | 14
SO-2605-079 | Carress | 5531-2A(LHF) | SOFA | 1 | 2026-06-05 | 2026-06-15 | 2026-06-01 | Already overdue | 14
SO-2605-105 | Houzs Century | 5540-1A(LHF) | SOFA | 1 | 2026-06-03 | 2026-06-15 | 2026-06-01 | Already overdue | 14
SO-2605-123 | Houzs Century | 2038(A)-(SS) | BEDFRAME | 1 | 2026-06-05 | 2026-06-15 | 2026-06-10 | Late | 5
SO-2605-173 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-15 | 2026-06-01 | Already overdue | 14
SO-2605-229 | Houzs Century | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-15 | 2026-06-10 | Late | 5
SO-2605-241 | Houzs Century | 2009(A)-(Q) | BEDFRAME | 1 | 2026-06-04 | 2026-06-15 | 2026-06-09 | Late | 6
SO-2605-241 | Houzs Century | 2009(A)-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-15 | 2026-06-09 | Late | 6
SO-2605-264 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-15 | 2026-06-08 | Late | 7
SO-2605-269 | The Conts | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-15 | 2026-06-10 | Late | 5
SO-2605-269 | The Conts | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-15 | 2026-06-10 | Late | 5
SO-2605-280 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 1 | 2026-06-04 | 2026-06-15 | 2026-06-08 | Late | 7
SO-2605-280 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 1 | 2026-06-04 | 2026-06-15 | 2026-06-08 | Late | 7
SO-2605-285 | Houzs Century | 1013-(SS) | BEDFRAME | 1 | 2026-06-04 | 2026-06-15 | 2026-06-08 | Late | 7
SO-2605-288 | Houzs Century | 1052-(Q) | BEDFRAME | 1 | 2026-06-05 | 2026-06-15 | 2026-06-10 | Late | 5
SO-2605-291 | Houzs Century | 1003(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-15 | 2026-06-08 | Late | 7
SO-2605-111 | Carress | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-16 | 2026-06-11 | Late | 5
SO-2605-111 | Carress | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-16 | 2026-06-11 | Late | 5
SO-2605-123 | Houzs Century | 1003(A)-(SK) | BEDFRAME | 1 |  | 2026-06-16 | 2026-06-10 | Late | 6
SO-2605-174 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-16 | 2026-06-01 | Already overdue | 15
SO-2605-175 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-16 | 2026-06-01 | Already overdue | 15
SO-2605-200 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-16 | 2026-06-12 | Late | 4
SO-2605-229 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-16 | 2026-06-10 | Late | 6
SO-2605-244 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-16 | 2026-06-10 | Late | 6
SO-2605-245 | Houzs Century | 1013-(S) | BEDFRAME | 1 | 2026-06-05 | 2026-06-16 | 2026-06-10 | Late | 6
SO-2605-246 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-16 | 2026-06-12 | Late | 4
SO-2605-259 | Carress | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-16 | 2026-06-10 | Late | 6
SO-2605-261 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-16 | 2026-06-11 | Late | 5
SO-2605-275 | Houzs Century | 1007-(Q) | BEDFRAME | 1 | 2026-06-05 | 2026-06-16 | 2026-06-12 | Late | 4
SO-2605-275 | Houzs Century | 1007-(K) | BEDFRAME | 1 | 2026-06-05 | 2026-06-16 | 2026-06-12 | Late | 4
SO-2605-288 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-16 | 2026-06-10 | Late | 6
SO-2605-297 | Houzs Century | 1007-(Q) | BEDFRAME | 1 | 2026-06-05 | 2026-06-16 | 2026-06-11 | Late | 5
SO-2604-281 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-077 | Houzs Century | 5540-L(RHF) | SOFA | 1 |  | 2026-06-17 | 2026-06-02 | Late | 15
SO-2605-077 | Houzs Century | 5540-CSL | SOFA | 1 |  | 2026-06-17 | 2026-06-02 | Late | 15
SO-2605-077 | Houzs Century | 5540-1NA | SOFA | 1 |  | 2026-06-17 | 2026-06-02 | Late | 15
SO-2605-176 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-17 | 2026-06-01 | Already overdue | 16
SO-2605-235 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-243 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-243 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-243 | Houzs Century | 1007-(Q) | BEDFRAME | 1 |  | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-243 | Houzs Century | 2009(A)-(K) | BEDFRAME | 1 |  | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-261 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-17 | 2026-06-11 | Late | 6
SO-2605-282 | Houzs Century | 1007-(Q) | BEDFRAME | 1 | 2026-06-05 | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-282 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-17 | 2026-06-12 | Late | 5
SO-2605-294 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 | 2026-06-05 | 2026-06-17 | 2026-06-12 | Late | 5
SO-2604-293 | Houzs Century | 5530-2A(RHF) | SOFA | 1 |  | 2026-06-18 | 2026-06-03 | Late | 15
SO-2604-293 | Houzs Century | 5530-L(LHF) | SOFA | 1 | 2026-06-08 | 2026-06-18 | 2026-06-03 | Late | 15
SO-2605-077 | Houzs Century | 5540-1A(LHF) | SOFA | 1 | 2026-06-03 | 2026-06-18 | 2026-06-02 | Late | 16
SO-2605-080 | Houzs Century | 5530-STOOL | SOFA | 1 |  | 2026-06-18 | 2026-06-03 | Late | 15
SO-2605-202 | Houzs Century | 2033(HF)(W)-(SS) | BEDFRAME | 1 | 2026-06-06 | 2026-06-18 | 2026-06-13 | Late | 5
SO-2605-202 | Houzs Century | 2033(HF)(W)-(K) | BEDFRAME | 1 | 2026-06-06 | 2026-06-18 | 2026-06-13 | Late | 5
SO-2605-216 | Carress | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-216 | Carress | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-216 | Carress | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-216 | Carress | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-242 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-18 | 2026-06-13 | Late | 5
SO-2605-242 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-18 | 2026-06-13 | Late | 5
SO-2605-252 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-271 | Carress | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-271 | Carress | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-281 | Houzs Century | 1005-(Q) | BEDFRAME | 1 | 2026-06-03 | 2026-06-18 | 2026-06-15 | Late | 3
SO-2605-069 | Carress | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-19 | 2026-06-18 | Late | 1
SO-2605-080 | Houzs Century | 5530-L(RHF) | SOFA | 1 |  | 2026-06-19 | 2026-06-03 | Late | 16
SO-2605-080 | Houzs Century | 5530-2NA | SOFA | 1 |  | 2026-06-19 | 2026-06-03 | Late | 16
SO-2605-080 | Houzs Century | 5530-1A(LHF) | SOFA | 1 |  | 2026-06-19 | 2026-06-03 | Late | 16
SO-2605-190 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 | 2026-06-05 | 2026-06-19 | 2026-06-19 | On time
SO-2605-211 | Houzs Century | 2009(A)-(SK) | BEDFRAME | 1 | 2026-06-08 | 2026-06-19 | 2026-06-16 | Late | 3
SO-2605-228 | Houzs Century | 1030-(K) | BEDFRAME | 1 | 2026-06-08 | 2026-06-19 | 2026-06-17 | Late | 2
SO-2605-260 | Houzs Century | 2038(A)-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-19 | 2026-06-17 | Late | 2
SO-2605-274 | Houzs Century | 1023-(K) | BEDFRAME | 1 | 2026-06-08 | 2026-06-19 | 2026-06-16 | Late | 3
SO-2605-292 | Houzs Century | 1007-(SS) | BEDFRAME | 1 | 2026-06-08 | 2026-06-19 | 2026-06-15 | Late | 4
SO-2605-292 | Houzs Century | 1007-(SS) | BEDFRAME | 1 | 2026-06-08 | 2026-06-19 | 2026-06-15 | Late | 4
SO-2605-292 | Houzs Century | 2008(A)-(K) | BEDFRAME | 1 | 2026-06-03 | 2026-06-19 | 2026-06-15 | Late | 4
SO-2605-293 | Houzs Century | 1013-(K) | BEDFRAME | 1 | 2026-06-04 | 2026-06-19 | 2026-06-15 | Late | 4
SO-2605-293 | Houzs Century | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-19 | 2026-06-15 | Late | 4
SO-2605-071 | Carress | 5531-L(RHF) | SOFA | 1 |  | 2026-06-20 | 2026-06-08 | Late | 12
SO-2605-071 | Carress | 5531-2A(LHF) | SOFA | 1 |  | 2026-06-20 | 2026-06-08 | Late | 12
SO-2605-189 | Houzs Century | 1003(A)-(K) | BEDFRAME | 1 |  | 2026-06-20 | 2026-06-24 | On time
SO-2605-191 | Houzs Century | 2006(A)-(Q) | BEDFRAME | 1 | 2026-06-08 | 2026-06-20 | 2026-06-19 | Late | 1
SO-2605-194 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-20 | 2026-06-03 | Late | 17
SO-2605-194 | Carress | 5531-L(LHF) | SOFA | 1 | 2026-06-09 | 2026-06-20 | 2026-06-03 | Late | 17
SO-2605-197 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-20 | 2026-06-03 | Late | 17
SO-2605-197 | Carress | 5531-1A(LHF) | SOFA | 1 |  | 2026-06-20 | 2026-06-03 | Late | 17
SO-2605-231 | Houzs Century | 2041(A)-(Q) | BEDFRAME | 1 | 2026-06-04 | 2026-06-20 | 2026-06-25 | On time
SO-2605-231 | Houzs Century | 1003(A)-(Q) | BEDFRAME | 1 | 2026-06-08 | 2026-06-20 | 2026-06-25 | On time
SO-2605-284 | Houzs Century | 1007-(Q) | BEDFRAME | 1 | 2026-06-05 | 2026-06-20 | 2026-06-19 | Late | 1
SO-2605-289 | Carress | 1013-(Q) | BEDFRAME | 1 | 2026-06-02 | 2026-06-20 | 2026-06-22 | On time
SO-2605-302 | Carress | 1007-(K) | BEDFRAME | 1 | 2026-06-05 | 2026-06-20 | 2026-06-29 | On time
SV-2605-002 | Houzs Century | 2006(A)-(K) | BEDFRAME | 1 |  | 2026-06-20 | 2026-07-08 | On time
SO-2605-130 | Houzs Century | 5530-1A(RHF) | SOFA | 1 |  | 2026-06-22 | 2026-06-08 | Late | 14
SO-2605-130 | Houzs Century | 5530-1NA | SOFA | 1 |  | 2026-06-22 | 2026-06-08 | Late | 14
SO-2605-130 | Houzs Century | 5530-1A(LHF) | SOFA | 1 |  | 2026-06-22 | 2026-06-08 | Late | 14
SO-2605-177 | The Conts | 6112-2S | SOFA | 1 | 2026-06-09 | 2026-06-23 | 2026-06-08 | Late | 15
SO-2605-178 | The Conts | 6112-2S | SOFA | 1 | 2026-06-09 | 2026-06-23 | 2026-06-08 | Late | 15
SO-2605-179 | The Conts | 6112-2S | SOFA | 1 | 2026-06-09 | 2026-06-24 | 2026-06-08 | Late | 16
SO-2605-180 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-24 | 2026-06-08 | Late | 16
SO-2605-103 | Houzs Century | 5536-1A(RHF) | SOFA | 1 |  | 2026-06-25 | 2026-06-10 | Late | 15
SO-2605-181 | The Conts | 6112-2S | SOFA | 1 |  | 2026-06-25 | 2026-06-08 | Late | 17
SO-2605-183 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-25 | 2026-06-08 | Late | 17
SO-2605-183 | Carress | 5531-1A(LHF) | SOFA | 1 |  | 2026-06-26 | 2026-06-08 | Late | 18
SO-2605-196 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-26 | 2026-06-08 | Late | 18
SO-2605-196 | Carress | 5531-L(LHF) | SOFA | 1 | 2026-06-09 | 2026-06-26 | 2026-06-08 | Late | 18
SO-2605-240 | Houzs Century | 5530-2A(RHF) | SOFA | 1 |  | 2026-06-27 | 2026-06-08 | Late | 19
SO-2605-240 | Houzs Century | 5530-L(LHF) | SOFA | 1 | 2026-06-08 | 2026-06-27 | 2026-06-08 | Late | 19
SV-2605-003 | Houzs Century | 5530-L(RHF) | SOFA | 1 | 2026-06-10 | 2026-06-27 | 2026-06-09 | Late | 18
SO-2605-076 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-29 | 2026-06-12 | Late | 17
SO-2605-076 | Carress | 5531-L(LHF) | SOFA | 1 | 2026-06-09 | 2026-06-29 | 2026-06-12 | Late | 17
SO-2605-270 | The Conts | 5535-L(RHF) | SOFA | 1 |  | 2026-06-29 | 2026-06-10 | Late | 19
SO-2605-270 | The Conts | 5535-2A(LHF) | SOFA | 1 | 2026-06-10 | 2026-06-29 | 2026-06-10 | Late | 19
SO-2605-237 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-06-30 | 2026-06-13 | Late | 17
SO-2605-237 | Carress | 5531-L(LHF) | SOFA | 1 |  | 2026-06-30 | 2026-06-13 | Late | 17
SO-2605-223 | Houzs Century | 5536-2S | SOFA | 1 |  | 2026-07-01 | 2026-06-15 | Late | 16
SO-2605-223 | Houzs Century | 5536-2A(RHF) | SOFA | 1 |  | 2026-07-01 | 2026-06-15 | Late | 16
SO-2605-223 | Houzs Century | 5536-CNR | SOFA | 1 |  | 2026-07-01 | 2026-06-15 | Late | 16
SO-2605-223 | Houzs Century | 5536-1A(LHF) | SOFA | 1 | 2026-06-11 | 2026-07-02 | 2026-06-15 | Late | 17
SO-2605-225 | Houzs Century | 5536-1A(RHF) | SOFA | 1 |  | 2026-07-02 | 2026-06-16 | Late | 16
SO-2605-225 | Houzs Century | 5536-1A(LHF) | SOFA | 1 | 2026-06-11 | 2026-07-02 | 2026-06-16 | Late | 16
SO-2605-273 | Houzs Century | 5535-2A(RHF) | SOFA | 1 |  | 2026-07-02 | 2026-06-16 | Late | 16
SO-2605-236 | Carress | 5531-L(RHF) | SOFA | 1 |  | 2026-07-03 | 2026-06-17 | Late | 16
SO-2605-236 | Carress | 5531-2A(LHF) | SOFA | 1 | 2026-06-05 | 2026-07-03 | 2026-06-17 | Late | 16
SO-2605-273 | Houzs Century | 5535-L(LHF) | SOFA | 1 | 2026-06-11 | 2026-07-03 | 2026-06-16 | Late | 17
SO-2605-290 | Houzs Century | 5530-STOOL | SOFA | 1 |  | 2026-07-03 | 2026-06-19 | Late | 14
SO-2605-106 | Houzs Century | 5535-1S | SOFA | 1 |  | 2026-07-04 | 2026-06-22 | Late | 12
SO-2605-106 | Houzs Century | 5535-1A(RHF) | SOFA | 1 |  | 2026-07-04 | 2026-06-22 | Late | 12
SO-2605-290 | Houzs Century | 5530-2A(RHF) | SOFA | 1 |  | 2026-07-04 | 2026-06-19 | Late | 15
SO-2605-290 | Houzs Century | 5530-1A(LHF) | SOFA | 1 | 2026-06-06 | 2026-07-04 | 2026-06-19 | Late | 15
SO-2605-106 | Houzs Century | 5535-1A(LHF) | SOFA | 1 |  | 2026-07-06 | 2026-06-22 | Late | 14
SO-2605-106 | Houzs Century | 5535-1A(RHF) | SOFA | 1 |  | 2026-07-06 | 2026-06-22 | Late | 14
SO-2605-106 | Houzs Century | 5535-1NA | SOFA | 1 |  | 2026-07-06 | 2026-06-22 | Late | 14
SO-2605-106 | Houzs Century | 5535-1A(LHF) | SOFA | 1 |  | 2026-07-06 | 2026-06-22 | Late | 14
SO-2605-303 | Carress | 5535-1A(RHF) | SOFA | 1 |  | 2026-07-06 | 2026-06-22 | Late | 14
SO-2605-184 | Houzs Century | 5536-1A(RHF) | SOFA | 1 |  | 2026-07-07 | 2026-06-24 | Late | 13
SO-2605-184 | Houzs Century | 5536-CNR | SOFA | 1 |  | 2026-07-07 | 2026-06-24 | Late | 13
SO-2605-303 | Carress | 5535-2A(LHF) | SOFA | 1 | 2026-06-10 | 2026-07-07 | 2026-06-22 | Late | 15
SO-2605-184 | Houzs Century | 5536-2A(LHF) | SOFA | 1 | 2026-06-11 | 2026-07-08 | 2026-06-24 | Late | 14
SO-2605-198 | Houzs Century | 5530-2A(RHF) | SOFA | 1 |  | 2026-07-08 | 2026-06-24 | Late | 14
SO-2605-198 | Houzs Century | 5530-L(LHF) | SOFA | 1 |  | 2026-07-08 | 2026-06-24 | Late | 14
SO-2605-199 | Houzs Century | 5530-L(RHF) | SOFA | 1 |  | 2026-07-08 | 2026-06-24 | Late | 14
SO-2605-182 | Carress | 5531-2A(RHF) | SOFA | 1 |  | 2026-07-09 | 2026-06-25 | Late | 14
SO-2605-199 | Houzs Century | 5530-2A(LHF) | SOFA | 1 |  | 2026-07-09 | 2026-06-24 | Late | 15
SO-2605-182 | Carress | 5531-L(LHF) | SOFA | 1 | 2026-06-09 | 2026-07-10 | 2026-06-25 | Late | 15
SO-2605-224 | Houzs Century | 5530-L(RHF) | SOFA | 1 |  | 2026-07-10 | 2026-06-26 | Late | 14
SO-2605-224 | Houzs Century | 5530-2A(LHF) | SOFA | 1 |  | 2026-07-10 | 2026-06-26 | Late | 14
CO-2605-008-01 | Houzs Century | 5530-2A(LHF) | SOFA | 1 |  | 2026-07-11 | 9999-12-31 | On time
CO-2605-008-02 | Houzs Century | 5530-L(RHF) | SOFA | 1 |  | 2026-07-11 | 9999-12-31 | On time
SO-2605-301 | Carress | 5531-2S | SOFA | 1 | 2026-06-11 | 2026-07-11 | 2026-06-29 | Late | 12
SO-2604-083 | Carress | LONG PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-04-15 | No capacity data
SO-2604-083 | Carress | LONG PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-04-15 | No capacity data
SO-2604-324 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-25 | No capacity data
SO-2604-324 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-25 | No capacity data
SO-2605-063 | Houzs Century | LONG PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-25 | No capacity data
SO-2605-063 | Houzs Century | LONG PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-25 | No capacity data
SO-2605-104 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-28 | No capacity data
SO-2605-104 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-28 | No capacity data
SO-2605-104 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-28 | No capacity data
SO-2605-222 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-30 | No capacity data
SO-2605-222 | Houzs Century | SQUARE PILLOW | ACCESSORY | 1 |  | (not scheduled) | 2026-05-30 | No capacity data

## By Order
SO No | Customer | # Lines | Total Qty | Customer DD | Order Ready (all lines) | Status | Max Days Late
SO-2604-083 | Carress | 2 | 2 | 2026-04-15 | (not scheduled) | Partial (some items stalled)
SO-2604-092 | Houzs Century | 1 | 1 | 2026-04-29 | 2026-06-02 | Already overdue | 34
SO-2604-210 | Houzs Century | 1 | 1 | 2026-05-04 | 2026-06-02 | Already overdue | 29
SO-2604-300 | Houzs Century | 1 | 1 | 2026-05-25 | 2026-06-02 | Already overdue | 8
SO-2605-108 | Houzs Century | 1 | 1 | 2026-05-25 | 2026-06-02 | Already overdue | 8
SO-2605-162 | Houzs Century | 1 | 1 | 2026-05-25 | 2026-06-02 | Already overdue | 8
SO-2605-227 | Houzs Century | 1 | 1 | 2026-06-02 | 2026-06-02 | On time
SO-2603-207 | Houzs Century | 2 | 2 | 2026-05-04 | 2026-06-03 | Already overdue | 30
SO-2604-088 | Houzs Century | 3 | 3 | 2026-05-04 | 2026-06-03 | Already overdue | 30
SO-2604-276 | Houzs Century | 1 | 1 | 2026-05-13 | 2026-06-03 | Already overdue | 21
SO-2604-321 | Houzs Century | 1 | 1 | 2026-05-21 | 2026-06-03 | Already overdue | 13
SO-2605-009 | Houzs Century | 1 | 1 | 2026-05-22 | 2026-06-03 | Already overdue | 12
SO-2605-011 | Houzs Century | 1 | 1 | 2026-05-18 | 2026-06-03 | Already overdue | 16
SO-2605-023 | Houzs Century | 1 | 1 | 2026-05-18 | 2026-06-03 | Already overdue | 16
SO-2605-051 | Houzs Century | 2 | 2 | 2026-06-02 | 2026-06-03 | Late | 1
SO-2605-098 | Houzs Century | 2 | 2 | 2026-05-29 | 2026-06-03 | Already overdue | 5
SO-2605-132 | Houzs Century | 1 | 1 | 2026-06-04 | 2026-06-03 | On time
SO-2605-160 | Houzs Century | 1 | 1 | 2026-05-25 | 2026-06-03 | Already overdue | 9
SO-2605-161 | Houzs Century | 1 | 1 | 2026-05-25 | 2026-06-03 | Already overdue | 9
SO-2605-186 | Houzs Century | 1 | 1 | 2026-05-26 | 2026-06-03 | Already overdue | 8
SO-2605-187 | Houzs Century | 1 | 1 | 2026-05-30 | 2026-06-03 | Already overdue | 4
SO-2604-086 | Houzs Century | 2 | 2 | 2026-05-11 | 2026-06-04 | Already overdue | 24
SO-2604-265 | Houzs Century | 2 | 2 | 2026-05-16 | 2026-06-04 | Already overdue | 19
SO-2605-063 | Houzs Century | 5 | 5 | 2026-05-25 | 2026-06-04 | Partial (some items stalled) | 10
SO-2605-102 | Houzs Century | 1 | 1 | 2026-05-30 | 2026-06-04 | Already overdue | 5
SO-2605-157 | Houzs Century | 1 | 1 | 2026-06-01 | 2026-06-04 | Already overdue | 3
SO-2605-167 | The Conts | 1 | 1 | 2026-06-01 | 2026-06-04 | Already overdue | 3
SO-2605-205 | Houzs Century | 2 | 2 | 2026-06-01 | 2026-06-04 | Already overdue | 3
SO-2605-213 | Houzs Century | 1 | 1 | 2026-06-01 | 2026-06-04 | Already overdue | 3
SO-2605-064 | Houzs Century | 2 | 2 | 2026-05-28 | 2026-06-05 | Already overdue | 8
SO-2605-072 | Carress | 2 | 2 | 2026-05-25 | 2026-06-05 | Already overdue | 11
SO-2605-124 | Houzs Century | 1 | 1 | 2026-05-29 | 2026-06-05 | Already overdue | 7
SO-2605-188 | Houzs Century | 1 | 1 | 2026-06-01 | 2026-06-05 | Already overdue | 4
SO-2605-208 | Houzs Century | 1 | 1 | 2026-06-01 | 2026-06-05 | Already overdue | 4
SO-2605-210 | Houzs Century | 1 | 1 | 2026-06-04 | 2026-06-05 | Late | 1
SO-2605-010 | Houzs Century | 1 | 1 | 2026-05-30 | 2026-06-06 | Already overdue | 7
SO-2605-050 | Houzs Century | 2 | 2 | 2026-05-30 | 2026-06-06 | Already overdue | 7
SO-2605-141 | Carress | 1 | 1 | 2026-06-01 | 2026-06-06 | Already overdue | 5
SO-2605-166 | The Conts | 2 | 2 | 2026-06-01 | 2026-06-06 | Already overdue | 5
SO-2605-207 | Houzs Century | 1 | 1 | 2026-06-03 | 2026-06-06 | Late | 3
SO-2605-212 | Houzs Century | 1 | 1 | 2026-06-01 | 2026-06-06 | Already overdue | 5
SO-2605-233 | Houzs Century | 1 | 1 | 2026-06-02 | 2026-06-06 | Late | 4
SO-2605-234 | Houzs Century | 3 | 3 | 2026-06-02 | 2026-06-06 | Late | 4
SO-2604-307 | The Conts | 1 | 1 | 2026-06-01 | 2026-06-08 | Already overdue | 7
SO-2604-327 | Carress | 2 | 2 | 2026-06-01 | 2026-06-08 | Already overdue | 7
SO-2605-052 | Houzs Century | 1 | 1 | 2026-06-03 | 2026-06-08 | Late | 5
SO-2605-067 | Carress | 2 | 2 | 2026-06-01 | 2026-06-08 | Already overdue | 7
SO-2605-099 | Houzs Century | 2 | 2 | 2026-06-03 | 2026-06-08 | Late | 5
SO-2605-154 | Houzs Century | 1 | 1 | 2026-06-03 | 2026-06-08 | Late | 5
SO-2605-193 | Carress | 1 | 1 | 2026-06-03 | 2026-06-08 | Late | 5
SO-2605-209 | Houzs Century | 4 | 4 | 2026-06-03 | 2026-06-08 | Late | 5
SO-2605-251 | Houzs Century | 1 | 1 | 2026-06-01 | 2026-06-08 | Already overdue | 7
SO-2605-283 | Houzs Century | 1 | 1 | 2026-06-05 | 2026-06-08 | Late | 3
SO-2605-286 | Houzs Century | 1 | 1 | 2026-06-06 | 2026-06-08 | Late | 2
SO-2605-296 | Houzs Century | 3 | 3 | 2026-06-06 | 2026-06-08 | Late | 2
SO-2605-109 | Houzs Century | 2 | 2 | 2026-06-01 | 2026-06-09 | Already overdue | 8
SO-2605-131 | Houzs Century | 7 | 7 | 2026-06-01 | 2026-06-09 | Already overdue | 8
SO-2605-140 | Houzs Century | 1 | 1 | 2026-06-05 | 2026-06-09 | Late | 4
SO-2605-153 | Houzs Century | 2 | 2 | 2026-06-03 | 2026-06-09 | Late | 6
SO-2605-195 | Carress | 1 | 1 | 2026-06-03 | 2026-06-09 | Late | 6
SO-2605-239 | Carress | 1 | 1 | 2026-06-04 | 2026-06-09 | Late | 5
SO-2605-247 | Houzs Century | 1 | 1 | 2026-06-03 | 2026-06-09 | Late | 6
SO-2605-254 | Houzs Century | 2 | 2 | 2026-06-04 | 2026-06-09 | Late | 5
SO-2605-299 | Houzs Century | 3 | 3 | 2026-06-06 | 2026-06-09 | Late | 3
SO-2605-300 | Houzs Century | 2 | 2 | 2026-06-06 | 2026-06-09 | Late | 3
SO-2604-324 | Houzs Century | 4 | 4 | 2026-05-25 | 2026-06-10 | Partial (some items stalled) | 16
SO-2605-078 | Houzs Century | 3 | 3 | 2026-05-25 | 2026-06-10 | Already overdue | 16
SO-2605-171 | Houzs Century | 1 | 1 | 2026-05-25 | 2026-06-10 | Already overdue | 16
SO-2605-185 | Houzs Century | 4 | 4 | 2026-06-05 | 2026-06-10 | Late | 5
SO-2605-204 | Houzs Century | 2 | 2 | 2026-06-01 | 2026-06-10 | Already overdue | 9
SO-2605-214 | Houzs Century | 1 | 1 | 2026-06-03 | 2026-06-10 | Late | 7
SO-2605-248 | Houzs Century | 1 | 1 | 2026-06-04 | 2026-06-10 | Late | 6
SO-2605-249 | Houzs Century | 1 | 1 | 2026-06-04 | 2026-06-10 | Late | 6
SO-2605-279 | Houzs Century | 1 | 1 | 2026-06-03 | 2026-06-10 | Late | 7
SO-2604-345 | Carress | 1 | 1 | 2026-05-27 | 2026-06-11 | Already overdue | 15
SO-2605-096 | Houzs Century | 3 | 3 | 2026-06-04 | 2026-06-11 | Late | 7
SO-2605-192 | Houzs Century | 4 | 4 | 2026-06-05 | 2026-06-11 | Late | 6
SO-2605-220 | Houzs Century | 1 | 1 | 2026-05-27 | 2026-06-11 | Already overdue | 15
SO-2605-238 | Houzs Century | 3 | 3 | 2026-06-05 | 2026-06-11 | Late | 6
SO-2605-257 | Houzs Century | 2 | 2 | 2026-06-05 | 2026-06-11 | Late | 6
SO-2605-278 | Houzs Century | 1 | 1 | 2026-06-04 | 2026-06-11 | Late | 7
SO-2605-070 | Carress | 2 | 2 | 2026-06-08 | 2026-06-12 | Late | 4
SO-2605-104 | Houzs Century | 6 | 6 | 2026-05-28 | 2026-06-12 | Partial (some items stalled) | 15
SO-2605-255 | Houzs Century | 1 | 1 | 2026-06-05 | 2026-06-12 | Late | 7
SO-2605-256 | Houzs Century | 1 | 1 | 2026-06-05 | 2026-06-12 | Late | 7
SO-2605-258 | Houzs Century | 1 | 1 | 2026-06-06 | 2026-06-12 | Late | 6
SO-2605-262 | Houzs Century | 2 | 2 | 2026-06-05 | 2026-06-12 | Late | 7
SO-2605-263 | Houzs Century | 1 | 1 | 2026-06-05 | 2026-06-12 | Late | 7
SO-2605-298 | Houzs Century | 1 | 1 | 2026-06-06 | 2026-06-12 | Late | 6
SO-2605-203 | Houzs Century | 1 | 1 | 2026-06-08 | 2026-06-13 | Late | 5
SO-2605-206 | Houzs Century | 1 | 1 | 2026-06-12 | 2026-06-13 | Late | 1
SO-2605-215 | Houzs Century | 4 | 4 | 2026-06-06 | 2026-06-13 | Late | 7
SO-2605-221 | Houzs Century | 3 | 3 | 2026-05-28 | 2026-06-13 | Already overdue | 16
SO-2605-222 | Houzs Century | 4 | 4 | 2026-05-30 | 2026-06-13 | Partial (some items stalled) | 14
SO-2605-226 | Houzs Century | 2 | 2 | 2026-06-08 | 2026-06-13 | Late | 5
SO-2605-265 | Houzs Century | 2 | 2 | 2026-06-12 | 2026-06-13 | Late | 1
SO-2605-276 | Houzs Century | 1 | 1 | 2026-06-08 | 2026-06-13 | Late | 5
SO-2605-277 | Houzs Century | 1 | 1 | 2026-06-08 | 2026-06-13 | Late | 5
SO-2605-295 | Houzs Century | 1 | 1 | 2026-06-08 | 2026-06-13 | Late | 5
SO-2605-079 | Carress | 2 | 2 | 2026-06-01 | 2026-06-15 | Already overdue | 14
SO-2605-105 | Houzs Century | 2 | 2 | 2026-06-01 | 2026-06-15 | Already overdue | 14
SO-2605-173 | The Conts | 1 | 1 | 2026-06-01 | 2026-06-15 | Already overdue | 14
SO-2605-241 | Houzs Century | 2 | 2 | 2026-06-09 | 2026-06-15 | Late | 6
SO-2605-264 | Houzs Century | 1 | 1 | 2026-06-08 | 2026-06-15 | Late | 7
SO-2605-269 | The Conts | 2 | 2 | 2026-06-10 | 2026-06-15 | Late | 5
SO-2605-280 | Houzs Century | 2 | 2 | 2026-06-08 | 2026-06-15 | Late | 7
SO-2605-285 | Houzs Century | 2 | 2 | 2026-06-08 | 2026-06-15 | Late | 7
SO-2605-291 | Houzs Century | 2 | 2 | 2026-06-08 | 2026-06-15 | Late | 7
SO-2605-111 | Carress | 2 | 2 | 2026-06-11 | 2026-06-16 | Late | 5
SO-2605-123 | Houzs Century | 2 | 2 | 2026-06-10 | 2026-06-16 | Late | 6
SO-2605-174 | The Conts | 1 | 1 | 2026-06-01 | 2026-06-16 | Already overdue | 15
SO-2605-175 | The Conts | 1 | 1 | 2026-06-01 | 2026-06-16 | Already overdue | 15
SO-2605-200 | Houzs Century | 3 | 3 | 2026-06-12 | 2026-06-16 | Late | 4
SO-2605-229 | Houzs Century | 2 | 2 | 2026-06-10 | 2026-06-16 | Late | 6
SO-2605-244 | Houzs Century | 1 | 1 | 2026-06-10 | 2026-06-16 | Late | 6
SO-2605-245 | Houzs Century | 1 | 1 | 2026-06-10 | 2026-06-16 | Late | 6
SO-2605-246 | Houzs Century | 1 | 1 | 2026-06-12 | 2026-06-16 | Late | 4
SO-2605-259 | Carress | 2 | 2 | 2026-06-10 | 2026-06-16 | Late | 6
SO-2605-275 | Houzs Century | 2 | 2 | 2026-06-12 | 2026-06-16 | Late | 4
SO-2605-288 | Houzs Century | 2 | 2 | 2026-06-10 | 2026-06-16 | Late | 6
SO-2605-297 | Houzs Century | 2 | 2 | 2026-06-11 | 2026-06-16 | Late | 5
SO-2604-281 | Houzs Century | 1 | 1 | 2026-06-12 | 2026-06-17 | Late | 5
SO-2605-176 | The Conts | 1 | 1 | 2026-06-01 | 2026-06-17 | Already overdue | 16
SO-2605-235 | Houzs Century | 1 | 1 | 2026-06-12 | 2026-06-17 | Late | 5
SO-2605-243 | Houzs Century | 4 | 4 | 2026-06-12 | 2026-06-17 | Late | 5
SO-2605-261 | Houzs Century | 3 | 3 | 2026-06-11 | 2026-06-17 | Late | 6
SO-2605-282 | Houzs Century | 2 | 2 | 2026-06-12 | 2026-06-17 | Late | 5
SO-2605-294 | Houzs Century | 1 | 1 | 2026-06-12 | 2026-06-17 | Late | 5
SO-2604-293 | Houzs Century | 2 | 2 | 2026-06-03 | 2026-06-18 | Late | 15
SO-2605-077 | Houzs Century | 4 | 4 | 2026-06-02 | 2026-06-18 | Late | 16
SO-2605-202 | Houzs Century | 2 | 2 | 2026-06-13 | 2026-06-18 | Late | 5
SO-2605-216 | Carress | 4 | 4 | 2026-06-15 | 2026-06-18 | Late | 3
SO-2605-242 | Houzs Century | 2 | 2 | 2026-06-13 | 2026-06-18 | Late | 5
SO-2605-252 | Houzs Century | 1 | 1 | 2026-06-15 | 2026-06-18 | Late | 3
SO-2605-271 | Carress | 2 | 2 | 2026-06-15 | 2026-06-18 | Late | 3
SO-2605-281 | Houzs Century | 1 | 1 | 2026-06-15 | 2026-06-18 | Late | 3
SO-2605-069 | Carress | 1 | 1 | 2026-06-18 | 2026-06-19 | Late | 1
SO-2605-080 | Houzs Century | 4 | 4 | 2026-06-03 | 2026-06-19 | Late | 16
SO-2605-190 | Houzs Century | 1 | 1 | 2026-06-19 | 2026-06-19 | On time
SO-2605-211 | Houzs Century | 1 | 1 | 2026-06-16 | 2026-06-19 | Late | 3
SO-2605-228 | Houzs Century | 1 | 1 | 2026-06-17 | 2026-06-19 | Late | 2
SO-2605-260 | Houzs Century | 1 | 1 | 2026-06-17 | 2026-06-19 | Late | 2
SO-2605-274 | Houzs Century | 1 | 1 | 2026-06-16 | 2026-06-19 | Late | 3
SO-2605-292 | Houzs Century | 3 | 3 | 2026-06-15 | 2026-06-19 | Late | 4
SO-2605-293 | Houzs Century | 2 | 2 | 2026-06-15 | 2026-06-19 | Late | 4
SO-2605-071 | Carress | 2 | 2 | 2026-06-08 | 2026-06-20 | Late | 12
SO-2605-189 | Houzs Century | 1 | 1 | 2026-06-24 | 2026-06-20 | On time
SO-2605-191 | Houzs Century | 1 | 1 | 2026-06-19 | 2026-06-20 | Late | 1
SO-2605-194 | Carress | 2 | 2 | 2026-06-03 | 2026-06-20 | Late | 17
SO-2605-197 | Carress | 2 | 2 | 2026-06-03 | 2026-06-20 | Late | 17
SO-2605-231 | Houzs Century | 2 | 2 | 2026-06-25 | 2026-06-20 | On time
SO-2605-284 | Houzs Century | 1 | 1 | 2026-06-19 | 2026-06-20 | Late | 1
SO-2605-289 | Carress | 1 | 1 | 2026-06-22 | 2026-06-20 | On time
SO-2605-302 | Carress | 1 | 1 | 2026-06-29 | 2026-06-20 | On time
SV-2605-002 | Houzs Century | 1 | 1 | 2026-07-08 | 2026-06-20 | On time
SO-2605-130 | Houzs Century | 3 | 3 | 2026-06-08 | 2026-06-22 | Late | 14
SO-2605-177 | The Conts | 1 | 1 | 2026-06-08 | 2026-06-23 | Late | 15
SO-2605-178 | The Conts | 1 | 1 | 2026-06-08 | 2026-06-23 | Late | 15
SO-2605-179 | The Conts | 1 | 1 | 2026-06-08 | 2026-06-24 | Late | 16
SO-2605-180 | The Conts | 1 | 1 | 2026-06-08 | 2026-06-24 | Late | 16
SO-2605-103 | Houzs Century | 2 | 2 | 2026-06-10 | 2026-06-25 | Late | 15
SO-2605-181 | The Conts | 1 | 1 | 2026-06-08 | 2026-06-25 | Late | 17
SO-2605-183 | Carress | 2 | 2 | 2026-06-08 | 2026-06-26 | Late | 18
SO-2605-196 | Carress | 2 | 2 | 2026-06-08 | 2026-06-26 | Late | 18
SO-2605-240 | Houzs Century | 2 | 2 | 2026-06-08 | 2026-06-27 | Late | 19
SV-2605-003 | Houzs Century | 1 | 1 | 2026-06-09 | 2026-06-27 | Late | 18
SO-2605-076 | Carress | 2 | 2 | 2026-06-12 | 2026-06-29 | Late | 17
SO-2605-270 | The Conts | 2 | 2 | 2026-06-10 | 2026-06-29 | Late | 19
SO-2605-237 | Carress | 2 | 2 | 2026-06-13 | 2026-06-30 | Late | 17
SO-2605-223 | Houzs Century | 4 | 4 | 2026-06-15 | 2026-07-02 | Late | 17
SO-2605-225 | Houzs Century | 2 | 2 | 2026-06-16 | 2026-07-02 | Late | 16
SO-2605-236 | Carress | 2 | 2 | 2026-06-17 | 2026-07-03 | Late | 16
SO-2605-273 | Houzs Century | 2 | 2 | 2026-06-16 | 2026-07-03 | Late | 17
SO-2605-290 | Houzs Century | 3 | 3 | 2026-06-19 | 2026-07-04 | Late | 15
SO-2605-106 | Houzs Century | 6 | 6 | 2026-06-22 | 2026-07-06 | Late | 14
SO-2605-303 | Carress | 2 | 2 | 2026-06-22 | 2026-07-07 | Late | 15
SO-2605-184 | Houzs Century | 3 | 3 | 2026-06-24 | 2026-07-08 | Late | 14
SO-2605-198 | Houzs Century | 2 | 2 | 2026-06-24 | 2026-07-08 | Late | 14
SO-2605-199 | Houzs Century | 2 | 2 | 2026-06-24 | 2026-07-09 | Late | 15
SO-2605-182 | Carress | 2 | 2 | 2026-06-25 | 2026-07-10 | Late | 15
SO-2605-224 | Houzs Century | 2 | 2 | 2026-06-26 | 2026-07-10 | Late | 14
CO-2605-008-01 | Houzs Century | 1 | 1 | 9999-12-31 | 2026-07-11 | On time
CO-2605-008-02 | Houzs Century | 1 | 1 | 9999-12-31 | 2026-07-11 | On time
SO-2605-301 | Carress | 1 | 1 | 2026-06-29 | 2026-07-11 | Late | 12